## VPI&S
HOUSTON VALVE CO., LTD.
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: On-off Valve(Butterfly) | [6 empty] | ITEM NO. : 0014
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [14 empty] | FOR FINAL |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | RST | IN | OUT | RST | IN | OUT | RST | IN | OUT | RST | IN | OUT | RST | IN | OUT | RST | FNL | TDB
1 | VP-TEP–I-0014-DO-0001-L | Vendor Print Index & Schedule | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 2; FOR FINAL IN: 05/19; FOR FINAL OUT: 07/15; FOR FINAL RST: 1
2 | VP-TEP–I-0014-DO-0002-L | Organization Chart | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 2
3 | VP-TEP–I-0014-DO-0003-L | Valve List | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 1
4 | VP-TEP–I-0014-DO-0004-L | Sub-Vendor List | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 2
5 | VP-TEP–I-0014-DO-0005-L | Spare Part List for 2 Years Operation | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 1
6 | VP-TEP–I-0014-CA-0006-L | Actuator Sizing Calculation | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 2
7 | VP-TEP–I-0014-19-0007-L | General Assembly Drawing | A4 |  | S | FOR APPROVAL IN: 2022/03/30; FOR APPROVAL IN: 2022/05/31; FOR FINAL IN: 2022/07/19
[5 empty] | A | FOR APPROVAL IN: 03/31; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 2; FOR APPROVAL IN: 05/19; FOR APPROVAL OUT: 07/05; FOR APPROVAL RST: 2; FOR FINAL IN: 08/10
8 | VP-TEP–I-0014-DA-0008-L | Data Sheet | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR APPROVAL IN: 2022/05/31; FOR FINAL IN: 2022/07/19
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 3; FOR APPROVAL IN: 05/19; FOR APPROVAL OUT: 07/05; FOR APPROVAL RST: 2; FOR FINAL IN: 08/10
9 | VP-TEP–I-0014-PR-0009-L | Inpection & Test Plan | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 1
10 | VP-TEP–I-0014-PR-0010-L | Inspection & Test Procedure | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 1
11 | VP-TEP–I-0014-PR-0011-L | Packing Procedure with Packing List | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 1
12 | VP-TEP–I-0014-PR-0012-L | PMI Procedure | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 1
13 | VP-TEP–I-0014-PR-0013-L | NDE Procedure | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 1
14 | VP-TEP–I-0014-DO-0014-L | Certificate(Including Fire Safe Design) | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 2
15 | VP-TEP–I-0014-DO-0015-L | Product Catalogue | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 1
16 | VP-TEP–I-0014-GU-0016-L | Installation, Operation & Maintenance Manual | A4 |  | S | FOR APPROVAL IN: 2022/03/11; FOR FINAL IN: 2022/05/31
[5 empty] | A | FOR APPROVAL IN: 03/11; FOR APPROVAL OUT: 05/17; FOR APPROVAL RST: 1
17 | VP-TEP–I-0014-DO-0017-L | Inspection and Test Report with IRN and Packing List | A4 |  | S | FOR APPROVAL IN: 2022/10/31; FOR FINAL IN: 2022/10/31
A
18 | VP-TEP–I-0014-DO-0018-L | Photos for KGS Stamp of Emergency Shutdown Valve | A4 |  | S | FOR APPROVAL IN: 2022/10/31; FOR FINAL IN: 2022/10/31
A
Note : |  | S/A : Schedule/Actual | RST : Result of V/P Review |  |  | FOR APPROVAL IN: N : Approved As Noted; FOR APPROVAL IN: RE : Reviewed with no comment; FOR FINAL IN: FNL : Final
|  | IN/OUT : Incoming/Outgoing | A: Approved |  |  | FOR APPROVAL IN: R : Rejected; FOR APPROVAL IN: RFC : Return For Correction; FOR FINAL IN: TDB : Technical Data Book
PROJECT NAME |  | TEP Project |  |  | PROJECT NO | FOR APPROVAL IN: -; FOR APPROVAL IN: ISSUED; FOR APPROVAL RST: A; FOR FINAL IN: 2022/03/11; FINAL TDB: B | 2022/05/19
P/O NO. |  | PO-TEP-I-0014-L |  |  | DATE | FOR APPROVAL IN: 2022. 08. 10; FOR APPROVAL RST: C; FOR FINAL IN: -; FINAL TDB: 0 | 2022/08/10