## VPI&S
I
KC corporation
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: WROUGHT FITTING | [6 empty] | ITEM NO. : P-0006
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [11 empty] | FOR FINAL |  |  |  | FOR FINAL |  |  |  | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-P-0006-DO-0001-L | Vendor Print Index & Schedule |  |  | S | A 2021.12.29 | [11 empty] | 0 2022.02.16 |  |  |  | 1 2022.03.31
[5 empty] | A | 12.29 |  | 001 | N | [8 empty] | 02.16 |  | 002 | N | 03.31 |  | 003 | A
2 | VP-TEP-P-0006-LI-0001-L | Sub Vendor List |  |  | S | A 2021.12.29 | [11 empty] | 0 2022.02.16 |  |  |  | 1 2022.03.31
[5 empty] | A | 12.29 |  | 001 | N | [8 empty] | 02.16 |  | 002 | N | 03.31 |  | 003 | A
3 | VP-TEP-P-0006-PR-0001-L | Inspection & Test Plan |  |  | S | A 2021.12.29 |  |  |  | B 2022.02.16 | [7 empty] | 0 2022.03.31
[5 empty] | A | 12.29 |  | 001 | R | 02.16 |  | 002 | N |  |  |  |  | 03.31 |  | 003 | A
4 | VP-TEP-P-0006-PR-0002-L | Inspection & Test Procedure |  |  | S | A 2021.12.29 |  |  |  | B 2022.02.16 | [7 empty] | 0 2022.03.31
[5 empty] | A | 12.29 |  | 001 | R | 02.16 |  | 002 | N |  |  |  |  | 03.31 |  | 003 | A
5 | VP-TEP-P-0006-PR-0003-L | NDE Procedure |  |  | S | A 2021.12.29 | [11 empty] | 0 2022.02.16 |  |  |  | 1 2022.03.31
[5 empty] | A | 12.29 |  | 001 | N | [8 empty] | 02.16 |  | 002 | N | 03.31 |  | 003 | A
6 | VP-TEP-P-0006-PR-0004-L | PMI Procedure |  |  | S | A 2021.12.29 |  |  |  | B 2022.02.16 | [7 empty] | 0 2022.03.31
[5 empty] | A | 12.29 |  | 001 | R | 02.16 |  | 002 | N |  |  |  |  | 03.31 |  | 003 | A
7 | VP-TEP-P-0006-PR-0005-L | WPS & PQR |  |  | S | A 2021.12.29 | [11 empty] | 0 2022.02.16 |  |  |  | 1 2022.03.31
[5 empty] | A | 12.29 |  | 001 | N | [8 empty] | 02.16 |  | 002 | N | 03.31 |  | 003 | A
8 | VP-TEP-P-0006-PR-0006-L | Marking & Color Coding Procedure |  |  | S | A 2021.12.29 | [11 empty] | 0 2022.02.16 |  |  |  | 1 2022.03.31
[5 empty] | A | 12.29 |  | 001 | N | [8 empty] | 02.16 |  | 002 | N | 03.31 |  | 003 | A
9 | VP-TEP-P-0006-PR-0007-L | PE Coating Procedure |  |  | S | A 2021.12.29 | [11 empty] | 0 2022.02.16 |  |  |  | 1 2022.03.31
[5 empty] | A | 12.29 |  | 001 | N | [8 empty] | 02.16 |  | 002 | N | 03.31 |  | 003 | N | 05.16 |  | 004
10 | VP-TEP-P-0006-PR-0008-L | Packing Procedure |  |  | S | [12 empty] | 0 2022.02.16 |  |  |  | 1 2022.03.31 |  |  |  | 2 2022.05.16
[5 empty] | A | [12 empty] | 02.16 |  | 002 | N | 03.31 |  | 003 | N | 05.16 |  | 004
11 | VP-TEP-P-0006-20-0001-L | Drawing |  |  | S | A 2021.12.29 | [11 empty] | 0 2022.02.16 |  |  |  | 1 2022.03.31 |  |  |  | 2 2022.05.16
[5 empty] | A | 12.29 |  | 001 | N | [8 empty] | 02.16 |  | 002 | N | 03.31 |  | 003 | A
12 | VP-TEP-P-0006-RE-0001-L | Inspection & Test Report |  |  | S | △
A
Note : |  | S/A : Schedule/Actual | RST : Result of V/P Review | [6 empty] | N : Approved As Noted | [7 empty] | FNL : Final
|  | IN/OUT : Incoming/Outgoing | A: Approved | [6 empty] | R : Rejected | [7 empty] | TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO | [8 empty] | ISSUED |  |  | 0 | [13 empty] | 2
P/O NO. |  | PO-TEP-P-0006-L |  |  | DATE | [11 empty] | 1 | [13 empty] | 3