## VPI&S
KC corporation
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: FLANGE | [6 empty] | ITEM NO. : P-0007
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [7 empty] | FOR FINAL |  |  |  | FOR FINAL |  |  |  | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-P-0007-DO-0001-L | Vendor Print Index & Schedule |  |  | S | A 2021.12.15 | [7 empty] | 0 2022.02.15
[5 empty] | A | 12.15 | 01.25 | 001 | N |  |  |  |  | 02.15 |  | 002 | A
2 | VP-TEP-P-0007-PR-0001-L | Inspection & Test Plan |  |  | S | A 2021.12.15 | [7 empty] | 0 2022.02.15 |  |  |  | 1 2022.04.04
[5 empty] | A | 12.15 | 01.25 | 001 | N |  |  |  |  | 02.15 |  | 002 | N | 04.04 |  | 003
3 | VP-TEP-P-0007-PR-0002-L | Inspection & Test Procedure |  |  | S | A 2021.12.15 | [7 empty] | 0 2022.02.15 |  |  |  | 1 2022.04.04
[5 empty] | A | 12.15 | 01.25 | 001 | N |  |  |  |  | 02.15 |  | 002 | N | 04.04 |  | 003
4 | VP-TEP-P-0007-20-0001-L | Drawing |  |  | S | A 2021.12.15 | [7 empty] | 0 2022.02.15
[5 empty] | A | 12.15 | 01.25 | 001 | N |  |  |  |  | 02.15 |  | 002 | A
5 | VP-TEP-P-0007-PR-0003-L | PMI Procedure |  |  | S | A 2021.12.15 | [7 empty] | 0 2022.02.15 |  |  |  | 1 2022.04.04
[5 empty] | A | 12.15 | 01.25 | 001 | N |  |  |  |  | 02.15 |  | 002 | A | 04.04 |  | 004
6 | VP-TEP-P-0007-PR-0004-L | Marking & Color Coding Procedure |  |  | S | A 2021.12.15 | [7 empty] | 0 2022.02.15 |  |  |  | 1 2022.04.04
[5 empty] | A | 12.15 | 01.25 | 001 | N |  |  |  |  | 02.15 |  | 002 | A | 04.04 |  | 004
7 | VP-TEP-P-0007-PR-0005-L | Packing Procedure |  |  | S | A 2021.12.15 | [7 empty] | 0 2022.02.15
[5 empty] | A | 12.15 | 01.25 | 001 | A |  |  |  |  | 02.15 |  | 002 | A
8 | VP-TEP-P-0007-RE-0001-L | Inspection & Test Report |  |  | S
A
9 |  |  |  |  | S
A
10 |  |  |  |  | S
A
Note : |  | S/A : Schedule/Actual | RST : Result of V/P Review | [6 empty] | N : Approved As Noted |  |  |  | FNL : Final
|  | IN/OUT : Incoming/Outgoing | A: Approved | [6 empty] | R : Rejected |  |  |  | TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | - | [16 empty] | 2
P/O NO. |  | PO-TEP-P-0007-L-01 |  |  | DATE |  |  |  |  | 2021.12.15 | [16 empty] | 3