## VPI&S
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: | [8 empty] | ITEM NO. : |  | E0003 | [8 empty] | Updated Date : |  |  | 2022-09-28
NO | DOCUMENT NO. | DOCUMENT TITLE | Aproval / Inform | First Issue Plan Date | SIZE | PAGE | S/A | FOR APPROVAL | [11 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[8 empty] | 1st |  |  |  | 2nd |  |  |  | 3rd
[8 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-E0003-PM-LI-0001 | Vendor Print Index Schedule | A | 2022.01.14 | A4 | 3 | S | 1.14
[7 empty] | A | 1.14 | 3.2 | 1 | 1 | 4.21 |  | 5
2 | VP-TEP-E0003-PM-OT-0001 | Organization Chart | A | 2022.01.14 | A4 | 2 | S | 1.14
[7 empty] | A | 1.14 | 3.2 | 1 | 1 | 4.21 |  | 5
3 | VP-TEP-E0003-EL-GA-0001 | General Arrangement Outline Drawing for GT (FKG1X) | A | 2022.03.02 | A3 | 13 | S | 3.2 | [17 empty] | Key V/P
[7 empty] | A | 2.11 | 3.17 | 2 | 3 | 4.19 | 5.26 | 4 | 1
4 | VP-TEP-E0003-EL-GA-0002 | General Arrangement Outline Drawing for ST (FKG1F) | A | 2022.03.02 | A3 | 12 | S | 3.2 | [17 empty] | Key V/P
[7 empty] | A | 2.11 | 3.17 | 2 | 3 | 4.19 | 5.26 | 4 | 1
5 | VP-TEP-E0003-EL-SQ-0001 | Elementary Diagram for GT #1 (FKG1X) | A | 2022.04.15 | A3 | 64 | S | 4.15
[7 empty] | A | 2.11 | 3.17 | 2 | 3 | 4.19 | 5.26 | 4 | 2
6 | VP-TEP-E0003-EL-SQ-0002 | Elementary Diagram for GT #2 (FKG1X) | A | 2022.04.15 | A3 | 64 | S | 4.15
[7 empty] | A | 2.11 | 3.17 | 2 | 3 | 4.19 | 5.26 | 4 | 2
7 | VP-TEP-E0003-EL-SQ-0003 | Elementary Diagram for ST (FKG1F) | A | 2022.06.15 | A3 | 59 | S | 4.15
[7 empty] | A | 2.11 | 3.17 | 2 | 3 | 4.19 | 5.26 | 4 | 2 | 7.22 |  | 7
8 | VP-TEP-E0003-EL-SP-0001 | Technical Datasheet for GT (FKG1X) | A | 2022.03.02 | A4 | 4 | S | 3.2 | [17 empty] | Key V/P
[7 empty] | A | 2.11 | 3.17 | 2 | 3 | 4.19 | 5.26 | 4 | 2
9 | VP-TEP-E0003-EL-SP-0002 | Technical Datasheet for ST (FKG1F) | A | 2022.03.02 | A4 | 4 | S | 3.2 | [17 empty] | Key V/P
[7 empty] | A | 2.11 | 3.17 | 2 | 3 | 4.19 | 5.26 | 4 | 2
10 | VP-TEP-E0003-EL-CF-0001 | SF6 Pressure Scale Drawing for GT (FKG1X) | A | 2022.03.02 | A3 | 3 | S | 3.2
[7 empty] | A | 2.11 | 3.17 | 2 | 1 | 4.21 |  | 5
11 | VP-TEP-E0003-EL-CF-0002 | SF6 Pressure Scale Drawing for ST (FKG1F) | A | 2022.03.02 | A3 | 3 | S | 3.2
[7 empty] | A | 2.11 | 3.17 | 2 | 1 | 4.21 |  | 5
12 | VP-TEP-E0003-EL-LI-0001 | Catalogue for GT (FKG1X) | A | 2022.01.14 | A4 | 3 | S | 1.14
[7 empty] | A | 1.14 | 3.2 | 1 | 2 | 4.21 |  | 5
13 | VP-TEP-E0003-EL-LI-0002 | Catalogue for ST (FKG1F) | A | 2022.01.14 | A4 | 3 | S | 1.14
[7 empty] | A | 1.14 | 3.2 | 1 | 2 | 4.21 |  | 5
14 | VP-TEP-E0003-EL-SP-0003 | Technical Datasheet for Current Transformer (CT) | A | 2022.08.15 | A4 |  | S | △
A
15 | VP-TEP-E0003-EL-SP-0004 | Technical Datasheet for Voltage Transformer (VT) | A | 2022.08.15 | A4 |  | S | △
A
16 | VP-TEP-E0003-EL-SP-0005 | Technical Datasheet for Motor | A | 2022.08.15 | A4 |  | S | △
A
17 | VP-TEP-E0003-EL-MA-0001 | Operation & Maintenance Manual | A | 2023.02.10 | A4 |  | S | △
A
18 | VP-TEP-E0003-EL-PR-0001 | Packing, Shipping and Transportation Procedure for GT (FKG1X) | A | 2022.10.20 | A4 |  | S | △
A
19 | VP-TEP-E0003-EL-PR-0002 | Packing, Shipping and Transportation Procedure for ST (FKG1F) | A | 2022.12.20 | A4 |  | S | △
A
20 | VP-TEP-E0003-EL-OT-0001 | Nameplate for GT (FKG1X) | A | 2022.04.15 | A3 | 3 | S | 4.15
[7 empty] | A | 2.11 | 3.17 | 2 | 1 | 4.21 |  | 5
21 | VP-TEP-E0003-EL-OT-0002 | Nameplate for ST (FKG1F) | A | 2022.04.15 | A3 | 3 | S | 4.15
[7 empty] | A | 2.11 | 3.17 | 2 | 1 | 4.21 |  | 5
22 | VP-TEP-E0003-EL-SQ-0004 | Interlocking Diagram for GT (FKG1X) | A | 2022.04.15 | A3 | 12 | S | 4.15
[7 empty] | A | 2.11 | 3.17 | 2 | 1 | 4.21 |  | 5
23 | VP-TEP-E0003-EL-SQ-0005 | Interlocking Diagram for ST (FKG1F) | A | 2022.04.15 | A3 | 11 | S | 4.15
[7 empty] | A | 2.11 | 3.17 | 2 | 1 | 4.21 |  | 5
24 | VP-TEP-E0003-EL-PR-0003 | Painting and Coating Procedure | A | 2022.04.15 | A4 | 7 | S | 4.15
[7 empty] | A | 2.11 | 3.17 | 2 | 3 | 4.19 | 5.26 | 4 | 1
25 | VP-TEP-E0003-QA-PL-0001 | Factory Inspection & Test Plan | A | 2022.01.14 | A4 | 21 | S | 1.14 | [17 empty] | Key V/P
[7 empty] | A | 1.14 | 3.2 | 1 | 3
26 | VP-TEP-E0003-QA-PR-0001 | Factory Inspection & Test Procedure | A | 2022.01.14 | A4 | 14 | S | 1.14 | [17 empty] | Key V/P
[7 empty] | A | 1.14 | 3.2 | 1 | 3
27 | VP-TEP-E0003-QA-RE-0001 | Factory Inspection & Test Report | A | 2022.10.25 | A4 |  | S | △
A
28 | VP-TEP-E0003-QA-PL-0002 | Site Inspection & Test Plan | A | 2023.02.10 | A4 |  | S | △
A
29 | VP-TEP-E0003-QA-PR-0002 | Site Inspection & Test Procedure | A | 2023.02.10 | A4 |  | S | △
A
30 | VP-TEP-E0003-QA-RE-0002 | Site Inspection & Test Report | A | 2023.06.07 | A4 |  | S | △
A
31 | VP-TEP-E0003-EL-LI-0003 | Load List for GT (FKG1X) | A | 2022.03.02 | A4 | 2 | S | 3.2 | [17 empty] | Key V/P
[7 empty] | A | 2.11 | 3.17 | 2 | 3
32 | VP-TEP-E0003-EL-LI-0004 | Load List for ST (FKG1F) | A | 2022.03.02 | A4 | 2 | S | 3.2 | [17 empty] | Key V/P
[7 empty] | A | 2.11 | 3.17 | 2 | 3
33 | VP-TEP-E0003-QA-PR-0003 | WPS & PQR | A | 2022.03.02 | A4 | 28 | S | 3.2
[7 empty] | A | 2.25 | 3.17 | 3 | 2
34 | VP-TEP-E0003-EL-LI-0005 | Special Tool List | A | 2022.03.02 | A4 | 2 | S | 3.2
[7 empty] | A | 2.11 | 3.17 | 2 | 1 | 4.21 |  | 5
35 | VP-TEP-E0003-EL-LI-0006 | Spare Part List | A | 2022.03.02 | A4 | 2 | S | 3.2
[7 empty] | A | 2.11 | 3.17 | 2 | 1 | 4.21 |  | 5
36 | VP-TEP-E0003-EL-LI-0007 | Sub Vendor List | A | 2022.03.02 | A4 | 4 | S | 3.2 | [17 empty] | Key V/P
[7 empty] | A | 2.11 | 3.17 | 2 | 2
Note : |  | S/A : Schedule/Actual | [12 empty] | RST : Result of V/P Review |  |  |  |  | N : Approved As Noted |  |  |  | FNL : Final
|  | IN/OUT : Incoming/Outgoing | [12 empty] | A: Approved |  |  |  |  | R : Rejected |  |  |  | TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  |  |  | PROJECT NO
P/O NO. |  | PO-TEP-E-0003-P |  |  |  |  | DATE