## VPI&S
I
(주)케이씨
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: Cathodic Protection System | [6 empty] | ITEM NO. : E0009
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [15 empty] | FOR CONSTRUCTION | [7 empty] | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | CODE | IN | OUT | TR# | CODE | IN | OUT | TR# | CODE | IN | OUT | TR# | CODE | IN | OUT | TR# | CODE | IN | OUT | TR# | CODE | FNL | TDB
1 | VP-TEP-E0009-EL-LI-0001 | Vendor Print Index & Schedule for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 4 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
2 | VP-TEP-E0009-PM-OT-0001 | Project Organization Chart for Cathodic Protection System |  |  | S | 2021.09.17 | [15 empty] | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 2 | [12 empty] | 21.11.30 |  | 0004
3 | VP-TEP-E0009-EL-BM-0001 | Bill of Material for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 3 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
4 | VP-TEP-E0009-EL-LI-0002 | Sub-Vendor List for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 3 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
5 | VP-TEP-E0009-EL-SP-0001 | Technical Specification for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 4 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
6 | VP-TEP-E0009-EL-CA-0001 | Design Calculation for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 4 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
7 | VP-TEP-E0009-EL-LI-0003 | Electrical Load List for Cathodic Protection System |  |  | S | 2021.09.17 | [15 empty] | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 2 | [12 empty] | 21.11.30 |  | 0004
8 | VP-TEP-E0009-EL-DS-0001 | Equipment and Component for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 3 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
9 | VP-TEP-E0009-EL-PR-0001 | Painting Procedure for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 3 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
10 | VP-TEP-E0009-EL-PR-0002 | Packing & Transportation Procedure for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 4 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
11 | VP-TEP-E0009-EL-MA-0001 | Installation Manual for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 4 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
12 | VP-TEP-E0009-EL-MA-0002 | Operation & Maintenance Manual for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 4 | 21.11.30 | 22.01.13 | 0005 | 1
13 | VP-TEP-E0009-QA-PL-0001 | Shop Inspection and Test Plan for Cathodic Protection System |  |  | S | 2021.09.17 | [15 empty] | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 1 | [12 empty] | 21.11.30 |  | 0004
14 | VP-TEP-E0009-QA-PR-0001 | Shop Inspection and Test Procedure for Cathodic Protection System |  |  | S | 2021.09.17 | [15 empty] | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 2 | [12 empty] | 21.11.30 |  | 0004
15 | VP-TEP-E0009-QA-RE-0001 | Shop Test Report for Cathodic Protection System |  |  | S | 2022.07.11
A
16 | VP-TEP-E0009-QA-PL-0002 | SAT Inspection and Test Plan for Cathodic Protection System |  |  | S | 2021.09.17 | [15 empty] | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 2 | [12 empty] | 21.11.30 |  | 0004
17 | VP-TEP-E0009-QA-PR-0002 | SAT Inspection and Test Procedure for Cathodic Protection System |  |  | S | 2021.09.17 | [15 empty] | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 1 | [12 empty] | 21.11.30 |  | 0004
18 | VP-TEP-E0009-QA-RE-0002 | SAT Test Report for Cathodic Protection System |  |  | S | 2022.11.30
A
19 | VP-TEP-E0009-EL-GA-0001 | Overall Plot Plan for Cathodic Protection System |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25 | [9 empty] | KEY VP
[5 empty] | A | 21.09.28 | 21.12.03 | 0002 | 3 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
20 | VP-TEP-E0009-EL-GA-0002 | Cathodic Protection System Plan for Tank Bottom |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [21 empty] | KEY VP
[5 empty] | A | 21.09.28 | 21.12.03 | 0002 | 3 | 21.11.30 | 22.01.13 | 0005 | 1
Note : |  | S/A : Schedule/Actual | CODE : Result of V/P Review | [6 empty] | CODE 1: Approved | [7 empty] | CODE 2 : Approved with Comment | [7 empty] | FNL : Final
|  | IN/OUT : Incoming/Outgoing | CODE 3 : Reviewed with comment | [6 empty] | CODE 4: Rejected | [7 empty] | RFC : Return For Correction | [7 empty] | TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | C012-115453 | [11 empty] | ISSUED |  | B | A | 2021. 09. 17. |  |  |  |  | C | 2022.01.25
P/O NO. |  | PO-TEP-E-0009-P |  |  | DATE |  |  |  |  | 2021. 08. 12. | [14 empty] | B | 2021. 11. 30. |  |  |  |  | D
(주)케이씨
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: Cathodic Protection System | [6 empty] | ITEM NO. : E0009
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [15 empty] | FOR CONSTRUCTION | [7 empty] | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | CODE | IN | OUT | TR# | CODE | IN | OUT | TR# | CODE | IN | OUT | TR# | CODE | IN | OUT | TR# | CODE | IN | OUT | TR# | CODE | FNL | TDB
21 | VP-TEP-E0009-EL-GA-0003 | Cathodic Protection System Plan for Underground Pipeline |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25 | [9 empty] | KEY VP
[5 empty] | A | 21.10.15 | 21.12.03 | 0003 | 3 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
22 | VP-TEP-E0009-EL-GA-0004 | Rectifier & Test Box for Cathodic Protection System (Tank Bottom) |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 |  |  |  | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 3 | 21.11.30 | 22.01.13 | 0005 | 3 | 22.01.25 |  | 0007
23 | VP-TEP-E0009-EL-GA-0005 | Rectifier & Anode Junction Box & Test Box for Cathodic Protection System (Underground Pipeline) |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 3 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
24 | VP-TEP-E0009-EL-SQ-0001 | Schematic Diagram for Cathodic Protection System (Tank Bottom) |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 |  |  |  | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 3 | 21.11.30 | 22.01.13 | 0005 | 3 | 22.01.25 |  | 0007
25 | VP-TEP-E0009-EL-SQ-0002 | Schematic Diagram for Cathodic Protection System (Underground Pipeline) |  |  | S | 2021.09.17 | [15 empty] | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 2 | [12 empty] | 21.11.30 |  | 0004
26 | VP-TEP-E0009-EL-ID-0001 | Installation Detail for Cathodic Protection System (Tank Bottom) |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 3 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
27 | VP-TEP-E0009-EL-ID-0002 | Installation Detail for Cathodic Protection System (Underground Pipeline) |  |  | S | 2021.09.17 | [15 empty] | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 1 | [12 empty] | 21.11.30 |  | 0004
28 | VP-TEP-E0009-EL-CS-0001 | Connection Diagram for Cathodic Protection System (Tank Bottom) |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.09.28 | 21.12.03 | 0002 | 3 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
29 | VP-TEP-E0009-EL-CS-0002 | Connection Diagram for Cathodic Protection System (Underground Pipeline) |  |  | S | 2021.09.17 |  |  |  | 2021.11.30 | [11 empty] | 2022.01.25
[5 empty] | A | 21.10.15 | 21.12.03 | 0003 | 3 | 21.11.30 | 22.01.13 | 0005 | 1 | [8 empty] | 22.01.25 |  | 0006
30 | VP-TEP-E0009-EL-LI-0004 | Spare Part for Two(2) Year Operation of Cathodic Protection System |  |  | S | 2021.09.17 | [15 empty] | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 1 | [12 empty] | 21.11.30 |  | 0004
31 | VP-TEP-E0009-EL-LI-0005 | Special Tool for Cathodic Protection System |  |  | S | 2021.09.17 | [15 empty] | 2021.11.30
[5 empty] | A | 21.09.17 | 21.11.18 | 0001 | 1 | [12 empty] | 21.11.30 |  | 0004
32 | - | - |  |  | S
A
33 | - | - |  |  | S
A
34 | - | - |  |  | S
A
35 | - | - |  |  | S
A
36 | - | - |  |  | S
A
37 | - | - |  |  | S
A
38 | - | - |  |  | S
A
39 | - | - |  |  | S
A
40 | - | - |  |  | S
A
Note : |  | S/A : Schedule/Actual | CODE : Result of V/P Review | [6 empty] | CODE 1: Approved | [7 empty] | CODE 2 : Approved with Comment | [7 empty] | FNL : Final
|  | IN/OUT : Incoming/Outgoing | CODE 3 : Reviewed with comment | [6 empty] | CODE 4: Rejected | [7 empty] | RFC : Return For Correction | [7 empty] | TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | C012-115453 | [11 empty] | ISSUED |  | B | A | 2021. 09. 17. |  |  |  |  | C | 2022.01.25
P/O NO. |  | PO-TEP-E-0009-P |  |  | DATE |  |  |  |  | 2021. 08. 12. | [14 empty] | B | 2021. 11. 30. |  |  |  |  | D
A
B
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
A
B
B
B
B
B
B
B
B
B
B
B
B
B
A
B
B
B
B
A
B
C
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
C