## Sheet1
NAME OF EQUIPMENT : FIRE FIGHTING EQUIPMENT
NO | DOCUMENT No | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-F0001-FF-LI-0001 | Vendor Print Index & Schedule | A4 | 3 | S | △ | 2022-01-21 |  |  | △ | 2022-03-10
[5 empty] | A | 1.26 | 2.25 | 1 | N | 3.24 |  | 3
3 | VP-TEP-F0001-FF-LI-0003 | Sub Vendor List | A4 | 3 | S | △ | 2022-01-21 |  |  | △ | 2022-03-10
[5 empty] | A | 1.26 | 2.25 | 1 | A | 3.24 |  | 3
4 | VP-TEP-F0001-FF-DS-0001 | Data Sheet | A4 | 6 | S | △ | 2022-01-21 |  |  | △ | 2022-03-10
[5 empty] | A | 1.26 | 2.25 | 1 | N | 3.24 |  | 3
5 | VP-TEP-F0001-FF-TD-0001 | Drawing | A4 | 12 | S | △ | 2022-01-21 |  |  | △ | 2022-03-10
[5 empty] | A | 1.26 | 2.25 | 1 | N | 3.24 |  | 3
6 | VP-TEP-F0001-FF-OT-0001 | Catalog | A4 | 13 | S | △ | 2022-01-21 |  |  | △ | 2022-03-10
[5 empty] | A | 1.26 | 2.25 | 1 | A | 3.24 |  | 3
7 | VP-TEP-F0001-FF-RE-0001 | Inspection & Test Report | A4 |  | S | △ | 2022-04-11
A
8 | VP-TEP-F0001-FF-PR-0001 | Inspection & Test Plan | A4 | 3 | S | △ | 2022-01-28 |  |  | △ | 2022-03-10
[5 empty] | A | 1.26 | 2.25 | 1 | N | 3.22 |  | 2
9 | VP-TEP-F0001-FF-PR-0002 | Inspection & Test Procedure | A4 | 8 | S | △ | 2022-01-28 |  |  | △ | 2022-03-10
[5 empty] | A | 1.26 | 2.25 | 1 | N | 3.22 |  | 2
10 | VP-TEP-F0001-FF-PR-0003 | Painting Procedure | A4 | 10 | S | △ | 2022-01-28 |  |  | △ | 2022-03-10
[5 empty] | A | 1.26 | 2.25 | 1 | N | 3.22 |  | 2
11 | VP-TEP-F0001-FF-PR-0004 | Packing Procedure | A4 | 7 | S | △ | 2022-01-28 |  |  | △ | 2022-03-10
[5 empty] | A | 1.26 | 2.25 | 1 | N | 3.22 |  | 2
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | - | [11 empty] | ISSUED |  |  | A | 2022-01-26 |  |  |  |  | 2
P/O NO. |  | PO-TEP-F-0001-P |  |  | DATE |  |  |  |  | 2022-01-26 | [14 empty] | 0 | 2022-03-24 |  |  |  |  | 3