## VPI&S
I
국제M&P
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: MOV & ON-OFF (GATE, GLOBE VALVE) | [6 empty] | ITEM NO. :
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-I0022-IN-LI-0001 | Vendor Print Index & Schedule | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 08
[5 empty] | A | FOR APPROVAL IN: 8/10
2 | VP-TEP-I0022-IN-LI-0002 | Sub-Vendor List | A4 |  | S | FOR APPROVAL IN: △ 2022. 08. 22
A
3 | VP-TEP-I0022-IN-LI-0003 | Organization Chart | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 08
[5 empty] | A | FOR APPROVAL IN: 8/10
4 | VP-TEP-I0022-IN-LI-0004 | General Assembly Drawings | A3 |  | S | FOR APPROVAL IN: △ 2022. 07. 08
[5 empty] | A | FOR APPROVAL IN: 8/10
5 | VP-TEP-I0022-IN-LI-0005 | Power & Utility Consumption List | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 08
[5 empty] | A | FOR APPROVAL IN: 8/10
6 | VP-TEP-I0022-IN-LI-0006 | Spare Part List (2year, Commissioning, Installation and pre-commissioning) | A4 |  | S | FOR APPROVAL IN: △ 2022. 08. 22
A
7 | VP-TEP-I0022-IN-LI-0007 | Special Tool List | A4 |  | S | FOR APPROVAL IN: △ 2022. 08. 22
A
8 | VP-TEP-I0022-IN-LI-0008 | MOV List | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 08
A
9 | VP-TEP-I0022-IN-DS-0001 | Data Sheet | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 08
[5 empty] | A | FOR APPROVAL IN: 8/10
10 | VP-TEP-I0022-IN-WD-0001 | Wiring and Tubing Diagram | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 08
[5 empty] | A | FOR APPROVAL IN: 8/10
11 | VP-TEP-I0022-IN-CA-0001 | Calculation Sheet | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 08
[5 empty] | A | FOR APPROVAL IN: 8/10
12 | VP-TEP-I0022-IN-PL-0001 | Inspection and Test Plan | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 15
[5 empty] | A | FOR APPROVAL IN: 8/18
13 | VP-TEP-I0022-IN-PR-0001 | Inspection and Test Procedure | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 15
[5 empty] | A | FOR APPROVAL IN: 8/18
14 | VP-TEP-I0022-IN-PR-0002 | Painting Procedure | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 15
[5 empty] | A | FOR APPROVAL IN: 8/18
15 | VP-TEP-I0022-IN-PR-0003 | Packing Procedure | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 15
[5 empty] | A | FOR APPROVAL IN: 8/18
16 | VP-TEP-I0022-IN-PR-0004 | PMI Procedure | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 15
[5 empty] | A | FOR APPROVAL IN: 8/18
17 | VP-TEP-I0022-IN-PR-0005 | NDE Procedure | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 15
[5 empty] | A | FOR APPROVAL IN: 8/18
18 | VP-TEP-I0022-IN-MA-0001 | O&M Manual | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 15
[5 empty] | A | FOR APPROVAL IN: 8/18
19 | VP-TEP-I0022-IN-OT-0001 | Valve Catalog | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 08
[5 empty] | A | FOR APPROVAL IN: 8/10
20 | VP-TEP-I0022-IN-OT-0002 | WPS&PQR with weld map | A4 |  | S | FOR APPROVAL IN: △ 2022. 07. 08
[5 empty] | A | FOR APPROVAL IN: 8/18
21 | VP-TEP-I0022-IN-OT-0003 | Welder List and Welder Qualification Record | A4 |  | S
A
22 | VP-TEP-I0022-IN-OT-0004 | Inspection and Test Report | A4 |  | S | FOR APPROVAL IN: △ Within 2weeks after delivery
A
Note : |  | S/A : Schedule/Actual | RST : Result of V/P Review |  |  | FOR APPROVAL IN: N : Approved As Noted; FOR APPROVAL IN: RE : Reviewed with no comment; FOR FINAL IN: FNL : Final
|  | IN/OUT : Incoming/Outgoing | A: Approved |  |  | FOR APPROVAL IN: R : Rejected; FOR APPROVAL IN: RFC : Return For Correction; FOR FINAL IN: TDB : Technical Data Book
PROJECT NAME |  | TEP Project |  |  | PROJECT NO | FOR APPROVAL IN: 400051; FOR APPROVAL IN: ISSUED; FOR APPROVAL RST: 0; FINAL TDB: 2
P/O NO. |  | PO-TEP-I-0022-P |  |  | DATE | FOR APPROVAL IN: 2022. 08. 10; FOR APPROVAL RST: 1; FINAL TDB: 3
KM&P