## VPI&S
I
국제M&P
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: MOV (BUTTERFLY VALVE) | [6 empty] | ITEM NO. :
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-I0024-IN-LI-0001 | Vendor Print Index & Schedule | A4 |  | S | △ 2022. 05. 31
[5 empty] | A | 6/8 |  |  | #001
2 | VP-TEP-I0024-IN-LI-0002 | Sub-Vendor List | A4 |  | S | △ 2022. 05. 31
[5 empty] | A | 6/8 |  |  | #001
3 | VP-TEP-I0024-IN-LI-0003 | Organization Chart | A4 |  | S | △ 2022. 05. 31
[5 empty] | A | 6/8 |  |  | #001
4 | VP-TEP-I0024-IN-LI-0004 | General Assembly Drawings | A3 |  | S | △ 2022. 05. 31
[5 empty] | A | 6/8 |  |  | #001
5 | VP-TEP-I0024-IN-LI-0005 | Power & Utility Consumption List | A4 |  | S | △ 2022. 06. 10
[5 empty] | A | 7/22
6 | VP-TEP-I0024-IN-DS-0001 | Data Sheet | A4 |  | S | △ 2022. 06. 10
[5 empty] | A | 7/22
7 | VP-TEP-I0024-IN-WD-0001 | Wiring and Tubing Diagram | A4 |  | S | △ 2022. 06. 10
[5 empty] | A | 7/22
8 | VP-TEP-I0024-IN-CA-0001 | Calculation Sheet | A4 |  | S | △ 2022. 06. 10
[5 empty] | A | 7/22
9 | VP-TEP-I0024-IN-PL-0001 | Inspection and Test Plan | A4 |  | S | △ 2022. 06. 10
[5 empty] | A | 7/22
10 | VP-TEP-I0024-IN-PR-0001 | Inspection and Test Procedure | A4 |  | S | △ 2022. 06. 10
[5 empty] | A | 7/22
11 | VP-TEP-I0024-IN-PR-0002 | Painting Procedure | A4 |  | S | △ 2022. 06. 10
[5 empty] | A | 7/22
12 | VP-TEP-I0024-IN-PR-0003 | Packing Procedure | A4 |  | S | △ 2022. 06. 10
[5 empty] | A | 7/22
13 | VP-TEP-I0024-IN-PR-0004 | PMI Procedure | A4 |  | S | △ 2022. 06. 10
[5 empty] | A | 7/22
15 | VP-TEP-I0024-IN-MA-0001 | O&M Manual | A4 |  | S | △ 2022. 06. 10
[5 empty] | A | 7/22
16 | VP-TEP-I0024-IN-OT-0001 | Inspection and Test Report | A4 |  | S | △ Within 2weeks after delivery
A
[5 empty] | S | △
A
[5 empty] | S | △
A
Note : |  | S/A : Schedule/Actual | RST : Result of V/P Review | [6 empty] | N : Approved As Noted | [7 empty] | RE : Reviewed with no comment | [7 empty] | FNL : Final
|  | IN/OUT : Incoming/Outgoing | A: Approved | [6 empty] | R : Rejected | [7 empty] | RFC : Return For Correction | [7 empty] | TDB : Technical Data Book
PROJECT NAME |  | TEP Project |  |  | PROJECT NO |  |  |  |  | 400051 | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-I-0024-P |  |  | DATE |  |  |  |  | 2022. 07. 22 | [14 empty] | 1 | [5 empty] | 3
KM&P