## Table 1
㈜ 대덕기술
NAME OF EQUIPMENT: Ultrasonic Flowmeter | [7 empty] | VENDOR PRINT INDEX & SCHEDULE | [13 empty] | ITEM NO. |  | : PO-TEP-I-0029-P
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [11 empty] | FOR FINAL |  |  |  | FINAL |  |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-I0029-PM-LI-0001 | VENDOR PRINT INDEX & SCHEDULE | A4 | 2 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
2 | VP-TEP-I0029-PM-OT-0001 | PROJECT ORGANIZATION | A4 | 2 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
3 | VP-TEP-I0029-PM-SC-0001 | PROJECT SCHEDULE | A4 | 2 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
4 | VP-TEP-I0029-IN-LI-0002 | BILL OF MATERIAL | A4 | 2 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
5 | VP-TEP-I0029-IN-LI-0003 | UTILITY CONSUMPTION LIST | A4 | 2 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
6 | VP-TEP-I0029-IN-DS-0001 | SPECIFICATION | A4 | 2 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
7 | VP-TEP-I0029-IN-CA-0001 | SIZING CALCULATION | A4 | 3 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
8 | VP-TEP-I0029-IN-ID-0001 | DIMENSION DRAWING | A4 | 3 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
9 | VP-TEP-I0029-IN-CF-0001 | SYSTEM CONFIGURATION | A4 | 2 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
10 | VP-TEP-I0029-IN-OT-0001 | CATALOG | A4 | 23 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
11 | VP-TEP-I0029-IN-LI-0003 | UTILITY CONSUMPTION LIST | A4 | 2 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
12 | VP-TEP-I0029-IN-OT-0002 | CERTIFICATE | A4 | 5 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
13 | VP-TEP-I0029-QA-PL-0001 | INSPECTION & TEST PLAN | A4 | 2 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
14 | VP-TEP-I0029-QA-PR-0001 | INSPECTION & TEST PROCEDURE | A4 | 5 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
15 | VP-TEP-I0029-QA-PR-0002 | PACKING PROCEDURE | A4 | 8 | S | A | 2022-08-31
[5 empty] | A | 2022-08-31 |  | 1
16 | VP-TEP-I0029-PM-RE-0001 | MONTHLY PROGRESS REPORT | A4 | 3 | S | A | 2022-11-01
[5 empty] | A | 2022-11-01 |  | 1
17 | VP-TEP-I0029-QA-OT-0001 | INSPECTION REPORT | A4 | 5 | S | A | 2022-12-05
[5 empty] | A | 2022-12-05 |  | 1
Note : S/A : Schedule/Actual IN/OUT : Incoming/Outgoing |  |  | RST : Result of V/P Review A: Approved |  |  |  |  | N : Approved As Noted R : Rejected | [9 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | TEP PROJECT |  |  | PROJECT NO |  |  |  |  | - | [6 empty] | ISUUED | 0 |  |  |  | 2
P/O NO. |  | PO-TEP-I-0029-P |  |  | DATE |  |  |  |  | 2022-08-04 | [7 empty] | 1 |  |  |  | 3
KDHEC 제어:
Datasheet & List 로 수 정하고 LIST 추가반영 요.
적용대상이 하나인 경 우에도 LIST 는 제출 요.
KDHEC 제어:
하기 누락사항 추가요.
-Spare part list
->(installation, commissioning , 2 year spare part 포함)
-Electric Wiring Diagram
해당 V/P는 공식 도서에서는 제외하고 추후 MPR에만 추가바랍니다.
도서 제외 요망
Inspection & Test Report 로 수정
Item No. 는 빈칸 으로 반영 요망
PDF 파일 명은 하기와 같은 구조로 반영 요망
VP No._VP 타이틀_Rev.XX