## Sheet
PO-TEP-P-0001-P-01
Vendor Information | [5 empty] | Review Code From (HENC) | [12 empty] | Correspondence Legend
Name | : ㈜명진티에스알 언양공장 |  |  |  |  | 1 : Approved. (Vendor can proceed the next stage, Rev.0 ) | [12 empty] | Letter In :
Att. | : 이윤지 과장 |  |  |  |  | 2 : Approved with comment (Vendor can proceed the next stage, Rev.0 ) | [12 empty] | Letter Out :
Tel No. | : 02-2168-3381 |  |  |  |  | 3 : Reviewed with Comment. (Vendor have to re-issue as For Approval within ten (10) days of calendar days) | [12 empty] | TR In :
M No. | : 010-5507-9787 |  |  |  |  | 4 : Rejected (Vendor have to re-issue as For Approval within ten (10) days of calendar days as Rev.A ) | [12 empty] | TR Out :
Fax No. | : 02-2168-3383
E-mail | yjlee@mjtsr.com
Add. | :
PROJECT : 통영천연가스발전사업 | [11 empty] | If Required | [11 empty] | Date : | 2022-09-28
No. | DOCUMENT No. | Document Title | Class | Class | Rev. | From Vendor |  |  | KDHEC (9Days) |  |  | To Vendor |  |  | TEP Comment to HENC |  |  |  | To Vendor |  |  |  | Remarks
[6 empty] | Plan | Actual | TR# | Due Date | Actual | TR# | Actual | R.S. | TR# | Due Date | Actual | R.S. | TR# | Due Date | Actual | R.S | TR#
1 | VP-TEP-P0001-PI-LI-0001 | Vendor Print Index & Schedule |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
2 | VP-TEP-P0001-PI-LI-0002 | Organization Chart |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
3 | VP-TEP-P0001-PI-LI-0003 | Sub-Vendor List |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
4 | VP-TEP-P0001-PI-SC-0001 | Overall Schedule |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
5 | VP-TEP-P0001-PI-TD-0001 | Fabrication Isometric Drawing (Spool Drawing) |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
6 | VP-TEP-P0001-PI-PL-0001 | Inspection & Test Plan |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
7 | VP-TEP-P0001-PI-PR-0001 | Inspection & Test Procedure |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
8 | VP-TEP-P0001-PI-PR-0002 | WPS & PQR |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
9 | VP-TEP-P0001-PI-PR-0003 | NDE Procedure |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
10 | VP-TEP-P0001-PI-PR-0004 | Fabrication Procedure |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
11 | VP-TEP-P0001-PI-PR-0005 | Ext. PE Coating Procedure (Including Cold Tape Wrapping Procedure) |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
12 | VP-TEP-P0001-PI-PR-0006 | Int. Glass Flake Coating Procedure |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
13 | VP-TEP-P0001-PI-PR-0007 | Rubber Lining Procedure |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
14 | VP-TEP-P0001-PI-PR-0008 | Painting Procedure |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
15 | VP-TEP-P0001-PI-PR-0009 | Packing & Preservation Procedure |  |  | A | 2021-07-21 | 2021-07-22 | T-0001
B
0
16 | VP-TEP-P0001-PI-RE-0001 | Inspection & Test Report |  |  | A
B
0
Total |  |  |  | 0 | A | 15 | 15 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Plan | #REF! | Actual | #REF!
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | #REF! |  | #REF!

## Sheet1
□ Code 1 - Approved
□ Code 2 - Approved with comment
□ Code 3 - Reviewed with comment
□ Code 4 - Rejected
This Approval does not relieve the vendor/subcontractor of his responsibiliies to meet all requirement of the contract. In case of Review with Comment anf Rejected, vendor/subcontract shall not proceed until the re-submitted documents are returned to them by owner.
APPROVED BY : DATE :
HANWHA ENGINEERING & CONSTRUCTION CORP.