## Table 2
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: SS SMLS PIPE | [6 empty] | ITEM NO. : P-0004
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [15 empty] | FOR FINAL | [7 empty] | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-P0004-PI-LI-0001 | Vendor Print Index & Schedule | A4 | 2 | S | 2022-06-28
[5 empty] | A | 06월 28일 |  | 1
2 | VP-TEP-P0004-PI-PL-0001 | Inspection & Test Plan | A4 | 2 | S | 2022-06-28
[5 empty] | A | 06월 28일 |  | 1
3 | VP-TEP-P0004-PI-PR-0001 | Packing Procedure | A4 | 5 | S | 2022-06-28
[5 empty] | A | 06월 28일 |  | 1
4 | VP-TEP-P0004-PI-PR-0002 | Inspection & Test Procedure | A4 | 5 | S | 2022-06-28
[5 empty] | A | 06월 28일 |  | 1
5 | VP-TEP-P0004-PI-PR-0003 | Marking & Colorcoding Procedure | A4 | 3 | S | 2022-06-28
[5 empty] | A | 06월 28일 |  | 1
6 | VP-TEP-P0004-PI-PR-0004 | PMI Procedure | A4 | 7 | S | 2022-06-28
[5 empty] | A | 06월 28일 |  | 1
7 | VP-TEP-P0004-PI-RE-0001 | Inspection & test Report | A4 |  | S
A
8 |  |  |  |  | S | △
A
9 |  |  |  |  | S | △
A
10 |  |  |  |  | S | △
A
11 |  |  |  |  | S | △
A
12 |  |  |  |  | S | △
A
Note : |  | S/A : Schedule/Actual | RST : Result of V/P Review | [6 empty] | N : Approved As Noted | [7 empty] | RE : Reviewed with no comment | [7 empty] | FNL : Final
|  | IN/OUT : Incoming/Outgoing | A: Approved | [6 empty] | R : Rejected | [7 empty] | RFC : Return For Correction | [7 empty] | TDB : Technical Data Book
PROJECT NAME |  | TEP Project |  |  | PROJECT NO | [16 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-P-0004-P-01 |  |  | DATE |  |  |  |  | 2022-06-28 | [14 empty] | 1 | [5 empty] | 3