## Table 6
NAME OF EQUIPMENT: ALLOY STEEL PIPE
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [20 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT |  | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-P0006-PI-LI-0001 | Vendor Print Index & Schedule | A4 | 2 | S | △ |  | 2022-01-14 |  |  | 2022-04-15
[5 empty] | A | 1/19 | 2/16 |  | 1 | N | 6/2
2 | VP-TEP-P0006-PI-LI-0002 | Sub Vendor List | A4 | 2 | S | △ |  | 2022-01-14
[5 empty] | A | 1/19 | 2/16 |  | 1 | A
3 | VP-TEP-P0006-PI-PL-0001 | Inspection & Test Plan | A4 | 3 | S | △ |  | 2022-01-14 |  |  | 2022-02-28
[5 empty] | A | 1/19 | 2/16 |  | 2 | N | 3/16 | 4/7 | 6 | N
4 | VP-TEP-P0006-PI-PR-0002 | Inspection & Test Procedure | A4 | 5 | S | △ |  | 2022-01-14 |  |  | 2022-02-28 |  |  |  | 2022-04-15
[5 empty] | A | 1/19 | 2/16 |  | 2 | N | 3/16 | 4/7 | 6 | N | 6/2
5 | VP-TEP-P0006-PI-PR-0003 | WPS&PQR | A4 |  | S | △ |  | 2022-01-21 |  |  | 2022-02-28
[5 empty] | A | 1/26 | 2/16 |  | 3 | N | 3/4 | 4/7 | 4 | N
6 | VP-TEP-P0006-PI-PR-0004 | PMI Procedure | A4 | 6 | S | △ |  | 2022-01-14 |  |  | 2022-02-28
[5 empty] | A | 1/19 | 2/16 |  | 2 | N | 3/16 | 4/7 | 6 | N
7 | VP-TEP-P0006-PI-PR-0005 | Packing Procedure | A4 |  | S | △ |  | 2022-01-21 |  |  | 2022-04-15
[5 empty] | A | 3/8 | 4/7 |  | 5 | N | 6/2
8 | VP-TEP-P0006-PI-PR-0006 | Marking & Color Coding Procedure | A4 | 4 | S | △ |  | 2022-01-14
[5 empty] | A | 1/19 | 2/16 |  | 2 | N
9 | VP-TEP-P0006-PI-RE-0001 | Inspection & Test Report | A4 |  | S | △ |  | 2022-06-30
A
10 | VP-TEP-P0006-PI-PR-0007 | NDE Procedure | A4 |  | S | △ |  | 2022-04-15
[5 empty] | A | 6/2
11 |  |  |  |  | S
A
12 |  |  |  |  | S
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [7 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO | [5 empty] | - | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-P-0006-P-01 |  |  | DATE | [5 empty] | 2022. 6 . 2 | [14 empty] | 1 | [5 empty] | 3