## Table 7
NAME OF EQUIPMENT: STEAM & AIR TRAP
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-P0022-PI-LI-0001 | Vendor Print Index & Schedule | A4 | 2 | S | A
[5 empty] | A | 06-30 | 06-30 | 1
2 | VP-TEP-P0022-PI-TD-0001 | Assembly Drawing | A4 | 4 | S | A
[5 empty] | A | 06-30 | 06-30 | 1
3 | VP-TEP-P0022-PI-PR-0001 | Inspection & Test Procedure | A4 | 4 | S | A
[5 empty] | A | 06-30 | 06-30 | 1
4 | VP-TEP-P0022-PI-PL-0001 | Inspection & Test Plan | A4 | 2 | S | A
[5 empty] | A | 06-30 | 06-30 | 1
5 | VP-TEP-P0022-PI-PR-0002 | Painting Procedure | A4 | 4 | S | A
[5 empty] | A | 06-30 | 06-30 | 1
6 | VP-TEP-P0022-PI-PR-0003 | Packing Procedure | A4 | 11 | S | A
[5 empty] | A | 06-30 | 06-30 | 1
7 | VP-TEP-P0022-PI-PR-0005 | NDE Procedure | A4 | 23 | S | A
[5 empty] | A | 06-30 | 06-30 | 1
8 | VP-TEP-P0022-PI-PR-0006 | PMI Procedure | A4 | 10 | S | A
[5 empty] | A | 06-30 | 06-30 | 1
9 | VP-TEP-P0022-PI-LI-0002 | Sub Vendor List | A4 | 2 | S | A
[5 empty] | A | 06-30 | 06-30 | 1
10 | VP-TEP-P0022-PI-RE-0001 | Inspection & Test Report | A4 |  | S | △ | [25 empty] | LATER
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | TEP Project |  |  | PROJECT NO | [16 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-P-0022-P |  |  | DATE |  |  |  |  | 2022-06-30 | [14 empty] | 1 | [5 empty] | 3