## VPI&S_Fluff Transfer
Vendor Print Index & Schedule
NAME OF EQUIPMENT:Fluff Transfer
No. | Document No. | Document Title | Transmittal No. | Category "A/R/I" (For Approval / Review / Information) | Key VP | P/A | Issued for Approval | [11 empty] | Issue for Construction | [7 empty] | Final |  |  |  | Final Data Book |  |  |  | Remark
[7 empty] | Rev. A |  |  |  | Rev. B |  |  |  | Rev. C |  |  |  | Rev. 0 |  |  |  | Rev. 1 |  |  |  | N(for final)+1 |  |  |  | Later
[7 empty] | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST
General Documents
1 | VP-TEP-R0005-PM-LI-0001 | VENDOR PRINT INDEX & SCHEDULE |  | For Approval | O | P | TR-0003 | 2022.03.31
[6 empty] | A | 2022.07.12 | 2022.04.12 | TR-0001 | 3
2 | VP-TEP-R0005-PM-LI-0002 | UTILITY CONSUMPTION LIST |  | For Approval |  | P | TR-0002 | 2022.04.15
[6 empty] | A | 2022.07.05 | 2022.04.14 | TR-0002 | 2 |  | 2022.07.21 | TR-0017
3 | VP-TEP-R0005-PM-LI-0003 | LUBRICANT LIST |  | For Approval |  | P | TR-0002 | 2022.04.15
[6 empty] | A | 2022.07.05 | 2022.04.14 | TR-0002 | 2 |  | 2022.07.21 | TR-0017
4 | VP-TEP-R0005-PM-LI-0004 | SUB VENDOR LIST |  | For Approval | O | P |  | 2022.04.15
[6 empty] | A |  | 2022.04.15 | TR-0005
5 | VP-TEP-R0005-PM-LI-0005 | SPARE PARTS LIST |  | For Approval |  | P | TR-0002 | 2022.04.15
[6 empty] | A | 2022.07.05 | 2022.04.14 | TR-0002 | 2 |  | 2022.07.21 | TR-0017
6 | VP-TEP-R0005-PM-OT-0001 | 3D MODELING |  | For Approval |  | P | TR-0005 | 2022.09.15
[6 empty] | A | 2022.07.12 | 2022.05.17 | TR-0013 | 3
7 | VP-TEP-R0005-PM-PR-0001 | PACKING PROCEDURE |  | For Approval |  | P | TR-0008 | 2022.04.30
[6 empty] | A | 2022.7.19 | 2022.05.04 | TR-0008 | 3
8 | VP-TEP-R0005-PM-MA-0001 | O&M MANUAL FOR AIR COMPRESSOR |  | For Approval |  | P |  | 2022.10.15
A
9 | VP-TEP-R0005-PM-MA-0002 | O&M MANUAL FOR AIR DRYER PACKAGE |  | For Approval |  | P |  | 2022.10.15
A
Rotating Documents
10 | VP-TEP-R0005-RO-PI-0001 | P&I DRAWING FOR COMPRESSED AIR SYSTEM |  | For Approval | O | P | TR-0013 | 2022.04.30
[6 empty] | A | 2022.07.27 | 2022.05.03 | TR-0006 |  |  | 2022.08.09 | TR-0022
11 | VP-TEP-R0005-RO-PI-0002 | P&I DRAWING FOR AIR COMPRESSOR |  | For Approval | O | P | E-mail | 2022.04.30
[6 empty] | A | 2022.07.27 | 2022.05.03 | TR-0006 | [10 empty] | 2022.08.09 | TR-0022
12 | VP-TEP-R0005-RO-PI-0003 | P&I DRAWING FOR AIR DRYER |  | For Approval | O | P |  | 2022.04.30
[6 empty] | A |  | 2022.05.03 | TR-0006
13 | VP-TEP-R0005-RO-DS-0001 | DATA SHEET FOR AIR COMPRESSOR |  | For Approval |  | P | TR-0004 | 2022.04.15
[6 empty] | A | 2022.07.12 | 2022.04.14 | TR-0003 | 2
14 | VP-TEP-R0005-RO-OT-0001 | NAME PLATE DRAWING FOR AIR COMPRESSOR |  | For Approval |  | P |  | 2022.09.15
A
15 | VP-TEP-R0005-RO-OT-0002 | PERFORMANCE CURVE AND CORRECTION CURVE FOR AIR COMPRESSOR |  | For Approval |  | P | E-mail | 2022.04.30
[6 empty] | A | 2022.07.27 | 2022.05.03 | TR-0006 | [10 empty] | 2022.08.09 | TR-0022
16 | VP-TEP-R0005-RO-DS-0002 | DATA SHEET FOR AIR DRYER |  | For Approval |  | P |  | 2022.05.11
[6 empty] | A |  | 2022.05.11 | TR-0011
17 | VP-TEP-R0005-RO-CA-0001 | STRENGTH CALCULATION SHEET FOR AIR DRYER |  | For Approval |  | P |  | 2022.05.11
[6 empty] | A |  | 2022.05.11 | TR-0011
18 | VP-TEP-R0005-RO-OT-0003 | NAMEPLATE DRAWING FOR AIR DRYER |  | For Approval |  | P |  | 2022.09.15
A
19 | VP-TEP-R0005-RO-DS-0003 | DATA SHEET FOR AIR FILTER |  | For Approval |  | P |  | 2022.05.11
[6 empty] | A |  | 2022.05.11 | TR-0011
20 | VP-TEP-R0005-RO-CA-0002 | STRENGTH CALCULATION SHEET FOR AIR FILTER |  | For Approval |  | P |  | 2022.05.11
[6 empty] | A |  | 2022.05.11 | TR-0011
21 | VP-TEP-R0005-RO-OT-0004 | NAMEPLATE DRAWING FOR AIR FILTER |  |  |  | P |  | 2022.09.15
A
Civil Documents
22 | VP-TEP-R0005-CV-FA-0001 | FOUNDATION DRAWING & LOADING DATA FOR AIR COMPRESSOR |  | For Approval | O | P |  | 2022.05.07
[6 empty] | A |  | 2022.05.11 | TR-0011
23 | VP-TEP-R0005-CV-FA-0002 | FOUNDATION DIAGRAMS & LOADING DATA FOR AIR DRYER |  | For Approval | O | P |  | 2022.05.11
[6 empty] | A |  | 2022.05.11 | TR-0011
Piping Documents
24 | VP-TEP-R0005-PI-GA-0001 | GENERAL ARRANGEMENT DRAWING FOR COMPRESSED AIR SYSTEM |  | For Approval | O | P | TR-0005 | 2022.05.07
[6 empty] | A | 2022.07.12 | 2022.05.17 | TR-0013 | 3
25 | VP-TEP-R0005-PI-GA-0002 | GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSOR |  | For Approval | O | P | E-mail | 2022.04.30
[6 empty] | A | 2022.07.27 | 2022.05.03 | TR-0006 | [10 empty] | 2022.08.09 | TR-0022
26 | VP-TEP-R0005-PI-GA-0003 | GENERAL ARRANGEMENT DRAWING FOR AIR DRYER |  | For Approval | O | P | TR-0008 | 2022.05.11 |  |  | TR-0011
[6 empty] | A | 2022.7.19 | 2022.05.04 | TR-0008 | 2 | 2022.07.22 | 2022.07.21 | TR-0018 | 2
27 | VP-TEP-R0005-PI-GA-0004 | GENERAL ARRANGEMENT DRAWING FOR AIR FILTER |  | For Approval | O | P |  | 2022.05.11
[6 empty] | A |  | 2022.05.11 | TR-0011
28 | VP-TEP-R0005-PI-IS-0001 | ISO DRAWING FOR COMPRESSED AIR SYSTEM |  | For Approval |  | P |  | 2022.08.15
A
29 | VP-TEP-R0005-PI-PR-0001 | PAINTING PROCEDURE & SCHEDULE |  | For Approval |  | P | TR-0008 | 2022.04.30
[6 empty] | A | 2022.7.19 | 2022.05.04 | TR-0008 | 3
Electrical Documents
30 | VP-TEP-R0005-EL-LI-0001 | ELECTRIC LOAD LIST |  | For Approval | O | P | TR-0001 | 2022.04.15
[6 empty] | A | 2022.06.14 | 2022.04.14 | TR-0004 | 3
31 | VP-TEP-R0005-EL-SD-0001 | SINGLE LINE DIAGRAM FOR MASTER CONTROL PANEL |  | For Approval |  | P |  | 2022.05.07
[6 empty] | A |  | 2022.05.10 | TR-0010
32 | VP-TEP-R0005-EL-GA-0001 | PANEL LAYOUT & ARRANGEMENT DWG FOR MASTER CONTROL PANEL |  | For Approval |  | P |  | 2022.05.07
[6 empty] | A |  | 2022.05.10 | TR-0010
33 | VP-TEP-R0005-EL-SQ-0001 | PANEL SCHEMATIC & WIRING DIAGRAM FOR MASTER CONTROL PANEL |  | For Approval |  | P |  | 2022.05.07
[6 empty] | A |  | 2022.05.10 | TR-0010
34 | VP-TEP-R0005-EL-GA-0002 | LCP OUTLINE DRAWING FOR AIR COMPRESSOR |  | For Approval |  | P |  | 2022.05.07
[6 empty] | A |  | 2022.05.10 | TR-0010
35 | VP-TEP-R0005-EL-SD-0002 | SINGLE LINE DIAGRAM FOR AIR COMPRESSOR |  | For Approval |  | P |  | 2022.05.07
[6 empty] | A |  | 2022.05.10 | TR-0010
36 | VP-TEP-R0005-EL-SQ-0002 | SCHEMATIC & WIRING DIAGRAM FOR AIR COMPRESSOR |  | For Approval |  | P |  | 2022.05.07
[6 empty] | A |  | 2022.05.10 | TR-0010
37 | VP-TEP-R0005-EL-GA-0003 | LCP OUTLINE DRAWING FOR AIR DRYER |  | For Approval |  | P |  | 2022.06.03
[6 empty] | A |  | 2022.06.11 | TR-0016
38 | VP-TEP-R0005-EL-SD-0003 | SINGLE LINE DIAGRAM FOR AIR DRYER |  | For Approval |  | P |  | 2022.06.03
[6 empty] | A |  | 2022.06.11 | TR-0016
39 | VP-TEP-R0005-EL-SQ-0003 | SCHEMATIC & WIRING DIAGRAM FOR AIR DRYER |  | For Approval |  | P |  | 2022.06.03
[6 empty] | A |  | 2022.06.11 | TR-0016
40 | VP-TEP-R0005-EL-DS-0001 | MOTOR DATA SHEET & OUTLINE DRAWING FOR AIR COMPRESSOR |  | For Approval | O | P | TR-0009 | 2022.04.30
[6 empty] | A | 2022.07.19 | 2022.05.25 | TR-0014 | 3 |  | 2022.08.12 | TR-0024
Instrument Documents
41 | VP-TEP-R0005-IN-LI-0001 | PLC IO LIST FOR MASTER CONTROL PANEL |  | For Approval |  | P | TR-0010 | 2022.05.07
[6 empty] | A | 2022.07.21 | 2022.05.10 | TR-0009 | 3
42 | VP-TEP-R0005-IN-LI-0002 | DCS COMMUNICATION LIST FOR MASTER CONTROL PANEL |  | For Approval |  | P | TR-0010 | 2022.05.07
[6 empty] | A | 2022.07.21 | 2022.05.10 | TR-0009 | 3
43 | VP-TEP-R0005-IN-LD-0001 | PLC LOGIC DIAGRAM FOR MASTER CONTROL PANEL |  | For Approval |  | P | TR-0010 | 2022.05.07
[6 empty] | A | 2022.07.21 | 2022.05.10 | TR-0009 | 3
44 | VP-TEP-R0005-IN-LD-0002 | LOOP DIAGRAM FOR MASTER CONTROL PANEL |  | For Approval |  | P | TR-0010 | 2022.05.07
[6 empty] | A | 2022.07.21 | 2022.05.10 | TR-0009 | 2
45 | VP-TEP-R0005-IN-OT-0001 | INTERCONNECTING WIRING DIAGRAM FOR MASTER CONTROL PANEL |  | For Approval |  | P | TR-0010 | 2022.05.07
[6 empty] | A | 2022.07.21 | 2022.05.10 | TR-0009 | 3
46 | VP-TEP-R0005-IN-OT-0002 | LCD GRAPHIC SKETCH FOR MASTER CONTROL PANEL |  | For Approval |  | P | TR-0010 | 2022.05.07
[6 empty] | A | 2022.07.21 | 2022.05.10 | TR-0009 | 2
47 | VP-TEP-R0005-IN-CF-0001 | CONTROL SYSTEM CONFIGURATION DIAGRAM FOR MASTER CONTROL PANEL |  | For Approval |  | P | TR-0010 | 2022.05.07
[6 empty] | A | 2022.07.21 | 2022.05.10 | TR-0009 | 2
48 | VP-TEP-R0005-IN-LI-0003 | INSTRUMENT INDEX FOR AIR COMPRESSOR |  | For Approval |  | P | TR-0007 | 2022.04.30
[6 empty] | A | 2022.07.14 | 2022.05.27 | TE-0015 | 2
49 | VP-TEP-R0005-IN-LI-0004 | SET POINT LIST FOR AIR COMPRESSOR |  | For Approval |  | P | TR-0007 | 2022.04.30
[6 empty] | A | 2022.07.14 | 2022.05.27 | TE-0015 | 2
50 | VP-TEP-R0005-IN-DS-0001 | INSTRUMENT DATA SHEET FOR AIR COMPRESSOR |  | For Approval |  | P | TR-0007 | 2022.04.30
[6 empty] | A | 2022.07.14 | 2022.05.27 | TE-0015 | 2
51 | VP-TEP-R0005-IN-LI-0005 | INSTRUMENT INDEX FOR AIR DRYER |  | For Approval |  | P | TR-0009 | 2022.05.20
[6 empty] | A | 2022.07.19 | 2022.05.25 | TR-0014 | 2 |  | 2022.07.27 | TR-0021
52 | VP-TEP-R0005-IN-LI-0006 | SET POINT LIST FOR AIR DRYER |  | For Approval |  | P | TR-0009 | 2022.05.20
[6 empty] | A | 2022.07.19 | 2022.05.25 | TR-0014 | 2 |  | 2022.07.27 | TR-0021
53 | VP-TEP-R0005-IN-DS-0002 | INSTRUMENT DATA SHEET FOR AIR DRYER |  | For Approval |  | P | TR-0009 | 2022.05.20
[6 empty] | A | 2022.07.19 | 2022.05.25 | TR-0014 | 3 |  | 2022.07.27 | TR-0021
54 | VP-TEP-R0005-IN-GA-0001 | INSTRUMENT LAYOUT FOR AIR COMPRESSOR BUILDING |  | For Approval |  | P | TR-0012 | 2022.07.21
[6 empty] | A | 2022.07.22 | 2022.07.21 | TR-0019 | 2 |  | 2022.07.25 | TR-0020
55 | VP-TEP-R0005-IN-DS-0003 | INSTRUMENT DATA SHEET FOR SYSTEM PIPING LINE |  | For Approval |  | P |  | 2022.07.27
[6 empty] | A |  | 2022.07.27 | TR-0021
Quality Control Documents
56 | VP-TEP-R0005-QA-PR-0001 | WPS & PQR |  | For Approval |  | P |  | 2022.04.30
[6 empty] | A |  | 2022.05.04 | TR-0007
57 | VP-TEP-R0005-QA-PL-0001 | INSPECTION & TEST PLAN |  | For Approval | O | P | TR-0005 | 2022.05.11
[6 empty] | A | 2022.07.12 | 2022.05.16 | TR-0012 | 3
58 | VP-TEP-R0005-QA-PR-0002 | INSPECTION & TEST PROCEDURE |  | For Approval | O | P | TR-0005 | 2022.05.11
[6 empty] | A | 2022.07.12 | 2022.05.16 | TR-0012 | 3
59 | VP-TEP-R0005-QA-PR-0003 | INSPECTION AND TEST PLAN AND PROCEDURE FOR MOTOR |  | For Approval | O | P |  | 2022.05.11
A
60 | VP-TEP-R0005-QA-PR-0004 | HYDRO TEST PROCEDURE |  | For Approval |  | P |  | 2022.04.30
[6 empty] | A |  | 2022.05.04 | TR-0007
61 | VP-TEP-R0005-QA-PR-0005 | NDE PROCEDURE |  | For Approval |  | P |  | 2022.04.30
[6 empty] | A |  | 2022.05.04 | TR-0007
Project Name | [5 empty] | P/O NO. | [12 empty] | Doc. No. | [6 empty] | Rev. | [5 empty] | B
Vendor Name
Note
1. Abbreviation - RTS: Result of V/P Review, A: Approved, C: Approved with Comments, R: Rjected, RS: Resubmit, FI: For Information
2. Vendor shall submit the revised document within 14 calendar days after receive purchaser's response.