## VPI&S_Fluff Transfer
Vendor Print Index & Schedule
No. | Document No. | Document Title | Transmittal No. | Category "A/R/I" (For Approval / Review / Information) | Key VP | P/A | Issued for Approval | [11 empty] | Issue for Construction | [15 empty] | Final |  |  |  | Final Data Book |  |  |  | Remark
[7 empty] | Rev. A |  |  |  | Rev. B |  |  |  | Rev. C |  |  |  | Rev. 0 |  |  |  | Rev. 1 |  |  |  | Rev. 2 |  |  |  | Rev. 3 |  |  |  | N(for final)+1 |  |  |  | Later
[7 empty] | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST
General Documents
01 | VP-TEP-R0006-PM-LI-0001 | Vendor Print Index & Schedule |  | A |  | P | Rev. A Out: 2022-01-18
[6 empty] | A | Rev. A Out: 2022-01-18; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0001; Rev. A RST: 3; Rev. B Out: 2022-03-07; Rev. B In: 2022-05-16; Rev. B TR#: T-R0006-P-0018; Rev. B RST: 2; Rev. 0 Out: 2022-05-18
02 | VP-TEP-R0006-PM-PR-0001 | Installation Instruction / Erection Procedure |  | A |  | P | Rev. A Out: 2022-10-10
A
03 | VP-TEP-R0006-PM-MA-0001 | Training Manual |  | A |  | P | Rev. A Out: 2022-10-10
A
04 | VP-TEP-R0006-PM-PR-0002 | Preventive Maintenance Plan (Special Storage and handling procedure) |  | A |  | P | Rev. A Out: 2022-10-10
A
05 | VP-TEP-R0006-PM-MA-0002 | Operation & Maintenance Manual |  | A |  | P | Rev. A Out: 2022-10-10
A
06 | VP-TEP-R0006-PM-MA-0003 | Commissioning Manual |  | A |  | P | Rev. A Out: 2022-10-10
A
07 | VP-TEP-R0006-PM-LI-0002 | Sub Vendor List |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-18; Rev. A TR#: T-R0006-P-0005; Rev. A RST: 3; Rev. B Out: 2022-06-21
08 | VP-TEP-R0006-PM-LI-0003 | Spare Parts List For Start-Up and Commissioning |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-04; Rev. A In: 2022-03-17; Rev. A TR#: T-R0006-P-0004; Rev. A RST: 2; Rev. 0 Out: 2022-03-31; Rev. 0 In: 2022-05-30; Rev. 0 TR#: T-R0006-P-0021; Rev. 0 RST: 1
09 | VP-TEP-R0006-PM-LI-0004 | Recommended Spare Parts List For 2 Years Operation |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-04; Rev. A In: 2022-03-17; Rev. A TR#: T-R0006-P-0004; Rev. A RST: 2; Rev. 0 Out: 2022-03-31; Rev. 0 In: 2022-05-30; Rev. 0 TR#: T-R0006-P-0021; Rev. 0 RST: 1
10 | VP-TEP-R0006-PM-LI-0005 | Special Tools List |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-04; Rev. A In: 2022-03-17; Rev. A TR#: T-R0006-P-0004; Rev. A RST: 2; Rev. 0 Out: 2022-03-31; Rev. 0 In: 2022-05-30; Rev. 0 TR#: T-R0006-P-0021; Rev. 0 RST: 2; Rev. 1 Out: 2022-06-17
11 | VP-TEP-R0006-PM-LI-0006 | Lubrication List |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-04; Rev. A In: 2022-03-17; Rev. A TR#: T-R0006-P-0004; Rev. A RST: 3; Rev. B Out: 2022-03-31; Rev. B In: 2022-05-16; Rev. B TR#: T-R0006-P-0021; Rev. B RST: 1; Rev. 0 Out: 2022-05-18
12 | VP-TEP-R0006-PM-DB-0001 | As Built Drawings / Documents |  | A |  | P
A
Civil Documents
13 | VP-TEP-R0006-CV-CA-0001 | Foundation Loading Data for Intake Screen Plant |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-15; Rev. A TR#: T-R0006-P-0003; Rev. A RST: 3; Rev. B Out: 2022-03-21; Rev. B In: 2022-05-10; Rev. B TR#: T-R0006-P-0016; Rev. B RST: 1; Rev. 0 Out: 2022-05-10; Rev. 0 In: 2022-07-15; Rev. 0 TR#: T-R0006-P-0032; Rev. 0 RST: 1
14 | VP-TEP-R0006-CV-FA-0001 | Civil Foundation Drawing of Stop Gate & Guide for CWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-15; Rev. A TR#: T-R0006-P-0003; Rev. A RST: 3; Rev. B Out: 2022-03-21; Rev. B In: 2022-05-10; Rev. B TR#: T-R0006-P-0016; Rev. B RST: 1; Rev. 0 Out: 2022-05-10; Rev. 0 In: 2022-07-15; Rev. 0 TR#: T-R0006-P-0032; Rev. 0 RST: 1
15 | VP-TEP-R0006-CV-FA-0002 | Civil Foundation Drawing of Stop Gate & Guide for ACWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-15; Rev. A TR#: T-R0006-P-0003; Rev. A RST: 3; Rev. B Out: 2022-03-21; Rev. B In: 2022-05-10; Rev. B TR#: T-R0006-P-0016; Rev. B RST: 1; Rev. 0 Out: 2022-05-10; Rev. 0 In: 2022-07-15; Rev. 0 TR#: T-R0006-P-0032; Rev. 0 RST: 1
16 | VP-TEP-R0006-CV-FA-0003 | Civil Foundation Drawing of Trash Rack & Rake for CWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-15; Rev. A TR#: T-R0006-P-0003; Rev. A RST: 3; Rev. B Out: 2022-03-21; Rev. B In: 2022-05-10; Rev. B TR#: T-R0006-P-0016; Rev. B RST: 1; Rev. 0 Out: 2022-05-10; Rev. 0 In: 2022-07-15; Rev. 0 TR#: T-R0006-P-0032; Rev. 0 RST: 1
17 | VP-TEP-R0006-CV-FA-0004 | Civil Foundation Drawing of Trash Rack & Rake for ACWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-15; Rev. A TR#: T-R0006-P-0003; Rev. A RST: 3; Rev. B Out: 2022-03-21; Rev. B In: 2022-05-10; Rev. B TR#: T-R0006-P-0016; Rev. B RST: 1; Rev. 0 Out: 2022-05-10; Rev. 0 In: 2022-07-15; Rev. 0 TR#: T-R0006-P-0032; Rev. 0 RST: 1
18 | VP-TEP-R0006-CV-FA-0005 | Civil Foundation Drawing of Traveling Screen for CWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-15; Rev. A TR#: T-R0006-P-0003; Rev. A RST: 3; Rev. B Out: 2022-03-21; Rev. B In: 2022-05-10; Rev. B TR#: T-R0006-P-0016; Rev. B RST: 1; Rev. 0 Out: 2022-05-10; Rev. 0 In: 2022-07-15; Rev. 0 TR#: T-R0006-P-0032; Rev. 0 RST: 1
19 | VP-TEP-R0006-CV-FA-0006 | Civil Foundation Drawing of Traveling Screen for ACWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-15; Rev. A TR#: T-R0006-P-0003; Rev. A RST: 3; Rev. B Out: 2022-03-21; Rev. B In: 2022-05-10; Rev. B TR#: T-R0006-P-0016; Rev. B RST: 2; Rev. 0 Out: 2022-05-10; Rev. 0 In: 2022-07-15; Rev. 0 TR#: T-R0006-P-0032; Rev. 0 RST: 1
20 | VP-TEP-R0006-CV-FA-0007 | Civil Foundation Drawing of Trash Pit |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-15; Rev. A TR#: T-R0006-P-0003; Rev. A RST: 3; Rev. B Out: 2022-03-21; Rev. B In: 2022-05-10; Rev. B TR#: T-R0006-P-0016; Rev. B RST: 1; Rev. 0 Out: 2022-05-10; Rev. 0 In: 2022-07-15; Rev. 0 TR#: T-R0006-P-0032; Rev. 0 RST: 1
21 | VP-TEP-R0006-CV-FA-0008 | Civil Foundation Drawing of Storage Rack |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-15; Rev. A TR#: T-R0006-P-0003; Rev. A RST: 3; Rev. B Out: 2022-03-21; Rev. B In: 2022-05-10; Rev. B TR#: T-R0006-P-0016; Rev. B RST: 2; Rev. 0 Out: 2022-05-10; Rev. 0 In: 2022-07-15; Rev. 0 TR#: T-R0006-P-0032; Rev. 0 RST: 1
22 | VP-TEP-R0006-CV-FA-0009 | Civil Foundation Drawing of Screen Washing Pump |  | A | ○ | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-04-12; Rev. A In: 2022-05-30; Rev. A TR#: T-R0006-P-0023; Rev. A RST: 2; Rev. 0 Out: 2022-06-17
23 | VP-TEP-R0006-CV-BM-0001 | Embedded Material List for 1st Concrete |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-15; Rev. A TR#: T-R0006-P-0003; Rev. A RST: 2; Rev. 0 Out: 2022-04-12; Rev. 0 In: 2022-06-02; Rev. 0 TR#: T-R0006-P-0024; Rev. 0 RST: 3; Rev. 1 Out: 2022-06-17
Mechanical Documents
24 | VP-TEP-R0006-RO-DS-0001 | Technical Data Sheet for Intake Screen Plant |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 3; Rev. B Out: 2022-04-12; Rev. B In: 2022-06-03; Rev. B TR#: T-R0006-P-0025; Rev. B RST: 1; Rev. 0 Out: 2022-06-17
25 | VP-TEP-R0006-RO-SP-0001 | System Description with Operation & Control Philosophy for Intake Screen Plant |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-10; Rev. A In: 2022-03-29; Rev. A TR#: T-R0006-P-0007; Rev. A RST: 3; Rev. B Out: 2022-04-29
26 | VP-TEP-R0006-RO-PI-0001 | P & I Drawing for Intake Screen Plant |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 3; Rev. B Out: 2022-04-12; Rev. B In: 2022-06-03; Rev. B TR#: T-R0006-P-0025; Rev. B RST: 2; Rev. 0 Out: 2022-06-17
27 | VP-TEP-R0006-RO-LI-0001 | General Layout Drawing for Intake Screen Plant |  | A |  | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 3; Rev. B Out: 2022-04-12; Rev. B In: 2022-06-03; Rev. B TR#: T-R0006-P-0025; Rev. B RST: 2; Rev. 0 Out: 2022-06-17
28 | VP-TEP-R0006-RO-LI-0002 | General Arrangement Drawing of Stop Gate & Guide for CWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 2; Rev. 0 Out: 2022-03-11; Rev. 0 In: 2022-05-09; Rev. 0 TR#: T-R0006-P-0012; Rev. 0 RST: 1
29 | VP-TEP-R0006-RO-LI-0003 | General Arrangement Drawing of Stop Gate & Guide for ACWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 2; Rev. 0 Out: 2022-03-11; Rev. 0 In: 2022-05-09; Rev. 0 TR#: T-R0006-P-0012; Rev. 0 RST: 1
30 | VP-TEP-R0006-RO-LI-0004 | General Arrangement Drawing of Trash Rack & Rake for CWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 2; Rev. 0 Out: 2022-03-11; Rev. 0 In: 2022-05-09; Rev. 0 TR#: T-R0006-P-0012; Rev. 0 RST: 2; Rev. 1 Out: 2022-05-13; Rev. 1 In: 2022-07-01; Rev. 1 TR#: T-R0006-P-0028; Rev. 1 RST: 2; Rev. 2 Out: 2022-07-06
31 | VP-TEP-R0006-RO-LI-0005 | General Arrangement Drawing of Trash Rack & Rake for ACWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 2; Rev. 0 Out: 2022-03-11; Rev. 0 In: 2022-05-09; Rev. 0 TR#: T-R0006-P-0012; Rev. 0 RST: 2; Rev. 1 Out: 2022-05-13; Rev. 1 In: 2022-07-01; Rev. 1 TR#: T-R0006-P-0028; Rev. 1 RST: 2; Rev. 2 Out: 2022-07-06
32 | VP-TEP-R0006-RO-LI-0006 | General Arrangement Drawing of Traveling Screen for CWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 2; Rev. 0 Out: 2022-03-11; Rev. 0 In: 2022-05-09; Rev. 0 TR#: T-R0006-P-0012; Rev. 0 RST: 1
33 | VP-TEP-R0006-RO-LI-0007 | General Arrangement Drawing of Traveling Screen for ACWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 2; Rev. 0 Out: 2022-03-11; Rev. 0 In: 2022-05-09; Rev. 0 TR#: T-R0006-P-0012; Rev. 0 RST: 1
34 | VP-TEP-R0006-RO-LI-0008 | General Arrangement Drawing of Storage Rack |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 2; Rev. 0 Out: 2022-03-11; Rev. 0 In: 2022-05-09; Rev. 0 TR#: T-R0006-P-0012; Rev. 0 RST: 1
35 | VP-TEP-R0006-RO-LI-0009 | General Arrangement Drawing of Lifting Beam for CWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 2; Rev. 0 Out: 2022-03-11; Rev. 0 In: 2022-05-09; Rev. 0 TR#: T-R0006-P-0012; Rev. 0 RST: 1
36 | VP-TEP-R0006-RO-LI-0010 | General Arrangement Drawing of Lifting Beam for ACWP |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 2; Rev. 0 Out: 2022-03-11; Rev. 0 In: 2022-05-09; Rev. 0 TR#: T-R0006-P-0012; Rev. 0 RST: 1
37 | VP-TEP-R0006-RO-LI-0011 | General Arrangement Drawing of Screen Washing Pump |  | A | ○ | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-05-03; Rev. A In: 2022-06-24; Rev. A TR#: T-R0006-P-0026; Rev. A RST: 3; Rev. B Out: 2022-07-08
38 | VP-TEP-R0006-RO-LI-0012 | General Arrangement Drawing of Y-Strainer |  | A | ○ | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-04-26; Rev. A In: 2022-08-19; Rev. A TR#: T-R0006-P-0038; Rev. A RST: 2
39 | VP-TEP-R0006-RO-LI-0013 | Name Plate & Tag Plate list & drawing |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-10; Rev. A In: 2022-03-29; Rev. A TR#: T-R0006-P-0007; Rev. A RST: 3; Rev. B Out: 2022-04-29
40 | VP-TEP-R0006-RO-DS-0002 | Data Sheets for Screen Washing Pump |  | A | ○ | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-05-03; Rev. A In: 2022-06-24; Rev. A TR#: T-R0006-P-0026; Rev. A RST: 3; Rev. B Out: 2022-07-08
41 | VP-TEP-R0006-RO-DS-0003 | Data Sheets for Y-Strainer |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-04-26; Rev. A In: 2022-08-19; Rev. A TR#: T-R0006-P-0038; Rev. A RST: 1
42 | VP-TEP-R0006-RO-DS-0004 | Data Sheets For Valves (Manual) |  | A |  | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-07-13
43 | VP-TEP-R0006-RO-LI-0014 | Valve List (Manual) |  | A |  | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-04-21; Rev. A In: 2022-07-01; Rev. A TR#: T-R0006-P-0027; Rev. A RST: 2; Rev. 0 Out: 2022-07-06
44 | VP-TEP-R0006-RO-LI-0015 | Equipment List |  | A | ○ | P | Rev. A Out: 2022-02-15
[6 empty] | A | Rev. A Out: 2022-01-26; Rev. A In: 2022-03-04; Rev. A TR#: T-R0006-P-0002; Rev. A RST: 3; Rev. B Out: 2022-04-12; Rev. B In: 2022-06-03; Rev. B TR#: T-R0006-P-0025; Rev. B RST: 2; Rev. 0 Out: 2022-06-17
45 | VP-TEP-R0006-RO-LI-0016 | Utility Consumption List |  | A | ○ | P | Rev. A Out: 2022-02-15
[6 empty] | A | Rev. A Out: 2022-02-10; Rev. A In: 2022-03-29; Rev. A TR#: T-R0006-P-0007; Rev. A RST: 2; Rev. 0 Out: 2022-04-18; Rev. 0 In: 2022-05-16; Rev. 0 TR#: T-R0006-P-0020; Rev. 0 RST: 2; Rev. 1 Out: 2022-05-18
46 | VP-TEP-R0006-RO-OT-0001 | 3D Modeling |  | A |  | P | Rev. A Out: 2022-06-28
A
47 | VP-TEP-R0006-RO-SP-0002 | Technical Specification and Drawing of Cathodic Protection System |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-04-19; Rev. A In: 2022-07-19; Rev. A TR#: T-R0006-P-0033; Rev. A RST: 3; Rev. B Out: 2022-07-25
48 | VP-TEP-R0006-QA-PR-0001 | Painting Procedure (Painting Schedule and Color Codes) |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 3; Rev. B Out: 2022-07-28
49 | VP-TEP-R0006-QA-PR-0005 | Packing Procedure |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 3; Rev. B Out: 2022-07-28
Piping Documents
50 | VP-TEP-R0006-PI-GA-0001 | Piping Arrangement Drawing of Wash Water System with Pump, Valve, Strainer & Support |  | A |  | P | Rev. A Out: 2022-03-28
[6 empty] | A | Rev. A Out: 2022-04-15; Rev. A In: 2022-07-08; Rev. A TR#: T-R0006-P-0029; Rev. A RST: 3; Rev. B Out: 2022-07-28
51 | VP-TEP-R0006-PI-IS-0001 | Piping Isometric Drawing |  | A |  | P | Rev. A Out: 2022-03-28
[6 empty] | A | Rev. A Out: 2022-04-15; Rev. A In: 2022-07-08; Rev. A TR#: T-R0006-P-0029; Rev. A RST: 3; Rev. B Out: 2022-07-28
52 | VP-TEP-R0006-PI-SU-0001 | Piping Support Drawing |  | A |  | P | Rev. A Out: 2022-03-28
[6 empty] | A | Rev. A Out: 2022-04-15; Rev. A In: 2022-07-08; Rev. A TR#: T-R0006-P-0029; Rev. A RST: 3; Rev. B Out: 2022-07-28
Electrical Documents
53 | VP-TEP-R0006-EL-LI-0001 | Electrical Load List |  | A | ○ | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-28; Rev. A In: 2022-04-05; Rev. A TR#: T-R0006-P-0008; Rev. A RST: 3; Rev. B Out: 2022-05-24
54 | VP-TEP-R0006-EL-GA-0004 | Outline Drawing of Motors |  | A |  | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-05-13; Rev. A In: 2022-07-12; Rev. A TR#: T-R0006-P-0031; Rev. A RST: 2; Rev. 0 Out: 2022-07-25
55 | VP-TEP-R0006-EL-SP-0001 | Data Sheets & Characteristic Curves for Motors |  | A | ○ | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-05-13; Rev. A In: 2022-07-12; Rev. A TR#: T-R0006-P-0031; Rev. A RST: 2; Rev. 0 Out: 2022-07-25
56 | VP-TEP-R0006-EL-SD-0001 | Single Line Diagram (for Reference) (제출항목에서 제외됨) |  | A |  | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-28; Rev. A In: 2022-04-05; Rev. A TR#: T-R0006-P-0008; Rev. A RST: 3
57 | VP-TEP-R0006-EL-SQ-0001 | MCC Schematic Diagram (for Reference) |  | A |  | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-28; Rev. A In: 2022-04-05; Rev. A TR#: T-R0006-P-0008; Rev. A RST: 3; Rev. B Out: 2022-05-24
58 | VP-TEP-R0006-EL-GA-0001 | Electric General Arrangement Drawing |  | A |  | P | Rev. A Out: 2022-02-25
[6 empty] | A | Rev. A Out: 2022-02-25; Rev. A In: 2022-05-16; Rev. A TR#: T-R0006-P-0017; Rev. A RST: 1; Rev. 0 Out: 2022-05-22; Rev. 0 In: 2022-08-03; Rev. 0 TR#: T-R0006-P-0035; Rev. 0 RST: 2; Rev. 1 Out: 2022-08-04
59 | VP-TEP-R0006-EL-GA-0002 | Cable Raceway Drawing |  | A |  | P | Rev. A Out: 2022-02-25
[6 empty] | A | Rev. A Out: 2022-02-25; Rev. A In: 2022-05-16; Rev. A TR#: T-R0006-P-0017; Rev. A RST: 3; Rev. B Out: 2022-05-22; Rev. B In: 2022-08-03; Rev. B TR#: T-R0006-P-0036; Rev. B RST: 2; Rev. 0 Out: 2022-08-04
60 | VP-TEP-R0006-EL-GA-0003 | Grounding Plan |  | A |  | P | Rev. A Out: 2022-02-25
[6 empty] | A | Rev. A Out: 2022-02-25; Rev. A In: 2022-05-16; Rev. A TR#: T-R0006-P-0017; Rev. A RST: 3; Rev. B Out: 2022-08-18
61 | VP-TEP-R0006-EL-CS-0001 | Cable Schedule for Electrical |  | A |  | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-03-15; Rev. A In: 2022-05-16; Rev. A TR#: T-R0006-P-0019; Rev. A RST: 3; Rev. B Out: 2022-05-24
62 | VP-TEP-R0006-EL-CS-0002 | Interconnection Wiring Diagram for Electrical |  | A |  | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-03-15; Rev. A In: 2022-05-16; Rev. A TR#: T-R0006-P-0019; Rev. A RST: 3; Rev. B Out: 2022-08-18
63 | VP-TEP-R0006-EL-BM-0001 | Bill of Material for electrical |  | A |  | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-03-15; Rev. A In: 2022-05-16; Rev. A TR#: T-R0006-P-0019; Rev. A RST: 3; Rev. B Out: 2022-05-24
64 | VP-TEP-R0006-EL-SP-0002 | Electrical Heat Tracing Data |  | A |  | P | Rev. A Out: 2022-04-15
A
Instrument Documents
65 | VP-TEP-R0006-IN-CF-0001 | Control system Configuration Drawing |  | A |  | P | Rev. A Out: 2022-01-28
[6 empty] | A | Rev. A Out: 2022-01-28; Rev. A In: 2022-03-18; Rev. A TR#: T-R0006-P-0006; Rev. A RST: 3; Rev. B Out: 2022-04-15
66 | VP-TEP-R0006-IN-OT-0001 | Bill of Material for I&C |  | A |  | P | Rev. A Out: 2022-03-22
[6 empty] | A | Rev. A Out: 2022-03-22; Rev. A In: 2022-04-26; Rev. A TR#: T-R0006-P-0010; Rev. A RST: 3; Rev. B Out: 2022-08-18
67 | VP-TEP-R0006-IN-CS-0001 | Cable Schedule for I&C |  | A |  | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-03-15; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0013; Rev. A RST: 3; Rev. B Out: 2022-08-18
68 | VP-TEP-R0006-IN-CS-0002 | Interconnection Wiring Diagram for I&C |  | A |  | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-03-15; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0013; Rev. A RST: 3; Rev. B Out: 2022-08-18
69 | VP-TEP-R0006-IN-LI-0001 | Panel List & Drawing |  | A |  | P | Rev. A Out: 2022-02-18
[6 empty] | A | Rev. A Out: 2022-02-18; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0015; Rev. A RST: 3; Rev. B Out: 2022-07-19
70 | VP-TEP-R0006-IN-WD-0001 | Schematic Diagram |  | A |  | P | Rev. A Out: 2022-02-18
[6 empty] | A | Rev. A Out: 2022-02-18; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0015; Rev. A RST: 3; Rev. B Out: 2022-07-19
71 | VP-TEP-R0006-IN-LD-0001 | Control Logic Diagram |  | A |  | P | Rev. A Out: 2022-03-25
[6 empty] | A | Rev. A Out: 2022-03-25; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0014; Rev. A RST: 3
72 | VP-TEP-R0006-IN-LD-0002 | Control Loop Diagram |  | A |  | P | Rev. A Out: 2022-03-25
[6 empty] | A | Rev. A Out: 2022-03-25; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0014; Rev. A RST: 3
73 | VP-TEP-R0006-IN-LI-0002 | PLC I/O List |  | A | ○ | P | Rev. A Out: 2022-02-18
[6 empty] | A | Rev. A Out: 2022-02-18; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0015; Rev. A RST: 3; Rev. B Out: 2022-07-19
74 | VP-TEP-R0006-IN-LI-0003 | DCS I/O List |  | A | ○ | P | Rev. A Out: 2022-02-18
[6 empty] | A | Rev. A Out: 2022-02-18; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0015; Rev. A RST: 3; Rev. B Out: 2022-07-19
75 | VP-TEP-R0006-IN-LI-0004 | MOV List |  | A |  | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-04-21; Rev. A In: 2022-07-08; Rev. A TR#: T-R0006-P-0030; Rev. A RST: 3; Rev. B Out: 2022-08-01
76 | VP-TEP-R0006-IN-LI-0005 | Instrument List |  | A |  | P | Rev. A Out: 2022-02-25
[6 empty] | A | Rev. A Out: 2022-02-25; Rev. A In: 2022-04-07; Rev. A TR#: T-R0006-P-0009; Rev. A RST: 3; Rev. B Out: 2022-04-29; Rev. B In: 2022-07-25; Rev. B TR#: T-R0006-P-0034; Rev. B RST: 2; Rev. 0 Out: 2022-08-22
77 | VP-TEP-R0006-IN-LI-0006 | Alarm & Set Point List |  | A |  | P | Rev. A Out: 2022-02-18
[6 empty] | A | Rev. A Out: 2022-02-18; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0015; Rev. A RST: 2; Rev. 0 Out: 2022-07-19
78 | VP-TEP-R0006-IN-DS-0001 | Data sheets for PLC |  | A |  | P | Rev. A Out: 2022-02-25
[6 empty] | A | Rev. A Out: 2022-02-25; Rev. A In: 2022-04-07; Rev. A TR#: T-R0006-P-0009; Rev. A RST: 3; Rev. B Out: 2022-07-20
79 | VP-TEP-R0006-IN-DS-0002 | Data sheets for Instrument |  | A |  | P | Rev. A Out: 2022-02-25
[6 empty] | A | Rev. A Out: 2022-02-25; Rev. A In: 2022-04-07; Rev. A TR#: T-R0006-P-0009; Rev. A RST: 4; Rev. B Out: 2022-04-29; Rev. B In: 2022-07-25; Rev. B TR#: T-R0006-P-0034; Rev. B RST: 2; Rev. 0 Out: 2022-08-22
80 | VP-TEP-R0006-IN-DS-0003 | Data Sheets for MOV |  | A |  | P | Rev. A Out: 2022-03-15
[6 empty] | A | Rev. A Out: 2022-07-13
81 | VP-TEP-R0006-IN-ID-0001 | Instrument Installation Drawing |  | A |  | P | Rev. A Out: 2022-02-25
[6 empty] | A | Rev. A Out: 2022-02-25; Rev. A In: 2022-04-07; Rev. A TR#: T-R0006-P-0009; Rev. A RST: 3; Rev. B Out: 2022-04-29; Rev. B In: 2022-07-25; Rev. B TR#: T-R0006-P-0034; Rev. B RST: 3; Rev. C Out: 2022-08-22
82 | VP-TEP-R0006-IN-LO-0001 | Instrument Location Drawing |  | A |  | P | Rev. A Out: 2022-02-25
[6 empty] | A | Rev. A Out: 2022-02-25; Rev. A In: 2022-04-07; Rev. A TR#: T-R0006-P-0009; Rev. A RST: 3; Rev. B Out: 2022-05-22; Rev. B In: 2022-08-23; Rev. B TR#: T-R0006-P-0037; Rev. B RST: 2; Rev. 0 Out: 2022-08-04
83 | VP-TEP-R0006-IN-AG-0001 | LCD Graphic Sketch |  | A |  | P | Rev. A Out: 2022-04-29
A
Quality Control Documents
84 | VP-TEP-R0006-QA-MA-0001 | Quality Assurance Manual |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 1
85 | VP-TEP-R0006-QA-PR-0002 | Chemical Cleaning Procedure for Stainless Steel |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 3; Rev. B Out: 2022-08-09
86 | VP-TEP-R0006-QA-PR-0003 | Welding Procedure (WPS & PQR) |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 3; Rev. B Out: 2022-08-09
87 | VP-TEP-R0006-QA-PR-0004 | NDE Procedure |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 3; Rev. B Out: 2022-08-09
88 | VP-TEP-R0006-QA-PR-0006 | PMI Procedure |  | A |  | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 3; Rev. B Out: 2022-08-09
89 | VP-TEP-R0006-QA-PL-0001 | Shop Test & Inspection Plan for Intake Screen Plant |  | A | ○ | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 3; Rev. B Out: 2022-08-09
90 | VP-TEP-R0006-QA-PL-0002 | Shop Test & Inspection Plan for Motor |  | A | ○ | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 3; Rev. B Out: 2022-08-09
91 | VP-TEP-R0006-QA-PR-0007 | Shop Test & Inspection Procedure for Intake Screen Plant |  | A | ○ | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 3; Rev. B Out: 2022-08-09
92 | VP-TEP-R0006-QA-PR-0008 | Shop Test & Inspection Procedure for Motor |  | A | ○ | P | Rev. A Out: 2022-02-28
[6 empty] | A | Rev. A Out: 2022-02-28; Rev. A In: 2022-05-09; Rev. A TR#: T-R0006-P-0011; Rev. A RST: 3; Rev. B Out: 2022-08-09
93 | VP-TEP-R0006-QA-OT-0001 | Data Book for Intake Facility |  | A |  | P
A
Project Name |  | TONG YEONG ECO POWER LNG POWER PLANT PROJECT |  |  |  | P/O NO. | Rev. A RST: PO-TEP-R-0006-P; Rev. 0 Out: Doc. No.; Rev. 0 In: VP-TEP-R0006-PM-LI-0001; Rev. 1 RST: Rev.; Later In: A
Vendor Name |  | ECOSET
Note
1. Abbreviation - RTS: Result of V/P Review, A: Approved, C: Approved with Comments, R: Rejected, RS: Resubmit, FI: For Information
2. Vendor shall submit the revised document within 14 calendar days after receive purchaser's response.