## VPI&S_Fluff Transfer
No. | Document No. | Document Title | Category "A/R/I" (For Approval / Review / Information) | Key VP | P/A | Issued for Approval | [11 empty] | Issue for Final | [7 empty] | Final |  |  |  | Final Data Book |  |  |  | Remark
[6 empty] | Rev. A |  |  |  | Rev. B |  |  |  | Rev. C |  |  |  | Rev. 0 |  |  |  | Rev. 1 |  |  |  | N(for final)+1 |  |  |  | Later
[6 empty] | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST
General Documents
1 | VP-TEP-R0007-PM-LI-0001 | Vendor print index & schedule | A | O | P | 2022-02-25 |  |  |  | 2022-04-28
[5 empty] | A | 2022-02-18 |  | 001 | 003
2 | VP-TEP-R0007-PM-LI-0002 | Utility consumption list | A | O | P | 2022-02-25 |  |  |  | 2022-04-28
[5 empty] | A | 2022-02-25 | 2022-04-13 | 003 | 004 | 2022-06-10 |  | 008
3 | VP-TEP-R0007-PM-LI-0003 | Spare parts list | A |  | P | 2022-06-10
[5 empty] | A | 2022-07-19 |  | 014
4 | VP-TEP-R0007-PM-LI-0004 | Special tools list | A |  | P | 2022-05-10
A
5 | VP-TEP-R0007-PM-LI-0005 | Lubricants list | A |  | P | 2022-05-10
A
6 | VP-TEP-R0007-PM-LI-0006 | Sub-vendors list | A | O | P | 2022-02-25 |  |  |  | 2022-05-25
[5 empty] | A | 2022-03-07 | 2022-05-10 | 005 | 005 | 2022-06-10 |  | 008
7 | VP-TEP-R0007-PM-LI-0007 | Detailed packing list | I |  | P | 2022-12-10
A
8 | VP-TEP-R0007-PM-OT-0008 | 3D Modeling | I |  | P | 2022-09-10
A
9 | VP-TEP-R0007-PM-DB-0009 | Preliminary data book | A |  | P | 2022-12-10
A
10 | VP-TEP-R0007-PM-OT-0010 | Name plate drawing | A |  | P | 2022-10-05
A
11 | VP-TEP-R0007-PM-PR-0011 | Packing, shipping & storage procedure | A |  | P | 2022-05-06
A
12 | VP-TEP-R0007-PM-MA-0012 | Operation and maintenance manuals | A |  | P | 2022-11-04
A
13 | VP-TEP-R0007-PM-MA-0013 | Training manual | A |  | P | 2022-11-04
A
14 | VP-TEP-R0007-PM-PR-0057 | Painting schedule & procedure | A |  | P | 2022-05-10
A
Process Documents
15 | VP-TEP-R0007-PR-LI-0014 | Equipment List | A | O | P | 2022-02-25 | 2022-04-13 |  |  | 2022-04-28
[5 empty] | A | 2022-02-25 | 2022-03-22 | 003 | 004 | 2022-06-10 |  | 008
16 | VP-TEP-R0007-PR-PI-0015 | Piping and instrument diagram | A | O | P | 2022-02-17 |  |  |  | 2022-04-28
[5 empty] | A | 2022-02-18 | 2022-03-22 | 002 | 001 | 2022-05-19 |  | 007
17 | VP-TEP-R0007-PR-FD-0017 | Process flow diagram | A |  | P | 2022-02-25
[5 empty] | A | 2022-02-25 | 2022-03-22 | 003 | 004
18 | VP-TEP-R0007-PR-SP-0018 | System description | A |  | P | 2022-06-11
A
Rotating Documents
19 | VP-TEP-R0007-RO-SP-0019 | Specification for agitator | A |  | P | 2022-06-10
[5 empty] | A | 2022-07-12 |  | 012
20 | VP-TEP-R0007-RO-SP-0020 | Specification for pump | A | O | P | 2022-06-10
[5 empty] | A | 2022-06-10 |  | 008
Stationary Documents
21 | VP-TEP-R0007-ST-DS-0021 | Tank datasheet | A |  | P | 2022-05-30
[5 empty] | A | 2022-06-16 |  | 009
22 | VP-TEP-R0007-ST-CA-0022 | Tank calculation | A |  | P | 2022-05-30
[5 empty] | A | 2022-06-16 |  | 009
23 | VP-TEP-R0007-ST-DS-0023 | Fume scrubber datasheet | A |  | P | 2022-05-03
[5 empty] | A | 2022-05-09 |  | 006
24 | VP-TEP-R0007-ST-DS-0024 | Specification for eye washer & safety shower | A |  | P | 2022-09-10
A
Civil Documents
25 | VP-TEP-R0007-CV-FA-0025 | Foundation detail drawing | A | O | P | 2022-02-17 |  |  |  | 2022-04-28
[5 empty] | A | 2022-02-18 | 2022-03-22 | 002 | 001 | 2022-05-19 |  | 007
Piping Documents
26 | VP-TEP-R0007-PI-DS-0026 | Valve & specialty list including data sheet | A |  | P | 2022-05-30
[5 empty] | A | 2022-07-19 |  | 014
27 | VP-TEP-R0007-PI-IS-0027 | Auxiliary piping & tubing drawing | A |  | P | 2022-05-30
A
28 | VP-TEP-R0007-PI-SP-0028 | Piping material classification | A |  | P | 2022-05-25
[5 empty] | A | 2022-07-11 |  | 011
29 | VP-TEP-R0007-PI-IS-0029 | Piping isometric drawing | I |  | P | 2022-06-23
A
30 | VP-TEP-R0007-PI-GA-0030 | General arrangement drawing | A | O | P | 2022-02-17 |  |  |  | 2022-04-28
[5 empty] | A | 2022-02-18 | 2022-03-22 | 002 | 001 | 2022-05-19 |  | 007
Electrical Documents
31 | VP-TEP-R0007-EL-LI-0031 | Electric load list | A | O | P | 2022-06-10
[5 empty] | A | 2022-06-10 |  | 008
32 | VP-TEP-R0007-EL-CS-0032 | Electrical cable schedule | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-04 |  | 010
33 | VP-TEP-R0007-EL-LI-0033 | Cable connection list | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-04 |  | 010
34 | VP-TEP-R0007-EL-PL-0034 | Tray Route Plan & Section | A |  | P | 2022-06-25
A
35 | VP-TEP-R0007-EL-DS-0035 | LCP datasheet & drawing | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-04 |  | 010
36 | VP-TEP-R0007-EL-SP-0036 | Specification, BOM, catalog for Electrical Bulk Material | A |  | P | 2022-06-28
[5 empty] | A | 2022-07-13 |  | 013
37 | VP-TEP-R0007-EL-DS-0037 | Motor data sheet with motor characteristic curve | A | O | P | 2022-06-10
[5 empty] | A | 2022-06-10 |  | 008
38 | VP-TEP-R0007-EL-OT-0038 | Cable tray and conduit drawing | A |  | P | 2022-06-25
A
39 | VP-TEP-R0007-EL-SQ-0039 | Electrical schematic diagram for MCC and dist. Board | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-13 |  | 013
40 | VP-TEP-R0007-EL-SD-0040 | Single line diagram | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-04 |  | 010
41 | VP-TEP-R0007-EL-CF-0041 | System configuration diagram | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-04 |  | 010
42 | VP-TEP-R0007-EL-LI-0042 | Dosing skid I/O List | A | O | P | 2022-06-10
[5 empty] | A | 2022-06-10 |  | 008
Instrument & Control Documents
43 | VP-TEP-R0007-IN-LI-0043 | Instrument list | A |  | P | 2022-06-10
[5 empty] | A | 2022-07-04 |  | 010
44 | VP-TEP-R0007-IN-LI-0044 | Instrument I/O List with Alarm Set Point | A |  | P | 2022-06-25
A
45 | VP-TEP-R0007-IN-DS-0045 | Instrument datasheet | A |  | P | 2022-06-10 | [27 empty] | Metering cylinder포함
[5 empty] | A | 2022-07-04 |  | 010
46 | VP-TEP-R0007-IN-ID-0046 | Instrument installation drawing | A |  | P | 2022-06-10
A
47 | VP-TEP-R0007-IN-PD-0047 | Instrument arrangement plot plan | A |  | P | 2022-06-10
A
48 | VP-TEP-R0007-IN-WD-0048 | Interconnection wiring diagram for control | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-04 |  | 010
49 | VP-TEP-R0007-IN-SQ-0049 | Schematic diagram for control | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-04 |  | 010
50 | VP-TEP-R0007-IN-LD-0050 | Control logic diagram | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-04 |  | 010
51 | VP-TEP-R0007-IN-LD-0051 | Control loop diagram | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-04 |  | 010
52 | VP-TEP-R0007-IN-LS-0052 | Instrument level setting drawing | A |  | P | 2022-06-25
[5 empty] | A | 2022-07-04 |  | 010
53 | VP-TEP-R0007-EL-CF-0041 | System configuration diagram | A |  | P | 2022-11-04
A
54 | VP-TEP-R0007-EL-LI-0042 | Dosing skid I/O List | A | O | P | 2022-06-10
[5 empty] | A | 2022-07-04 |  | 008
54 | VP-TEP-R0007-EL-LI-0063 | DCS I/O List | A | O | P | 2022-06-10
[5 empty] | A | 2022-07-12 |  | 012
Quality Control Documents
55 | VP-TEP-R0007-QA-PL-0053 | Inspection and Test Plan | A | O | P | 2022-05-28
[5 empty] | A | 2022-06-10 |  | 008
56 | VP-TEP-R0007-QA-PR-0054 | Inspection and Test Procedure(Including Hydrostatic, Leak, Noise test and etc.) | A |  | P | 2022-06-10
[5 empty] | A | 2022-07-04 |  | 010
57 | VP-TEP-R0007-QA-PR-0055 | NDE procedure | A |  | P | 2022-03-04 |  |  |  | 2022-06-10 | [23 empty] | operator qualification record 포함
[5 empty] | A | 2022-03-07 | 2022-04-08 | 004 | 002 | 2022-07-11 |  | 011
58 | VP-TEP-R0007-QA-PR-0056 | WPS & PQR | A |  | P | 2022-06-10 | [27 empty] | Welding map과 welder qualification record 포함
[5 empty] | A |  |  | 010
59 | VP-TEP-R0007-QA-PR-0058 | PMI procedure | A |  | P | 2022-03-04 |  |  |  | 2022-06-10
[5 empty] | A | 2022-03-07 | 2022-04-08 | 004 | 002 | 2022-07-11 |  | 011
60 | VP-TEP-R0007-QA-PR-0059 | Chemical cleaning procedure | A |  | P | 2022-06-10
[5 empty] | A | 2022-07-04 |  | 010
61 | VP-TEP-R0007-QA-PR-0061 | Instrument calibration procedure | A |  | P | 2022-11-04
A
62 | VP-TEP-R0007-QA-PL-0062 | Quality Plan | A |  | P | 2022-06-15
A
63 | VP-TEP-R0007-QA-PR-0064 | Inspection and Test Reports | A |  | P | 2022-12-15
A
Project Name |  | TONGYEONG LNG POWER PLAN PROJECT |  |  | P/O NO. |  |  |  | PO-TEP-R-0007-P | [8 empty] | Doc. No. | VP-TEP-R0007-ME-PM-0001 | [5 empty] | Rev. | [5 empty] | A
Vendor Name |  | SUEZ
Note
1. Abbreviation - RTS: Result of V/P Review, A: Approved, C: Approved with ComSTnts, R: Rjected, RS: Resubmit, FI: For Information
2. Vendor shall submit the revised docuSTnt within 14 calendar days after receive purchaser's response.