## Table 2
NO | DOCUMENT No | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-LI-0001 | Vendor Print Index & Schedule | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-LI-0002 | Sub-vendor List | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-LI-0003 | Commissioning Spare Part List | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-LI-0004 | Recommended Spare Part List (2 Year) | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-LI-0005 | Equipment List | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-LI-0006 | Utility Consumption List | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-LI-0007 | Lubricant List | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-LI-0008 | Electrical Load List | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-QA-PL-0001 | Inspection & Test Plan (Pump) | A4 |  | S | 2022-06-24 | [25 empty] | 품질
A
10 | VP-TEP-R0008-QA-PR-0001 | Inspection & Test Procedure (Pump) | A4 |  | S | 2022-06-24 | [25 empty] | 품질
A
11 | VP-TEP-R0008-QA-PL-0002 | Inspection & Test Plan (Motor) | A4 |  | S | 2022-06-21 | [25 empty] | 품질
[5 empty] | A | 6/21 |  | P-0003
12 | VP-TEP-R0008-QA-PR-0002 | Inspection & Test Procedure (Motor) | A4 |  | S | 2022-06-21 | [25 empty] | 품질
[5 empty] | A | 6/21 |  | P-0003
13 | VP-TEP-R0008-QA-PR-0003 | WPS & PQR | A4 |  | S | 2022-06-21 | [25 empty] | 품질
[5 empty] | A | 6/21 |  | P-0003
14 | VP-TEP-R0008-QA-PR-0004 | NDE Procedure | A4 |  | S | 2022-06-21 | [25 empty] | 품질
[5 empty] | A | 6/21 |  | P-0003
15 | VP-TEP-R0008-QA-PR-0005 | PMI Procedure | A4 |  | S | 2022-06-21 | [25 empty] | 품질
[5 empty] | A | 6/21 |  | P-0003
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
16 | VP-TEP-R0008-RO-PR-0006 | Painting Procedure | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
17 | VP-TEP-R0008-RO-PR-0007 | Packing Procedure | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
18 | VP-TEP-R0008-RO-MA-0001 | Operation & Maintenance Manual | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
19 | VP-TEP-R0008-QA-OT-0001 | Inspection & Test Report | A4 |  | S | 2022-12-27 | [25 empty] | 품질
A
20 | VP-TEP-R0008-PM-DB-0001 | Manufacturing Data Book | A4 |  | S | 2023-01-30
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0001 | Pump Data Sheet for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0002 | Pump Performance Curve for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0001 | Pump Calculation Sheet for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0001 | Pump Outline Drawing for Clean Drain Transfer Pump #A/#B | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0001 | Pump Sectional Drawing for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0001 | Pump P&ID for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0002 | Pump Name Plate Drawing for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0003 | Motor Data Sheet & Curve for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0002 | Motor Outline Drawing & T-Box Drawing for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0003 | Mechanical Seal Drawing for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0004 | Coupling Drawing for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0011 | Pump Data Sheet for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0012 | Pump Performance Curve for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0011 | Pump Calculation Sheet for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0011 | Pump Outline Drawing for #11 HRSG B/D Transfer Pump #A/#B | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0011 | Pump Sectional Drawing for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0011 | Pump P&ID for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0012 | Pump Name Plate Drawing for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0013 | Motor Data Sheet & Curve for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0012 | Motor Outline Drawing & T-Box Drawing for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0013 | Mechanical Seal Drawing for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0014 | Coupling Drawing for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0021 | Pump Data Sheet for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0022 | Pump Performance Curve for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0021 | Pump Calculation Sheet for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0021 | Pump Outline Drawing for #12 HRSG B/D Transfer Pump #A/#B | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0021 | Pump Sectional Drawing for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0021 | Pump P&ID for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0022 | Pump Name Plate Drawing for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0023 | Motor Data Sheet & Curve for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0022 | Motor Outline Drawing & T-Box Drawing for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0023 | Mechanical Seal Drawing for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0024 | Coupling Drawing for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0031 | Pump Data Sheet for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0032 | Pump Performance Curve for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0031 | Pump Calculation Sheet for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0031 | Pump Outline Drawing for Overboard Pump | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0031 | Pump Sectional Drawing for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0031 | Pump P&ID for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0032 | Pump Name Plate Drawing for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0033 | Motor Data Sheet & Curve for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0032 | Motor Outline Drawing & T-Box Drawing for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0033 | Mechanical Seal Drawing for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0034 | Coupling Drawing for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0041 | Pump Data Sheet for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0042 | Pump Performance Curve for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0041 | Pump Calculation Sheet for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0041 | Pump Outline Drawing for Sea Water Booster Pump | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0041 | Pump Sectional Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0041 | Pump P&ID for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0042 | Pump Name Plate Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0043 | Motor Data Sheet & Curve for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0042 | Motor Outline Drawing & T-Box Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0043 | Mechanical Seal Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0044 | Coupling Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
12 | VP-TEP-R0008-RO-OT-0045 | Junction Box Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 제어
[5 empty] | A | 6/21 |  | P-0004
13 | VP-TEP-R0008-RO-LI-0041 | Instrument List & Catalogue for Sea Water Booster Pump | A4 |  | S | 2022-06-24 | [25 empty] | 제어
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0051 | Pump Data Sheet for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0052 | Pump Performance Curve for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0051 | Pump Calculation Sheet for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0051 | Pump Outline Drawing for Closed Cooling Water Pump #A/#B/#C | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0051 | Pump Sectional Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0051 | Pump P&ID for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0052 | Pump Name Plate Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0053 | Motor Data Sheet & Curve for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0052 | Motor Outline Drawing & T-Box Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0053 | Mechanical Seal Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0054 | Coupling Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
12 | VP-TEP-R0008-RO-OT-0055 | Junction Box Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 제어
[5 empty] | A | 6/21 |  | P-0004
13 | VP-TEP-R0008-RO-LI-0051 | Instrument List & Catalogue for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-24 | [25 empty] | 제어
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0061 | Pump Data Sheet for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0062 | Pump Performance Curve for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0061 | Pump Calculation Sheet for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0061 | Pump Outline Drawing for Demi. Water Transfer Pump #A/#B/#C | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0061 | Pump Sectional Drawing for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0061 | Pump P&ID for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0062 | Pump Name Plate Drawing for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0063 | Motor Data Sheet & Curve for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-07-08 | [25 empty] | 전기
A
9 | VP-TEP-R0008-RO-GA-0062 | Motor Outline Drawing & T-Box Drawing for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-07-08 | [25 empty] | 전기
A
10 | VP-TEP-R0008-RO-OT-0063 | Mechanical Seal Drawing for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0064 | Coupling Drawing for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0071 | Pump Data Sheet for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0072 | Pump Performance Curve for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0071 | Pump Calculation Sheet for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0071 | Pump Outline Drawing for Service Water Pump #A/#B | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0071 | Pump Sectional Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0071 | Pump P&ID for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0072 | Name Plate Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0073 | Motor Data Sheet & Curve for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0072 | Motor Outline Drawing & T-Box Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0073 | Mechanical Seal Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0074 | Coupling Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
12 | VP-TEP-R0008-RO-GA-0073 | Pressure Tank Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
13 | VP-TEP-R0008-RO-OT-0075 | Local Control Panel Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 제어
[5 empty] | A | 6/21 |  | P-0004
14 | VP-TEP-R0008-RO-LI-0071 | Instrument List & Catalogue for Service Water Pump #A/#B | A4 |  | S | 2022-06-24 | [25 empty] | 제어
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE
1 | VP-TEP-R0008- RO-LI-0001 | Vendor Print Index & Schedule | S | 2022-06-21
2 |  |  | A | 6/21 |  | P-0001
3 | VP-TEP-R0008- RO-LI-0002 | Sub-vendor List | S | 2022-06-21
4 |  |  | A | 6/21 |  | P-0001
5 | VP-TEP-R0008- RO-LI-0003 | Commissioning Spare Part List | S | 2022-06-21
6 |  |  | A | 6/21 |  | P-0001
7 | VP-TEP-R0008- RO-LI-0004 | Recommended Spare Part List (2 Year) | S | 2022-06-21
8 |  |  | A | 6/21 |  | P-0001
9 | VP-TEP-R0008- RO-LI-0005 | Equipment List | S | 2022-06-21
10 |  |  | A | 6/21 |  | P-0001
11 | VP-TEP-R0008- RO-LI-0006 | Utility Consumption List | S | 2022-06-21
12 |  |  | A | 6/21 |  | P-0001
13 | VP-TEP-R0008- RO-LI-0007 | Lubricant List | S | 2022-06-21
14 |  |  | A | 6/21 |  | P-0001
15 | VP-TEP-R0008- RO-LI-0008 | Electrical Load List | S | 2022-06-21
16 |  |  | A | 6/21 |  | P-0002
17 | VP-TEP-R0008- QA-PL-0001 | Inspection & Test Plan (Pump) | S | 2022-06-24
18 |  |  | A
19 | VP-TEP-R0008- QA-PR-0001 | Inspection & Test Procedure (Pump) | S | 2022-06-24
20 |  |  | A
21 | VP-TEP-R0008- QA-PL-0002 | Inspection & Test Plan (Motor) | S | 2022-06-21
22 |  |  | A | 6/21 |  | P-0003
23 | VP-TEP-R0008- QA-PR-0002 | Inspection & Test Procedure (Motor) | S | 2022-06-21
24 |  |  | A | 6/21 |  | P-0003
25 | VP-TEP-R0008- QA-PR-0003 | WPS & PQR | S | 2022-06-21
26 |  |  | A | 6/21 |  | P-0003
27 | VP-TEP-R0008- QA-PR-0004 | NDE Procedure | S | 2022-06-21
28 |  |  | A | 6/21 |  | P-0003
29 | VP-TEP-R0008- QA-PR-0005 | PMI Procedure | S | 2022-06-21
30 |  |  | A | 6/21 |  | P-0003
31 | VP-TEP-R0008- RO-PR-0006 | Painting Procedure | S | 2022-06-21
32 |  |  | A | 6/21 |  | P-0001
33 | VP-TEP-R0008- RO-PR-0007 | Packing Procedure | S | 2022-06-21
34 |  |  | A | 6/21 |  | P-0001
35 | VP-TEP-R0008- RO-MA-0001 | Operation & Maintenance Manual | S | 2022-06-21
36 |  |  | A | 6/21 |  | P-0001
37 | VP-TEP-R0008- QA-OT-0001 | Inspection & Test Report | S | 2022-12-27
38 |  |  | A
39 | VP-TEP-R0008- PM-DB-0001 | Manufacturing Data Book | S | 2023-01-30
40 |  |  | A
41 | VP-TEP-R0008- RO-DS-0001 | Pump Data Sheet for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
42 |  |  | A | 6/21 |  | P-0001
43 | VP-TEP-R0008- RO-DS-0002 | Pump Performance Curve for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
44 |  |  | A | 6/21 |  | P-0001
45 | VP-TEP-R0008- RO-CA-0001 | Pump Calculation Sheet for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
46 |  |  | A | 6/21 |  | P-0001
47 | VP-TEP-R0008- RO-GA-0001 | Pump Outline Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
48 |  |  | A | 6/21 |  | P-0001
49 | VP-TEP-R0008- RO-OT-0001 | Pump Sectional Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
50 |  |  | A | 6/21 |  | P-0001
51 | VP-TEP-R0008- RO-PI-0001 | Pump P&ID for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
52 |  |  | A | 6/21 |  | P-0001
53 | VP-TEP-R0008- RO-OT-0002 | Pump Name Plate Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
54 |  |  | A | 6/21 |  | P-0001
55 | VP-TEP-R0008- RO-DS-0003 | Motor Data Sheet & Curve for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
56 |  |  | A | 6/21 |  | P-0002
57 | VP-TEP-R0008- RO-GA-0002 | Motor Outline Drawing & T-Box Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
58 |  |  | A | 6/21 |  | P-0002
59 | VP-TEP-R0008- RO-OT-0003 | Mechanical Seal Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
60 |  |  | A | 6/21 |  | P-0001
61 | VP-TEP-R0008- RO-OT-0004 | Coupling Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
62 |  |  | A | 6/21 |  | P-0001
63 | VP-TEP-R0008- RO-DS-0011 | Pump Data Sheet for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
64 |  |  | A | 6/21 |  | P-0001
65 | VP-TEP-R0008- RO-DS-0012 | Pump Performance Curve for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
66 |  |  | A | 6/21 |  | P-0001
67 | VP-TEP-R0008- RO-CA-0011 | Pump Calculation Sheet for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
68 |  |  | A | 6/21 |  | P-0001
69 | VP-TEP-R0008- RO-GA-0011 | Pump Outline Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
70 |  |  | A | 6/21 |  | P-0001
71 | VP-TEP-R0008- RO-OT-0011 | Pump Sectional Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
72 |  |  | A | 6/21 |  | P-0001
73 | VP-TEP-R0008- RO-PI-0011 | Pump P&ID for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
74 |  |  | A | 6/21 |  | P-0001
75 | VP-TEP-R0008- RO-OT-0012 | Pump Name Plate Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
76 |  |  | A | 6/21 |  | P-0001
77 | VP-TEP-R0008- RO-DS-0013 | Motor Data Sheet & Curve for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
78 |  |  | A | 6/21 |  | P-0002
79 | VP-TEP-R0008- RO-GA-0012 | Motor Outline Drawing & T-Box Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
80 |  |  | A | 6/21 |  | P-0002
81 | VP-TEP-R0008- RO-OT-0013 | Mechanical Seal Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
82 |  |  | A | 6/21 |  | P-0001
83 | VP-TEP-R0008- RO-OT-0014 | Coupling Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
84 |  |  | A | 6/21 |  | P-0001
85 | VP-TEP-R0008- RO-DS-0021 | Pump Data Sheet for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
86 |  |  | A | 6/21 |  | P-0001
87 | VP-TEP-R0008- RO-DS-0022 | Pump Performance Curve for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
88 |  |  | A | 6/21 |  | P-0001
89 | VP-TEP-R0008- RO-CA-0021 | Pump Calculation Sheet for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
90 |  |  | A | 6/21 |  | P-0001
91 | VP-TEP-R0008- RO-GA-0021 | Pump Outline Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
92 |  |  | A | 6/21 |  | P-0001
93 | VP-TEP-R0008- RO-OT-0021 | Pump Sectional Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
94 |  |  | A | 6/21 |  | P-0001
95 | VP-TEP-R0008- RO-PI-0021 | Pump P&ID for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
96 |  |  | A | 6/21 |  | P-0001
97 | VP-TEP-R0008- RO-OT-0022 | Pump Name Plate Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
98 |  |  | A | 6/21 |  | P-0001
99 | VP-TEP-R0008- RO-DS-0023 | Motor Data Sheet & Curve for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
100 |  |  | A | 6/21 |  | P-0002
101 | VP-TEP-R0008- RO-GA-0022 | Motor Outline Drawing & T-Box Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
102 |  |  | A | 6/21 |  | P-0002
103 | VP-TEP-R0008- RO-OT-0023 | Mechanical Seal Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
104 |  |  | A | 6/21 |  | P-0001
105 | VP-TEP-R0008- RO-OT-0024 | Coupling Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
106 |  |  | A | 6/21 |  | P-0001
107 | VP-TEP-R0008- RO-DS-0031 | Pump Data Sheet for Overboard Pump | S | 2022-06-21
108 |  |  | A | 6/21 |  | P-0001
109 | VP-TEP-R0008- RO-DS-0032 | Pump Performance Curve for Overboard Pump | S | 2022-06-21
110 |  |  | A | 6/21 |  | P-0001
111 | VP-TEP-R0008- RO-CA-0031 | Pump Calculation Sheet for Overboard Pump | S | 2022-06-21
112 |  |  | A | 6/21 |  | P-0001
113 | VP-TEP-R0008- RO-GA-0031 | Pump Outline Drawing for Overboard Pump | S | 2022-06-21
114 |  |  | A | 6/21 |  | P-0001
115 | VP-TEP-R0008- RO-OT-0031 | Pump Sectional Drawing for Overboard Pump | S | 2022-06-21
116 |  |  | A | 6/21 |  | P-0001
117 | VP-TEP-R0008- RO-PI-0031 | Pump P&ID for Overboard Pump | S | 2022-06-21
118 |  |  | A | 6/21 |  | P-0001
119 | VP-TEP-R0008- RO-OT-0032 | Pump Name Plate Drawing for Overboard Pump | S | 2022-06-21
120 |  |  | A | 6/21 |  | P-0001
121 | VP-TEP-R0008- RO-DS-0033 | Motor Data Sheet & Curve for Overboard Pump | S | 2022-06-21
122 |  |  | A | 6/21 |  | P-0002
123 | VP-TEP-R0008- RO-GA-0032 | Motor Outline Drawing & T-Box Drawing for Overboard Pump | S | 2022-06-21
124 |  |  | A | 6/21 |  | P-0002
125 | VP-TEP-R0008- RO-OT-0033 | Mechanical Seal Drawing for Overboard Pump | S | 2022-06-21
126 |  |  | A | 6/21 |  | P-0001
127 | VP-TEP-R0008- RO-OT-0034 | Coupling Drawing for Overboard Pump | S | 2022-06-21
128 |  |  | A | 6/21 |  | P-0001
129 | VP-TEP-R0008- RO-DS-0041 | Pump Data Sheet for Sea Water Booster Pump | S | 2022-06-21
130 |  |  | A | 6/21 |  | P-0001
131 | VP-TEP-R0008- RO-DS-0042 | Pump Performance Curve for Sea Water Booster Pump | S | 2022-06-21
132 |  |  | A | 6/21 |  | P-0001
133 | VP-TEP-R0008- RO-CA-0041 | Pump Calculation Sheet for Sea Water Booster Pump | S | 2022-06-21
134 |  |  | A | 6/21 |  | P-0001
135 | VP-TEP-R0008- RO-GA-0041 | Pump Outline Drawing for Sea Water Booster Pump | S | 2022-06-21
136 |  |  | A | 6/21 |  | P-0001
137 | VP-TEP-R0008- RO-OT-0041 | Pump Sectional Drawing for Sea Water Booster Pump | S | 2022-06-21
138 |  |  | A | 6/21 |  | P-0001
139 | VP-TEP-R0008- RO-PI-0041 | Pump P&ID for Sea Water Booster Pump | S | 2022-06-21
140 |  |  | A | 6/21 |  | P-0001
141 | VP-TEP-R0008- RO-OT-0042 | Pump Name Plate Drawing for Sea Water Booster Pump | S | 2022-06-21
142 |  |  | A | 6/21 |  | P-0001
143 | VP-TEP-R0008- RO-DS-0043 | Motor Data Sheet & Curve for Sea Water Booster Pump | S | 2022-06-21
144 |  |  | A | 6/21 |  | P-0002
145 | VP-TEP-R0008- RO-GA-0042 | Motor Outline Drawing & T-Box Drawing for Sea Water Booster Pump | S | 2022-06-21
146 |  |  | A | 6/21 |  | P-0002
147 | VP-TEP-R0008- RO-OT-0043 | Mechanical Seal Drawing for Sea Water Booster Pump | S | 2022-06-21
148 |  |  | A | 6/21 |  | P-0001
149 | VP-TEP-R0008- RO-OT-0044 | Coupling Drawing for Sea Water Booster Pump | S | 2022-06-21
150 |  |  | A | 6/21 |  | P-0001
151 | VP-TEP-R0008- RO-OT-0045 | Junction Box Drawing for Sea Water Booster Pump | S | 2022-06-21
152 |  |  | A | 6/21 |  | P-0004
153 | VP-TEP-R0008- RO-LI-0041 | Instrument List & Catalogue for Sea Water Booster Pump | S | 2022-06-24
154 |  |  | A
155 | VP-TEP-R0008- RO-DS-0051 | Pump Data Sheet for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
156 |  |  | A | 6/21 |  | P-0001
157 | VP-TEP-R0008- RO-DS-0052 | Pump Performance Curve for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
158 |  |  | A | 6/21 |  | P-0001
159 | VP-TEP-R0008- RO-CA-0051 | Pump Calculation Sheet for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
160 |  |  | A | 6/21 |  | P-0001
161 | VP-TEP-R0008- RO-GA-0051 | Pump Outline Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
162 |  |  | A | 6/21 |  | P-0001
163 | VP-TEP-R0008- RO-OT-0051 | Pump Sectional Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
164 |  |  | A | 6/21 |  | P-0001
165 | VP-TEP-R0008- RO-PI-0051 | Pump P&ID for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
166 |  |  | A | 6/21 |  | P-0001
167 | VP-TEP-R0008- RO-OT-0052 | Pump Name Plate Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
168 |  |  | A | 6/21 |  | P-0001
169 | VP-TEP-R0008- RO-DS-0053 | Motor Data Sheet & Curve for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
170 |  |  | A | 6/21 |  | P-0002
171 | VP-TEP-R0008- RO-GA-0052 | Motor Outline Drawing & T-Box Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
172 |  |  | A | 6/21 |  | P-0002
173 | VP-TEP-R0008- RO-OT-0053 | Mechanical Seal Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
174 |  |  | A | 6/21 |  | P-0001
175 | VP-TEP-R0008- RO-OT-0054 | Coupling Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
176 |  |  | A | 6/21 |  | P-0001
177 | VP-TEP-R0008- RO-OT-0055 | Junction Box Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
178 |  |  | A | 6/21 |  | P-0004
179 | VP-TEP-R0008- RO-LI-0051 | Instrument List & Catalogue for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-24
180 |  |  | A
181 | VP-TEP-R0008- RO-DS-0061 | Pump Data Sheet for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
182 |  |  | A | 6/21 |  | P-0001
183 | VP-TEP-R0008- RO-DS-0062 | Pump Performance Curve for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
184 |  |  | A | 6/21 |  | P-0001
185 | VP-TEP-R0008- RO-CA-0061 | Pump Calculation Sheet for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
186 |  |  | A | 6/21 |  | P-0001
187 | VP-TEP-R0008- RO-GA-0061 | Pump Outline Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
188 |  |  | A | 6/21 |  | P-0001
189 | VP-TEP-R0008- RO-OT-0061 | Pump Sectional Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
190 |  |  | A | 6/21 |  | P-0001
191 | VP-TEP-R0008- RO-PI-0061 | Pump P&ID for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
192 |  |  | A | 6/21 |  | P-0001
193 | VP-TEP-R0008- RO-OT-0062 | Pump Name Plate Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
194 |  |  | A | 6/21 |  | P-0001
195 | VP-TEP-R0008- RO-DS-0063 | Motor Data Sheet & Curve for Demi. Water Transfer Pump #A/#B/#C | S | 2022-07-08
196 |  |  | A
197 | VP-TEP-R0008- RO-GA-0062 | Motor Outline Drawing & T-Box Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-07-08
198 |  |  | A
199 | VP-TEP-R0008- RO-OT-0063 | Mechanical Seal Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
200 |  |  | A | 6/21 |  | P-0001
201 | VP-TEP-R0008- RO-OT-0064 | Coupling Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
202 |  |  | A | 6/21 |  | P-0001
203 | VP-TEP-R0008- RO-DS-0071 | Pump Data Sheet for Service Water Pump #A/#B | S | 2022-06-21
204 |  |  | A | 6/21 |  | P-0001
205 | VP-TEP-R0008- RO-DS-0072 | Pump Performance Curve for Service Water Pump #A/#B | S | 2022-06-21
206 |  |  | A | 6/21 |  | P-0001
207 | VP-TEP-R0008- RO-CA-0071 | Pump Calculation Sheet for Service Water Pump #A/#B | S | 2022-06-21
208 |  |  | A | 6/21 |  | P-0001
209 | VP-TEP-R0008- RO-GA-0071 | Pump Outline Drawing for Service Water Pump #A/#B | S | 2022-06-21
210 |  |  | A | 6/21 |  | P-0001
211 | VP-TEP-R0008- RO-OT-0071 | Pump Sectional Drawing for Service Water Pump #A/#B | S | 2022-06-21
212 |  |  | A | 6/21 |  | P-0001
213 | VP-TEP-R0008- RO-PI-0071 | Pump P&ID for Service Water Pump #A/#B | S | 2022-06-21
214 |  |  | A | 6/21 |  | P-0001
215 | VP-TEP-R0008- RO-OT-0072 | Name Plate Drawing for Service Water Pump #A/#B | S | 2022-06-21
216 |  |  | A | 6/21 |  | P-0001
217 | VP-TEP-R0008- RO-DS-0073 | Motor Data Sheet & Curve for Service Water Pump #A/#B | S | 2022-06-21
218 |  |  | A | 6/21 |  | P-0002
219 | VP-TEP-R0008- RO-GA-0072 | Motor Outline Drawing & T-Box Drawing for Service Water Pump #A/#B | S | 2022-06-21
220 |  |  | A | 6/21 |  | P-0002
221 | VP-TEP-R0008- RO-OT-0073 | Mechanical Seal Drawing for Service Water Pump #A/#B | S | 2022-06-21
222 |  |  | A | 6/21 |  | P-0001
223 | VP-TEP-R0008- RO-OT-0074 | Coupling Drawing for Service Water Pump #A/#B | S | 2022-06-21
224 |  |  | A | 6/21 |  | P-0001
225 | VP-TEP-R0008- RO-GA-0073 | Pressure Tank Drawing for Service Water Pump #A/#B | S | 2022-06-21
226 |  |  | A | 6/21 |  | P-0001
227 | VP-TEP-R0008- RO-OT-0075 | Local Control Panel Drawing for Service Water Pump #A/#B | S | 2022-06-21
228 |  |  | A | 6/21 |  | P-0004
229 | VP-TEP-R0008- RO-LI-0071 | Instrument List & Catalogue for Service Water Pump #A/#B | S | 2022-06-24
230 |  |  | A

## Table 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
16 | VP-TEP-R0008-RO-PR-0006 | Painting Procedure | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
17 | VP-TEP-R0008-RO-PR-0007 | Packing Procedure | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
18 | VP-TEP-R0008-RO-MA-0001 | Operation & Maintenance Manual | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
19 | VP-TEP-R0008-QA-OT-0001 | Inspection & Test Report | A4 |  | S | 2022-12-27 | [25 empty] | 품질
A
20 | VP-TEP-R0008-PM-DB-0001 | Manufacturing Data Book | A4 |  | S | 2023-01-30
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3

## Table 4
NAME OF EQUIPMENT: General Service Pump ITEM NO. : 14LCM11/12AP001
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0001 | Pump Data Sheet for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0002 | Pump Performance Curve for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0001 | Pump Calculation Sheet for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0001 | Pump Outline Drawing for Clean Drain Transfer Pump #A/#B | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0001 | Pump Sectional Drawing for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0001 | Pump P&ID for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0002 | Pump Name Plate Drawing for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0003 | Motor Data Sheet & Curve for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0002 | Motor Outline Drawing & T-Box Drawing for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0003 | Mechanical Seal Drawing for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0004 | Coupling Drawing for Clean Drain Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3

## Table 5
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0011 | Pump Data Sheet for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0012 | Pump Performance Curve for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0011 | Pump Calculation Sheet for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0011 | Pump Outline Drawing for #11 HRSG B/D Transfer Pump #A/#B | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0011 | Pump Sectional Drawing for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0011 | Pump P&ID for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0012 | Pump Name Plate Drawing for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0013 | Motor Data Sheet & Curve for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0012 | Motor Outline Drawing & T-Box Drawing for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0013 | Mechanical Seal Drawing for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0014 | Coupling Drawing for #11 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3

## Table 6
NAME OF EQUIPMENT: General Service Pump ITEM NO. : 16LCL11/12AP001
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0021 | Pump Data Sheet for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0022 | Pump Performance Curve for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0021 | Pump Calculation Sheet for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0021 | Pump Outline Drawing for #12 HRSG B/D Transfer Pump #A/#B | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0021 | Pump Sectional Drawing for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0021 | Pump P&ID for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0022 | Pump Name Plate Drawing for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0023 | Motor Data Sheet & Curve for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0022 | Motor Outline Drawing & T-Box Drawing for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0023 | Mechanical Seal Drawing for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0024 | Coupling Drawing for #12 HRSG B/D Transfer Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3

## Table 7
NAME OF EQUIPMENT: General Service Pump ITEM NO. : 14LCB20AP001
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0031 | Pump Data Sheet for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0032 | Pump Performance Curve for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0031 | Pump Calculation Sheet for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0031 | Pump Outline Drawing for Overboard Pump | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0031 | Pump Sectional Drawing for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0031 | Pump P&ID for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0032 | Pump Name Plate Drawing for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0033 | Motor Data Sheet & Curve for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0032 | Motor Outline Drawing & T-Box Drawing for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0033 | Mechanical Seal Drawing for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0034 | Coupling Drawing for Overboard Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3

## Table 8
NAME OF EQUIPMENT: General Service Pump ITEM NO. : 14PCC12AP001
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0041 | Pump Data Sheet for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0042 | Pump Performance Curve for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0041 | Pump Calculation Sheet for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0041 | Pump Outline Drawing for Sea Water Booster Pump | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0041 | Pump Sectional Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0041 | Pump P&ID for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0042 | Pump Name Plate Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0043 | Motor Data Sheet & Curve for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0042 | Motor Outline Drawing & T-Box Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0043 | Mechanical Seal Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0044 | Coupling Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
12 | VP-TEP-R0008-RO-OT-0045 | Junction Box Drawing for Sea Water Booster Pump | A4 |  | S | 2022-06-21 | [25 empty] | 제어
[5 empty] | A | 6/21 |  | P-0004
13 | VP-TEP-R0008-RO-LI-0041 | Instrument List & Catalogue for Sea Water Booster Pump | A4 |  | S | 2022-06-24 | [25 empty] | 제어
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3

## Table 9
NAME OF EQUIPMENT: General Service Pump ITEM NO. : 14PGB11/12/13AP001
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0051 | Pump Data Sheet for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0052 | Pump Performance Curve for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0051 | Pump Calculation Sheet for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0051 | Pump Outline Drawing for Closed Cooling Water Pump #A/#B/#C | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0051 | Pump Sectional Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0051 | Pump P&ID for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0052 | Pump Name Plate Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0053 | Motor Data Sheet & Curve for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0052 | Motor Outline Drawing & T-Box Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0053 | Mechanical Seal Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0054 | Coupling Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
12 | VP-TEP-R0008-RO-OT-0055 | Junction Box Drawing for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 제어
[5 empty] | A | 6/21 |  | P-0004
13 | VP-TEP-R0008-RO-LI-0051 | Instrument List & Catalogue for Closed Cooling Water Pump #A/#B/#C | A4 |  | S | 2022-06-24 | [25 empty] | 제어
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3

## Table 10
NAME OF EQUIPMENT: General Service Pump ITEM NO. : 14GHC01AP001/002/003
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0061 | Pump Data Sheet for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0062 | Pump Performance Curve for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0061 | Pump Calculation Sheet for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0061 | Pump Outline Drawing for Demi. Water Transfer Pump #A/#B/#C | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0061 | Pump Sectional Drawing for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0061 | Pump P&ID for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0062 | Pump Name Plate Drawing for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0063 | Motor Data Sheet & Curve for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-07-08 | [25 empty] | 전기
A
9 | VP-TEP-R0008-RO-GA-0062 | Motor Outline Drawing & T-Box Drawing for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-07-08 | [25 empty] | 전기
A
10 | VP-TEP-R0008-RO-OT-0063 | Mechanical Seal Drawing for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0064 | Coupling Drawing for Demi. Water Transfer Pump #A/#B/#C | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3

## Table 11
NAME OF EQUIPMENT: General Service Pump ITEM NO. : 14GHA01AP001/002
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0008-RO-DS-0071 | Pump Data Sheet for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
2 | VP-TEP-R0008-RO-DS-0072 | Pump Performance Curve for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
3 | VP-TEP-R0008-RO-CA-0071 | Pump Calculation Sheet for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
4 | VP-TEP-R0008-RO-GA-0071 | Pump Outline Drawing for Service Water Pump #A/#B | A3 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
5 | VP-TEP-R0008-RO-OT-0071 | Pump Sectional Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
6 | VP-TEP-R0008-RO-PI-0071 | Pump P&ID for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
7 | VP-TEP-R0008-RO-OT-0072 | Name Plate Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
8 | VP-TEP-R0008-RO-DS-0073 | Motor Data Sheet & Curve for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
9 | VP-TEP-R0008-RO-GA-0072 | Motor Outline Drawing & T-Box Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 전기
[5 empty] | A | 6/21 |  | P-0002
10 | VP-TEP-R0008-RO-OT-0073 | Mechanical Seal Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
11 | VP-TEP-R0008-RO-OT-0074 | Coupling Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
12 | VP-TEP-R0008-RO-GA-0073 | Pressure Tank Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 기계
[5 empty] | A | 6/21 |  | P-0001
13 | VP-TEP-R0008-RO-OT-0075 | Local Control Panel Drawing for Service Water Pump #A/#B | A4 |  | S | 2022-06-21 | [25 empty] | 제어
[5 empty] | A | 6/21 |  | P-0004
14 | VP-TEP-R0008-RO-LI-0071 | Instrument List & Catalogue for Service Water Pump #A/#B | A4 |  | S | 2022-06-24 | [25 empty] | 제어
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | RFQ-TEP-R-0008-P | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0008-P |  |  | DATE |  |  |  |  | 2022-06-21 | [14 empty] | 1 | [5 empty] | 3

## Sheet1
NO | DOCUMENT NO | DOCUMENT TITLE
1 | VP-TEP-R0008- RO-LI-0001 | Vendor Print Index & Schedule | S | 2022-06-21
2 |  |  | A | 6/21 | P-0001
3 | VP-TEP-R0008- RO-LI-0002 | Sub-vendor List | S | 2022-06-21
4 |  |  | A | 6/21 | P-0001
5 | VP-TEP-R0008- RO-LI-0003 | Commissioning Spare Part List | S | 2022-06-21
6 |  |  | A | 6/21 | P-0001
7 | VP-TEP-R0008- RO-LI-0004 | Recommended Spare Part List (2 Year) | S | 2022-06-21
8 |  |  | A | 6/21 | P-0001
9 | VP-TEP-R0008- RO-LI-0005 | Equipment List | S | 2022-06-21
10 |  |  | A | 6/21 | P-0001
11 | VP-TEP-R0008- RO-LI-0006 | Utility Consumption List | S | 2022-06-21
12 |  |  | A | 6/21 | P-0001
13 | VP-TEP-R0008- RO-LI-0007 | Lubricant List | S | 2022-06-21
14 |  |  | A | 6/21 | P-0001
15 | VP-TEP-R0008- RO-LI-0008 | Electrical Load List | S | 2022-06-21
16 |  |  | A | 6/21 | P-0002
17 | VP-TEP-R0008- QA-PL-0001 | Inspection & Test Plan (Pump) | S | 2022-06-24
18 |  |  | A
19 | VP-TEP-R0008- QA-PR-0001 | Inspection & Test Procedure (Pump) | S | 2022-06-24
20 |  |  | A
21 | VP-TEP-R0008- QA-PL-0002 | Inspection & Test Plan (Motor) | S | 2022-06-21
22 |  |  | A | 6/21 | P-0003
23 | VP-TEP-R0008- QA-PR-0002 | Inspection & Test Procedure (Motor) | S | 2022-06-21
24 |  |  | A | 6/21 | P-0003
25 | VP-TEP-R0008- QA-PR-0003 | WPS & PQR | S | 2022-06-21
26 |  |  | A | 6/21 | P-0003
27 | VP-TEP-R0008- QA-PR-0004 | NDE Procedure | S | 2022-06-21
28 |  |  | A | 6/21 | P-0003
29 | VP-TEP-R0008- QA-PR-0005 | PMI Procedure | S | 2022-06-21
30 |  |  | A | 6/21 | P-0003
31 | VP-TEP-R0008- RO-PR-0006 | Painting Procedure | S | 2022-06-21
32 |  |  | A | 6/21 | P-0001
33 | VP-TEP-R0008- RO-PR-0007 | Packing Procedure | S | 2022-06-21
34 |  |  | A | 6/21 | P-0001
35 | VP-TEP-R0008- RO-MA-0001 | Operation & Maintenance Manual | S | 2022-06-21
36 |  |  | A | 6/21 | P-0001
37 | VP-TEP-R0008- QA-OT-0001 | Inspection & Test Report | S | 2022-12-27
38 |  |  | A
39 | VP-TEP-R0008- PM-DB-0001 | Manufacturing Data Book | S | 2023-01-30
40 |  |  | A
41 | VP-TEP-R0008- RO-DS-0001 | Pump Data Sheet for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
42 |  |  | A | 6/21 | P-0001
43 | VP-TEP-R0008- RO-DS-0002 | Pump Performance Curve for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
44 |  |  | A | 6/21 | P-0001
45 | VP-TEP-R0008- RO-CA-0001 | Pump Calculation Sheet for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
46 |  |  | A | 6/21 | P-0001
47 | VP-TEP-R0008- RO-GA-0001 | Pump Outline Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
48 |  |  | A | 6/21 | P-0001
49 | VP-TEP-R0008- RO-OT-0001 | Pump Sectional Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
50 |  |  | A | 6/21 | P-0001
51 | VP-TEP-R0008- RO-PI-0001 | Pump P&ID for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
52 |  |  | A | 6/21 | P-0001
53 | VP-TEP-R0008- RO-OT-0002 | Pump Name Plate Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
54 |  |  | A | 6/21 | P-0001
55 | VP-TEP-R0008- RO-DS-0003 | Motor Data Sheet & Curve for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
56 |  |  | A | 6/21 | P-0002
57 | VP-TEP-R0008- RO-GA-0002 | Motor Outline Drawing & T-Box Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
58 |  |  | A | 6/21 | P-0002
59 | VP-TEP-R0008- RO-OT-0003 | Mechanical Seal Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
60 |  |  | A | 6/21 | P-0001
61 | VP-TEP-R0008- RO-OT-0004 | Coupling Drawing for Clean Drain Transfer Pump #A/#B | S | 2022-06-21
62 |  |  | A | 6/21 | P-0001
63 | VP-TEP-R0008- RO-DS-0011 | Pump Data Sheet for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
64 |  |  | A | 6/21 | P-0001
65 | VP-TEP-R0008- RO-DS-0012 | Pump Performance Curve for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
66 |  |  | A | 6/21 | P-0001
67 | VP-TEP-R0008- RO-CA-0011 | Pump Calculation Sheet for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
68 |  |  | A | 6/21 | P-0001
69 | VP-TEP-R0008- RO-GA-0011 | Pump Outline Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
70 |  |  | A | 6/21 | P-0001
71 | VP-TEP-R0008- RO-OT-0011 | Pump Sectional Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
72 |  |  | A | 6/21 | P-0001
73 | VP-TEP-R0008- RO-PI-0011 | Pump P&ID for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
74 |  |  | A | 6/21 | P-0001
75 | VP-TEP-R0008- RO-OT-0012 | Pump Name Plate Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
76 |  |  | A | 6/21 | P-0001
77 | VP-TEP-R0008- RO-DS-0013 | Motor Data Sheet & Curve for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
78 |  |  | A | 6/21 | P-0002
79 | VP-TEP-R0008- RO-GA-0012 | Motor Outline Drawing & T-Box Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
80 |  |  | A | 6/21 | P-0002
81 | VP-TEP-R0008- RO-OT-0013 | Mechanical Seal Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
82 |  |  | A | 6/21 | P-0001
83 | VP-TEP-R0008- RO-OT-0014 | Coupling Drawing for #11 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
84 |  |  | A | 6/21 | P-0001
85 | VP-TEP-R0008- RO-DS-0021 | Pump Data Sheet for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
86 |  |  | A | 6/21 | P-0001
87 | VP-TEP-R0008- RO-DS-0022 | Pump Performance Curve for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
88 |  |  | A | 6/21 | P-0001
89 | VP-TEP-R0008- RO-CA-0021 | Pump Calculation Sheet for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
90 |  |  | A | 6/21 | P-0001
91 | VP-TEP-R0008- RO-GA-0021 | Pump Outline Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
92 |  |  | A | 6/21 | P-0001
93 | VP-TEP-R0008- RO-OT-0021 | Pump Sectional Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
94 |  |  | A | 6/21 | P-0001
95 | VP-TEP-R0008- RO-PI-0021 | Pump P&ID for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
96 |  |  | A | 6/21 | P-0001
97 | VP-TEP-R0008- RO-OT-0022 | Pump Name Plate Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
98 |  |  | A | 6/21 | P-0001
99 | VP-TEP-R0008- RO-DS-0023 | Motor Data Sheet & Curve for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
100 |  |  | A | 6/21 | P-0002
101 | VP-TEP-R0008- RO-GA-0022 | Motor Outline Drawing & T-Box Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
102 |  |  | A | 6/21 | P-0002
103 | VP-TEP-R0008- RO-OT-0023 | Mechanical Seal Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
104 |  |  | A | 6/21 | P-0001
105 | VP-TEP-R0008- RO-OT-0024 | Coupling Drawing for #12 HRSG B/D Transfer Pump #A/#B | S | 2022-06-21
106 |  |  | A | 6/21 | P-0001
107 | VP-TEP-R0008- RO-DS-0031 | Pump Data Sheet for Overboard Pump | S | 2022-06-21
108 |  |  | A | 6/21 | P-0001
109 | VP-TEP-R0008- RO-DS-0032 | Pump Performance Curve for Overboard Pump | S | 2022-06-21
110 |  |  | A | 6/21 | P-0001
111 | VP-TEP-R0008- RO-CA-0031 | Pump Calculation Sheet for Overboard Pump | S | 2022-06-21
112 |  |  | A | 6/21 | P-0001
113 | VP-TEP-R0008- RO-GA-0031 | Pump Outline Drawing for Overboard Pump | S | 2022-06-21
114 |  |  | A | 6/21 | P-0001
115 | VP-TEP-R0008- RO-OT-0031 | Pump Sectional Drawing for Overboard Pump | S | 2022-06-21
116 |  |  | A | 6/21 | P-0001
117 | VP-TEP-R0008- RO-PI-0031 | Pump P&ID for Overboard Pump | S | 2022-06-21
118 |  |  | A | 6/21 | P-0001
119 | VP-TEP-R0008- RO-OT-0032 | Pump Name Plate Drawing for Overboard Pump | S | 2022-06-21
120 |  |  | A | 6/21 | P-0001
121 | VP-TEP-R0008- RO-DS-0033 | Motor Data Sheet & Curve for Overboard Pump | S | 2022-06-21
122 |  |  | A | 6/21 | P-0002
123 | VP-TEP-R0008- RO-GA-0032 | Motor Outline Drawing & T-Box Drawing for Overboard Pump | S | 2022-06-21
124 |  |  | A | 6/21 | P-0002
125 | VP-TEP-R0008- RO-OT-0033 | Mechanical Seal Drawing for Overboard Pump | S | 2022-06-21
126 |  |  | A | 6/21 | P-0001
127 | VP-TEP-R0008- RO-OT-0034 | Coupling Drawing for Overboard Pump | S | 2022-06-21
128 |  |  | A | 6/21 | P-0001
129 | VP-TEP-R0008- RO-DS-0041 | Pump Data Sheet for Sea Water Booster Pump | S | 2022-06-21
130 |  |  | A | 6/21 | P-0001
131 | VP-TEP-R0008- RO-DS-0042 | Pump Performance Curve for Sea Water Booster Pump | S | 2022-06-21
132 |  |  | A | 6/21 | P-0001
133 | VP-TEP-R0008- RO-CA-0041 | Pump Calculation Sheet for Sea Water Booster Pump | S | 2022-06-21
134 |  |  | A | 6/21 | P-0001
135 | VP-TEP-R0008- RO-GA-0041 | Pump Outline Drawing for Sea Water Booster Pump | S | 2022-06-21
136 |  |  | A | 6/21 | P-0001
137 | VP-TEP-R0008- RO-OT-0041 | Pump Sectional Drawing for Sea Water Booster Pump | S | 2022-06-21
138 |  |  | A | 6/21 | P-0001
139 | VP-TEP-R0008- RO-PI-0041 | Pump P&ID for Sea Water Booster Pump | S | 2022-06-21
140 |  |  | A | 6/21 | P-0001
141 | VP-TEP-R0008- RO-OT-0042 | Pump Name Plate Drawing for Sea Water Booster Pump | S | 2022-06-21
142 |  |  | A | 6/21 | P-0001
143 | VP-TEP-R0008- RO-DS-0043 | Motor Data Sheet & Curve for Sea Water Booster Pump | S | 2022-06-21
144 |  |  | A | 6/21 | P-0002
145 | VP-TEP-R0008- RO-GA-0042 | Motor Outline Drawing & T-Box Drawing for Sea Water Booster Pump | S | 2022-06-21
146 |  |  | A | 6/21 | P-0002
147 | VP-TEP-R0008- RO-OT-0043 | Mechanical Seal Drawing for Sea Water Booster Pump | S | 2022-06-21
148 |  |  | A | 6/21 | P-0001
149 | VP-TEP-R0008- RO-OT-0044 | Coupling Drawing for Sea Water Booster Pump | S | 2022-06-21
150 |  |  | A | 6/21 | P-0001
151 | VP-TEP-R0008- RO-OT-0045 | Junction Box Drawing for Sea Water Booster Pump | S | 2022-06-21
152 |  |  | A | 6/21 | P-0004
153 | VP-TEP-R0008- RO-LI-0041 | Instrument List & Catalogue for Sea Water Booster Pump | S | 2022-06-24
154 |  |  | A
155 | VP-TEP-R0008- RO-DS-0051 | Pump Data Sheet for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
156 |  |  | A | 6/21 | P-0001
157 | VP-TEP-R0008- RO-DS-0052 | Pump Performance Curve for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
158 |  |  | A | 6/21 | P-0001
159 | VP-TEP-R0008- RO-CA-0051 | Pump Calculation Sheet for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
160 |  |  | A | 6/21 | P-0001
161 | VP-TEP-R0008- RO-GA-0051 | Pump Outline Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
162 |  |  | A | 6/21 | P-0001
163 | VP-TEP-R0008- RO-OT-0051 | Pump Sectional Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
164 |  |  | A | 6/21 | P-0001
165 | VP-TEP-R0008- RO-PI-0051 | Pump P&ID for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
166 |  |  | A | 6/21 | P-0001
167 | VP-TEP-R0008- RO-OT-0052 | Pump Name Plate Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
168 |  |  | A | 6/21 | P-0001
169 | VP-TEP-R0008- RO-DS-0053 | Motor Data Sheet & Curve for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
170 |  |  | A | 6/21 | P-0002
171 | VP-TEP-R0008- RO-GA-0052 | Motor Outline Drawing & T-Box Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
172 |  |  | A | 6/21 | P-0002
173 | VP-TEP-R0008- RO-OT-0053 | Mechanical Seal Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
174 |  |  | A | 6/21 | P-0001
175 | VP-TEP-R0008- RO-OT-0054 | Coupling Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
176 |  |  | A | 6/21 | P-0001
177 | VP-TEP-R0008- RO-OT-0055 | Junction Box Drawing for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-21
178 |  |  | A | 6/21 | P-0004
179 | VP-TEP-R0008- RO-LI-0051 | Instrument List & Catalogue for Closed Cooling Water Pump #A/#B/#C | S | 2022-06-24
180 |  |  | A
181 | VP-TEP-R0008- RO-DS-0061 | Pump Data Sheet for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
182 |  |  | A | 6/21 | P-0001
183 | VP-TEP-R0008- RO-DS-0062 | Pump Performance Curve for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
184 |  |  | A | 6/21 | P-0001
185 | VP-TEP-R0008- RO-CA-0061 | Pump Calculation Sheet for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
186 |  |  | A | 6/21 | P-0001
187 | VP-TEP-R0008- RO-GA-0061 | Pump Outline Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
188 |  |  | A | 6/21 | P-0001
189 | VP-TEP-R0008- RO-OT-0061 | Pump Sectional Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
190 |  |  | A | 6/21 | P-0001
191 | VP-TEP-R0008- RO-PI-0061 | Pump P&ID for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
192 |  |  | A | 6/21 | P-0001
193 | VP-TEP-R0008- RO-OT-0062 | Pump Name Plate Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
194 |  |  | A | 6/21 | P-0001
195 | VP-TEP-R0008- RO-DS-0063 | Motor Data Sheet & Curve for Demi. Water Transfer Pump #A/#B/#C | S | 2022-07-08
196 |  |  | A
197 | VP-TEP-R0008- RO-GA-0062 | Motor Outline Drawing & T-Box Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-07-08
198 |  |  | A
199 | VP-TEP-R0008- RO-OT-0063 | Mechanical Seal Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
200 |  |  | A | 6/21 | P-0001
201 | VP-TEP-R0008- RO-OT-0064 | Coupling Drawing for Demi. Water Transfer Pump #A/#B/#C | S | 2022-06-21
202 |  |  | A | 6/21 | P-0001
203 | VP-TEP-R0008- RO-DS-0071 | Pump Data Sheet for Service Water Pump #A/#B | S | 2022-06-21
204 |  |  | A | 6/21 | P-0001
205 | VP-TEP-R0008- RO-DS-0072 | Pump Performance Curve for Service Water Pump #A/#B | S | 2022-06-21
206 |  |  | A | 6/21 | P-0001
207 | VP-TEP-R0008- RO-CA-0071 | Pump Calculation Sheet for Service Water Pump #A/#B | S | 2022-06-21
208 |  |  | A | 6/21 | P-0001
209 | VP-TEP-R0008- RO-GA-0071 | Pump Outline Drawing for Service Water Pump #A/#B | S | 2022-06-21
210 |  |  | A | 6/21 | P-0001
211 | VP-TEP-R0008- RO-OT-0071 | Pump Sectional Drawing for Service Water Pump #A/#B | S | 2022-06-21
212 |  |  | A | 6/21 | P-0001
213 | VP-TEP-R0008- RO-PI-0071 | Pump P&ID for Service Water Pump #A/#B | S | 2022-06-21
214 |  |  | A | 6/21 | P-0001
215 | VP-TEP-R0008- RO-OT-0072 | Name Plate Drawing for Service Water Pump #A/#B | S | 2022-06-21
216 |  |  | A | 6/21 | P-0001
217 | VP-TEP-R0008- RO-DS-0073 | Motor Data Sheet & Curve for Service Water Pump #A/#B | S | 2022-06-21
218 |  |  | A | 6/21 | P-0002
219 | VP-TEP-R0008- RO-GA-0072 | Motor Outline Drawing & T-Box Drawing for Service Water Pump #A/#B | S | 2022-06-21
220 |  |  | A | 6/21 | P-0002
221 | VP-TEP-R0008- RO-OT-0073 | Mechanical Seal Drawing for Service Water Pump #A/#B | S | 2022-06-21
222 |  |  | A | 6/21 | P-0001
223 | VP-TEP-R0008- RO-OT-0074 | Coupling Drawing for Service Water Pump #A/#B | S | 2022-06-21
224 |  |  | A | 6/21 | P-0001
225 | VP-TEP-R0008- RO-GA-0073 | Pressure Tank Drawing for Service Water Pump #A/#B | S | 2022-06-21
226 |  |  | A | 6/21 | P-0001
227 | VP-TEP-R0008- RO-OT-0075 | Local Control Panel Drawing for Service Water Pump #A/#B | S | 2022-06-21
228 |  |  | A | 6/21 | P-0004
229 | VP-TEP-R0008- RO-LI-0071 | Instrument List & Catalogue for Service Water Pump #A/#B | S | 2022-06-24
230 |  |  | A