## VPI&S_Fluff Transfer
Vendor Print Index & Schedule
No. | Document No. | Document Title | Transmittal No. | Category "A/R/I" (For Approval / Review / Information) | Key VP | P/A | Issued for Approval | [11 empty] | Issue for Final | [7 empty] | Final |  |  |  | Final Data Book |  |  |  | Remark
[7 empty] | Rev. A |  |  |  | Rev. B |  |  |  | Rev. C |  |  |  | Rev. 0 |  |  |  | Rev. 1 |  |  |  | N(for final)+1 |  |  |  | Later
[7 empty] | Out | In | TR# | STS | Out | In | TR# | STS | Out | In | TR# | STS | Out | In | TR# | STS | Out | In | TR# | STS | Out | In | TR# | STS | Out | In | TR# | STS
General Documents
1 | VP-TEP-R0010-PM-LI-0001 | Vendor Print Index Schedule (common) |  | For Approval | O | P | 2022-02-16 | 2022-03-02 | #0001 | 1 | [8 empty] | 2022-04-21 | 2022-05-09 | #0009 | 1
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 | [9 empty] | 2022-04-25 | 2022-07-11 | #0013
2 | VP-TEP-R0010-PM-LI-0002 | Sub Vendor List (common) |  | For Approval | O | P | 2022-02-22
[6 empty] | A | 2022-03-08 |  | #0005
3 | VP-TEP-R0010-PM-LI-0003 | Spare Parts List (common) |  | For Approval |  | P | 2022-02-22 | 2022-05-06 | #0010 | 3 | 2022-07-25
[6 empty] | A | 2022-04-22 | 2022-07-11 | #0010 |  | 2022-08-09 |  | #0032
4 | VP-TEP-R0010-PM-LI-0004 | Utility consumption list (common) |  | For Approval | O | P | 2022-02-22 | 2022-05-06 | #0010 | 2 | 2022-07-25
[6 empty] | A | 2022-04-22 | 2022-07-11 | #0010 |  | 2022-08-09 |  | #0032
5 | VP-TEP-R0010-PM-LI-0005 | Lubricant list (common) |  | For Approval |  | P | 2022-02-22 | 2022-05-06 | #0010 | 1 | 2022-07-25
[6 empty] | A | 2022-04-22 | 2022-07-11 | #0010 |  | 2022-08-09 |  | #0032
6 | VP-TEP-R0010-PM-OT-0001 | MECHANICAL DATA BOOK |  | For Approval |  | P | 2023-02-22
A
7 | VP-TEP-R0010-PM-OT-0002 | 3d modeling pipe (common) |  | For Approval |  | P | 2022-02-16 | 2022-03-02 | #0001 | 1 | 2022-04-21
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001
8 | VP-TEP-R0010-PM-PR-0001 | Packing Procedures (common) |  | For Approval |  | P | 2022-02-16 | 2022-05-06 | #0010 | 2 | 2022-07-25
[6 empty] | A | 2022-04-22 | 2022-07-11 | #0010 |  | 2022-08-09 |  | #0032
9 | VP-TEP-R0010-PM-MA-0001 | Instructions Manual for Erection, Installation, Operation, Maintenance (common) |  | For Approval |  | P | 2022-02-22
A
Rotating Documents
10 | VP-TEP-R0010-RO-PI-0001 | Piping & instrument Diagram (CVP) |  | For Approval | O | P | 2022-02-16 | 2022-03-02 | #0001 | 3 | 2022-04-21 | 2022-06-09 | #0012 | 3 | 2022-08-02
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 |  | 2022-05-26 | 2022-07-19 | #0021 |  | 2022-07-19 |  | #0025
11 | VP-TEP-R0010-RO-PI-0002 | Piping & instrument Diagram (WBVP) |  | For Approval | O | P | 2022-02-16 | 2022-03-02 | #0001 | 3 | 2022-04-21 | 2022-06-09 | #0012 | 3 | 2022-08-02
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 |  | 2022-05-26 | 2022-07-19 | #0021 |  | 2022-07-19 |  | #0025
12 | VP-TEP-R0010-RO-DS-0001 | Vacuum Pump Data Sheet & Performance Curves & Gear Reducer Data sheet & drawing (CVP) |  | For Approval | O | P | 2022-02-16 | 2022-03-02 | #0001 | 1 | 2022-04-21
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001
13 | VP-TEP-R0010-RO-DS-0002 | Vacuum Pump Data Sheet & Performance Curves (WBVP) |  | For Approval | O | P | 2022-02-16 | 2022-03-02 | #0001 | 3 | 2022-04-21
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001
14 | VP-TEP-R0010-RO-DS-0003 | Rec. Pump data sheet & drawing (CVP) |  | For Approval |  | P | 2022-02-16 | 2022-03-02 | #0001 | 1 | 2022-04-21
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001
15 | VP-TEP-R0010-RO-DD-0001 | Pump sectional drawing Coupling drawing (CVP) |  | For Approval |  | P | 2022-02-22 | 2022-04-08 | #0006 | 3 | 2022-06-10
[6 empty] | A | 2022-03-25 | 2022-05-27 | #0007
16 | VP-TEP-R0010-RO-DD-0002 | Pump sectional drawing Coupling drawing (WBVP) |  | For Approval |  | P | 2022-02-22 | 2022-04-08 | #0006 | 3 | 2022-06-10
[6 empty] | A | 2022-03-25 | 2022-05-27 | #0007
17 | VP-TEP-R0010-RO-CA-0001 | Calculation sheet for pump (CVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-30 | #0008 | 2 | 2022-07-14
[6 empty] | A | 2022-05-16 | 2022-06-30 | #0020 |  | 2022-08-08 |  | #0032
18 | VP-TEP-R0010-RO-CA-0002 | Calculation sheet for pump (WBVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-30 | #0008 | 2 | 2022-07-14
[6 empty] | A | 2022-05-16 | 2022-06-30 | #0020 |  | 2022-08-08 |  | #0032
Stationary Documents
19 | VP-TEP-R0010-ST-DS-0001 | Heat exchanger Data sheet & drawing (CVP) |  | For Approval |  | P | 2022-02-16 | 2022-03-02 | #0001 | 1 | [8 empty] | 2022-04-21
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 | [9 empty] | 2022-04-20 |  | #0008
20 | VP-TEP-R0010-ST-DS-0002 | Heat exchanger Data sheet & drawing (WBVP) |  | For Approval |  | P | 2022-02-16 | 2022-03-02 | #0001 | 1 | [8 empty] | 2022-04-21
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 | [9 empty] | 2022-04-20 |  | #0008
21 | VP-TEP-R0010-ST-DD-0001 | Separator drawing (CVP) |  | For Approval |  | P | 2022-02-22 | 2022-03-14 | #0002 | 3 | 2022-04-21
[6 empty] | A | 2022-02-28 | 2022-04-07 | #0004 |  | 2022-04-20 |  | #0009
22 | VP-TEP-R0010-ST-DD-0002 | Separator &Control Tank & Drain Tank Drawing(WBVP) |  | For Approval |  | P | 2022-02-22 | 2022-03-14 | #0002 | 3 | 2022-04-21
[6 empty] | A | 2022-02-28 | 2022-04-07 | #0004 |  | 2022-04-20 |  | #0009
Civil Documents
23 | VP-TEP-R0010-CV-FA-0001 | Foundation Drawing showing Foundation Information, Anchor Bolts & Loading (CVP) |  | For Approval | O | P | 2022-02-16 | 2022-03-02 | #0001 | 3 | 2022-04-21
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 |  | 2022-05-26 |  | #0023
24 | VP-TEP-R0010-CV-FA-0002 | Foundation Drawing showing Foundation Information, Anchor Bolts & Loading (WBVP) |  | For Approval | O | P | 2022-02-16 | 2022-03-02 | #0001 | 1 | 2022-04-21
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 |  | 2022-05-26 |  | #0023
Piping Documents
25 | VP-TEP-R0010-PI-LI-0001 | Valve List including control valve, PSV and etc. (common) |  | For Approval |  | P | 2022-02-22
[6 empty] | A | 2022-04-22 |  | #0011
26 | VP-TEP-R0010-PI-GA-0001 | General Arrangement Drawing (CVP) |  | For Approval | O | P | 2022-02-16 | 2022-03-02 | #0001 | 3 | 2022-04-21
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 |  | 2022-05-26 |  | #0022
27 | VP-TEP-R0010-PI-GA-0002 | General Arrangement Drawing (WBVP) |  | For Approval | O | P | 2022-02-16 | 2022-03-02 | #0001 | 3 | 2022-04-21
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 |  | 2022-05-26 |  | #0022
28 | VP-TEP-R0010-PI-PR-0001 | Paint Procedures (common) |  | For Approval |  | P | 2022-02-22
[6 empty] | A | 2022-04-22 |  | #0011
Instrument Documents
29 | VP-TEP-R0010-IN-LI-0001 | Input Output point list (including DCS IO list)(CVP) |  | For Approval |  | P | 2022-02-22
[6 empty] | A | 2022-05-04 |  | #0016
30 | VP-TEP-R0010-IN-LI-0002 | Input Output point list (including DCS IO list) (WBVP) |  | For Approval |  | P | 2022-02-22
[6 empty] | A | 2022-05-04 |  | #0016
31 | VP-TEP-R0010-IN-LI-0003 | Alarm set point list (CVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-23 | #0007 | 3 | 2022-07-15
[6 empty] | A | 2022-05-09 | 2022-07-01 | #0018 |  | 2022-08-08 |  | #0031
32 | VP-TEP-R0010-IN-LI-0004 | Alarm set point list (WBVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-23 | #0007 | 2 | 2022-07-15
[6 empty] | A | 2022-05-09 | 2022-07-01 | #0018 |  | 2022-08-08 |  | #0031
33 | VP-TEP-R0010-IN-LI-0005 | Instrument List (CVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-06 | #0012 | 3 | 2022-08-02
[6 empty] | A | 2022-04-22 | 2022-07-19 | #0021 |  | 2022-08-11 |  | #0034
34 | VP-TEP-R0010-IN-LI-0006 | Instrument List (WBVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-06 | #0012 | 3 | 2022-08-02
[6 empty] | A | 2022-04-22 | 2022-07-19 | #0021 |  | 2022-08-11 |  | #0034
35 | VP-TEP-R0010-IN-LD-0001 | Control Logic Diagrams, Functional Loop Diagrams (CVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-17 | #0015 | 3 | 2022-08-05
[6 empty] | A | 2022-05-03 | 2022-07-22 | #0014
36 | VP-TEP-R0010-IN-LD-0002 | Control Logic Diagrams, Functional Loop Diagrams(WBVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-17 | #0015 | 3 | 2022-08-05
[6 empty] | A | 2022-05-03 | 2022-07-22 | #0014
37 | VP-TEP-R0010-IN-IF-0001 | Signal Block Diagram, Control System Interconnection Diagrams (CVP) |  | For Approval |  | P | 2022-02-22
[6 empty] | A | 2022-05-03 |  | #0014
38 | VP-TEP-R0010-IN-IF-0002 | Signal Block Diagram, Control System Interconnection Diagrams (WBVP) |  | For Approval |  | P | 2022-02-22
[6 empty] | A | 2022-05-03 |  | #0014
39 | VP-TEP-R0010-IN-DS-0001 | Instrument Data sheets & catalog (CVP) |  | For Approval |  | P | 2022-02-22
[6 empty] | A | 2022-05-04 |  | #0016
40 | VP-TEP-R0010-IN-DS-0002 | Instrument Data sheets & catalog (WBVP) |  | For Approval |  | P | 2022-02-22
[6 empty] | A | 2022-05-04 |  | #0016
41 | VP-TEP-R0010-IN-DS-0003 | On-off Valve Data Sheet(CVP) |  | For Approval |  | P | 2022-02-22
[6 empty] | A | 2022-05-04 |  | #0016
42 | VP-TEP-R0010-IN-DS-0004 | On-off Valve Data Sheet(WBVP) |  | For Approval |  | P | 2022-02-22
[6 empty] | A | 2022-05-04 |  | #0016
43 | VP-TEP-R0010-IN-ID-0001 | Panel outline drawing (CVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-17 | #0007 | 3 | 2022-07-15
[6 empty] | A | 2022-05-03 | 2022-07-01 | #0018
44 | VP-TEP-R0010-IN-ID-0002 | Panel outline drawing (WBVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-17 | #0007 | 2 | 2022-07-15
[6 empty] | A | 2022-05-03 | 2022-07-01 | #0018
45 | VP-TEP-R0010-IN-ID-0003 | Instrument hook-up Drawings (CVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-23 | #0007 | 3 | 2022-07-15
[6 empty] | A | 2022-05-09 | 2022-07-01 | #0018 |  | 2022-08-08 |  | #0030
46 | VP-TEP-R0010-IN-ID-0004 | Instrument hook-up Drawings (WBVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-23 | #0007 | 3 | 2022-07-15
[6 empty] | A | 2022-05-09 | 2022-07-01 | #0018 |  | 2022-08-08 |  | #0030
47 | VP-TEP-R0010-IN-CF-0001 | Control system configuration diagram(CVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-17 | #0015 | 2 | 2022-08-05
[6 empty] | A | 2022-05-03 | 2022-07-22 | #0014
48 | VP-TEP-R0010-IN-CF-0002 | Control system configuration diagram(WBVP) |  | For Approval |  | P | 2022-02-22 | 2022-05-17 | #0015 | 2 | 2022-08-05
[6 empty] | A | 2022-05-03 | 2022-07-22 | #0014
49 | VP-TEP-R0010-IN-SP-0001 | System Functions & Control Description/Protectional Requirements |  | For Approval |  | P | 2022-02-22
A
Electrical Documents
50 | VP-TEP-R0010-EL-DS-0001 | Motor Data Sheet and curve (CVP) |  | For Approval |  | P | 2022-02-15 | 2022-03-02 | #0001 | 2 | [8 empty] | 2022-04-21 |  | #0017
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 | [9 empty] | 2022-05-09
51 | VP-TEP-R0010-EL-DS-0002 | Motor Data Sheet and curve (WBVP) |  | For Approval |  | P | 2022-02-15 | 2022-03-02 | #0001 | 2 | [8 empty] | 2022-04-21 |  | #0017
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 | [9 empty] | 2022-05-09
52 | VP-TEP-R0010-EL-DS-0003 | motor data sheet and curve for Rec. Pump (CVP) |  | For Approval |  | P | 2022-02-15 | 2022-03-02 | #0001 | 2 | [8 empty] | 2022-04-21 |  | #0017
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 | [9 empty] | 2022-05-09
53 | VP-TEP-R0010-EL-CS-0001 | Cable Schedule(Common) |  | For Approval |  | P | 2022-02-22 | 2022-05-18
[6 empty] | A | 2022-05-04 |  | #0015
54 | VP-TEP-R0010-EL-LI-0001 | Electrical Load list (common) |  | For Approval | O | P | 2022-02-15 | 2022-03-02 | #0001 | 2 | [8 empty] | 2022-04-21 |  | #0019
[6 empty] | A | 2022-02-16 | 2022-04-07 | #0001 | [9 empty] | 2022-05-11
Quality Control Documents
55 | VP-TEP-R0010-QA-MA-0001 | Q/A Program Manual (common) |  | For Approval |  | P | 2022-02-22 | 2022-03-09 | #0004 | 1 | [8 empty] | 2022-03-25
[6 empty] | A | 2022-02-23 | 2022-03-11 | #0002 | [9 empty] | 2022-04-26 |  | #0014
56 | VP-TEP-R0010-QA-PL-0001 | Shop Test & Inspection Plan (common) |  | For Approval |  | P | 2022-02-22 | 2022-03-09 | #0004 | 3 | 2022-03-25
[6 empty] | A | 2022-02-23 | 2022-03-11 | #0002 |  | 2022-08-04 |  | #0027
57 | VP-TEP-R0010-QA-PL-0002 | Field Test & Inspection Plan (common) |  | For Approval |  | P | 2022-02-22 | 2022-03-09 | #0004 | 3 | 2022-03-25
[6 empty] | A | 2022-02-23 | 2022-03-11 | #0002 |  | 2022-08-04 |  | #0027
58 | VP-TEP-R0010-QA-PL-0003 | Motor Test & Inspection Plan (common) |  | For Approval |  | P | 2022-02-22 | 2022-03-09 | #0004 | 3 | 2022-03-25 |  | #0024
[6 empty] | A | 2022-02-23 | 2022-03-11 | #0002 |  | 2022-06-20
59 | VP-TEP-R0010-QA-PR-0001 | Motor Test & Inspection Procedures (common) |  | For Approval |  | P | 2022-02-22 | 2022-03-09 | #0004 | 3 | 2022-03-25 |  | #0024
[6 empty] | A | 2022-02-23 | 2022-03-11 | #0002 |  | 2022-06-20
60 | VP-TEP-R0010-QA-PR-0002 | Shop Test & Inspection Procedures (common) |  | For Approval |  | P | 2022-02-22 | 2022-03-09 | #0004 | 3 | 2022-03-25
[6 empty] | A | 2022-02-23 | 2022-03-11 | #0002
61 | VP-TEP-R0010-QA-PR-0003 | WPS/PQR & Welding MapWelder List & Welder Qualification Record(common) |  | For Approval |  | P | 2022-02-22 | 2022-03-08 | #0001 | 2 | 2022-04-06 |  | #0026
[6 empty] | A | 2022-02-25 | 2022-03-23 | #0003 |  | 2022-08-03
62 | VP-TEP-R0010-QA-PR-0004 | NDE Procedures (common) |  | For Approval |  | P | 2022-02-22 | 2022-03-22 | #0003 | 3 | 2022-04-27
[6 empty] | A | 2022-03-08 | 2022-04-13 | #0005
63 | VP-TEP-R0010-QA-PR-0005 | PMI Procedures (common) |  | For Approval |  | P | 2022-02-22 | 2022-03-22 | #0003 | 3 | 2022-04-27
[6 empty] | A | 2022-03-08 | 2022-04-13 | #0005 |  | 2022-08-08 |  | #0028
64 | VP-TEP-R0010-QA-RE-0001 | Test & Inspection Reports (common) |  | For Approval |  | P | 2022-10-30
A
Project Name |  | TONG YEONG ECO POWER LNG POWER PLANT PROJECT |  |  |  | P/O NO. |  |  | PO-TEP-R-0010-P | [9 empty] | Doc. No. | VP-TEP-R0010 -PM-LI-0001 | [5 empty] | Rev. | [5 empty] | A
Vendor Name |  | GARDNERDENVER KOREA
Note
1. Abbreviation - STS: Status, A: Approved, C: Approved with Comments, R: Rjected, RS: Resubmit, FI: For Information
2. Vendor shall submit the revised document within 14 calendar days after receive purchaser's response.
Formulas:
In = [Issued for Approval, row below]+14
In = [Issue for Final, row below]+14
Issue for Final = [In, row below]+14
Rev. B = [In, row below]+14
Rev. C = [In, row below]+14