## Table 3
POWERKING PUMP Corp.
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: CLEAN & DIRTY OIL PUMP | [6 empty] | ITEM NO. : 14MV11PP001, 14MV12PP001, 14MV13PP001, 14V14PP001, 14MV15PP001
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0012-RO-LI-0001 | Vendor Print Index & Schedule | A4 | 4 | S | FOR APPROVAL IN: △ 17-May-22; FOR APPROVAL IN: △ 17-Aug-22
[5 empty] | A | FOR APPROVAL IN: 23-May; FOR APPROVAL OUT: 2-Aug; FOR APPROVAL TR#: 1; FOR APPROVAL RST: 1; FOR APPROVAL IN: 17-Aug; FOR APPROVAL TR#: 11
2 | VP-TEP-R0012-RO-LI-0002 | Sub-Vendor List | A4 | 3 | S | FOR APPROVAL IN: △ 24-May-22; FOR APPROVAL IN: △ 17-Aug-22
[5 empty] | A | FOR APPROVAL IN: 23-May; FOR APPROVAL OUT: 2-Aug; FOR APPROVAL TR#: 1; FOR APPROVAL RST: 1; FOR APPROVAL IN: 17-Aug; FOR APPROVAL TR#: 11
3 | VP-TEP-R0012-RO-LI-0003 | Electrical Load List | A4 |  | S | FOR APPROVAL IN: △ 24-May-2219-Jul-22
[5 empty] | A | FOR APPROVAL IN: 19-Jul; FOR APPROVAL OUT: 4-Aug; FOR APPROVAL TR#: 8; FOR APPROVAL RST: 3
4 | VP-TEP-R0012-RO-PR-0004 | Shop Inspection and Test Plan | A4 |  | S | FOR APPROVAL IN: △ 24-May-22; FOR APPROVAL IN: △ 13-Jul-22
[5 empty] | A | FOR APPROVAL IN: 25-May; FOR APPROVAL OUT: 01-Jul; FOR APPROVAL TR#: 3; FOR APPROVAL RST: 3; FOR APPROVAL IN: 13-Jul; FOR APPROVAL TR#: 6
5 | VP-TEP-R0012-RO-PR-0005 | Shop Inspection and Test Procedure | A4 |  | S | FOR APPROVAL IN: △ 24-May-22; FOR APPROVAL IN: △ 13-Jul-22
[5 empty] | A | FOR APPROVAL IN: 25-May; FOR APPROVAL OUT: 01-Jul; FOR APPROVAL TR#: 3; FOR APPROVAL RST: 3; FOR APPROVAL IN: 13-Jul; FOR APPROVAL TR#: 6
6 | VP-TEP-R0012-RO-PR-0006 | Motor Inspection and Test Plan | A4 |  | S | FOR APPROVAL IN: △ 31-May-2222-Jul-22
[5 empty] | A | FOR APPROVAL IN: 1-Aug; FOR APPROVAL TR#: 9
7 | VP-TEP-R0012-RO-PR-0007 | Motor Inspection and Test Procedure | A4 |  | S | FOR APPROVAL IN: △ 31-May-2222-Jul-22
[5 empty] | A | FOR APPROVAL IN: 1-Aug; FOR APPROVAL TR#: 9
8 | VP-TEP-R0012-RO-PR-0008 | N.D.E procedure | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 18-Jul-22
[5 empty] | A | FOR APPROVAL IN: 25-May; FOR APPROVAL OUT: 01-Jul; FOR APPROVAL TR#: 3; FOR APPROVAL RST: 3; FOR APPROVAL IN: 18-Jul; FOR APPROVAL TR#: 7
9 | VP-TEP-R0012-RO-PR-0009 | WPS & PQR with Welding Map | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 18-Jul-22
[5 empty] | A | FOR APPROVAL IN: 25-May; FOR APPROVAL OUT: 01-Jul; FOR APPROVAL TR#: 3; FOR APPROVAL RST: 3; FOR APPROVAL IN: 18-Jul; FOR APPROVAL TR#: 7
10 | VP-TEP-R0012-RO-RE-0010 | Welder Qualification Record | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 18-Jul-22
[5 empty] | A | FOR APPROVAL IN: 25-May; FOR APPROVAL OUT: 01-Jul; FOR APPROVAL TR#: 3; FOR APPROVAL RST: 3; FOR APPROVAL IN: 18-Jul; FOR APPROVAL TR#: 7
11 | VP-TEP-R0012-RO-PR-0011 | Rust prevention and paint specification | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 18-Jul-22
[5 empty] | A | FOR APPROVAL IN: 25-May; FOR APPROVAL OUT: 01-Jul; FOR APPROVAL TR#: 3; FOR APPROVAL RST: 3; FOR APPROVAL IN: 18-Jul; FOR APPROVAL TR#: 7
12 | VP-TEP-R0012-RO-PR-0012 | Packing Procedure | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 17-Aug-22
[5 empty] | A | FOR APPROVAL IN: 25-May; FOR APPROVAL OUT: 01-Jul; FOR APPROVAL TR#: 3; FOR APPROVAL RST: 1; FOR APPROVAL IN: 17-Aug; FOR APPROVAL TR#: 11
13 | VP-TEP-R0012-RO-PR-0013 | Handling, and storage instructions | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 17-Aug-22
[5 empty] | A | FOR APPROVAL IN: 25-May; FOR APPROVAL OUT: 01-Jul; FOR APPROVAL TR#: 3; FOR APPROVAL RST: 1; FOR APPROVAL IN: 17-Aug; FOR APPROVAL TR#: 11
14 | VP-TEP-R0012-RO-PL-0014 | Quality Manual | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 17-Aug-22
[5 empty] | A | FOR APPROVAL IN: 25-May; FOR APPROVAL OUT: 01-Jul; FOR APPROVAL TR#: 3; FOR APPROVAL RST: 1; FOR APPROVAL IN: 17-Aug; FOR APPROVAL TR#: 11
15 | VP-TEP-R0012-RO-RE-0015 | Test report | A4 |  | S | FOR APPROVAL IN: △ 28-Oct-22
A
Note : |  | S/A : Schedule/Actual | RST : Result of V/P Review |  |  | FOR APPROVAL IN: N : Approved As Noted; FOR APPROVAL IN: RE : Reviewed with no comment; FOR FINAL IN: FNL : Final
|  | IN/OUT : Incoming/Outgoing | A: Approved |  |  | FOR APPROVAL IN: R : Rejected; FOR APPROVAL IN: RFC : Return For Correction; FOR FINAL IN: TDB : Technical Data Book
PROJECT NAME |  | TEP Project |  |  | PROJECT NO | FOR APPROVAL IN: ISSUED; FOR APPROVAL RST: 0; FINAL TDB: 2
P/O NO. |  | PO-TEP-R-0012-P |  |  | DATE | FOR APPROVAL IN: 2022-05-23; FOR APPROVAL RST: 1; FINAL TDB: 3
16 | VP-TEP-R0012-RO-MA-0016 | Installation, operation & maintenance manual | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 17-Aug-22
[5 empty] | A | FOR APPROVAL IN: 31-May; FOR APPROVAL OUT: 04-Aug; FOR APPROVAL TR#: 4; FOR APPROVAL RST: 1; FOR APPROVAL IN: 17-Aug; FOR APPROVAL TR#: 11
17 | VP-TEP-R0012-RO-LI-0017 | Spare parts list for erection & commissioning | A4 |  | S | FOR APPROVAL IN: △ 08-Jun-22
[5 empty] | A | FOR APPROVAL IN: 13-Jun; FOR APPROVAL TR#: 5
18 | VP-TEP-R0012-RO-LI-0018 | Spare parts list for 2 (Two) years operation | A4 |  | S | FOR APPROVAL IN: △ 08-Jun-22
[5 empty] | A | FOR APPROVAL IN: 13-Jun; FOR APPROVAL TR#: 5
19 | VP-TEP-R0012-RO-LI-0019 | Lubricant list | A4 |  | S | FOR APPROVAL IN: △ 31-May-22
[5 empty] | A | FOR APPROVAL IN: 19-Jul; FOR APPROVAL OUT: 04-Aug; FOR APPROVAL TR#: 8; FOR APPROVAL RST: 2
20 | VP-TEP-R0012-RO-MA-0020 | Catalog | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 17-Aug-22
[5 empty] | A | FOR APPROVAL IN: 31-May; FOR APPROVAL OUT: 04-Aug; FOR APPROVAL TR#: 4; FOR APPROVAL RST: 1; FOR APPROVAL IN: 17-Aug; FOR APPROVAL TR#: 11
21 | VP-TEP-R0012-RO-DS-0021 | Pump datasheet and curve | A4 |  | S | FOR APPROVAL IN: △ 24-May-22; FOR APPROVAL IN: △ 5-Aug-22
[5 empty] | A | FOR APPROVAL IN: 24-May; FOR APPROVAL OUT: 1-Aug; FOR APPROVAL TR#: 2; FOR APPROVAL RST: 2; FOR APPROVAL IN: 5-Aug; FOR APPROVAL TR#: 10
22 | VP-TEP-R0012-RO-GA-0022 | G.A drawing with foundation plan | A3 |  | S | FOR APPROVAL IN: △ 24-May-22; FOR APPROVAL IN: △ 5-Aug-22
[5 empty] | A | FOR APPROVAL IN: 24-May; FOR APPROVAL OUT: 1-Aug; FOR APPROVAL TR#: 2; FOR APPROVAL RST: 2; FOR APPROVAL IN: 5-Aug; FOR APPROVAL TR#: 10
23 | VP-TEP-R0012-RO-OT-0023 | Cross sectional drawing with part list | A4 |  | S | FOR APPROVAL IN: △ 08-Jun-2229-Jul-22
[5 empty] | A | FOR APPROVAL IN: 1-Aug; FOR APPROVAL TR#: 9
24 | VP-TEP-R0012-RO-SP-0024 | Motor data sheet & curve | A4 |  | S | FOR APPROVAL IN: △ 31-May-2219-Jul-22
[5 empty] | A | FOR APPROVAL IN: 19-Jul; FOR APPROVAL OUT: 04-Aug; FOR APPROVAL TR#: 8; FOR APPROVAL RST: 1
25 | VP-TEP-R0012-RO-GA-0025 | Motor drawings including termical box & terminal details | A4 |  | S | FOR APPROVAL IN: △ 31-May-2219-Jul-22
[5 empty] | A | FOR APPROVAL IN: 19-Jul; FOR APPROVAL OUT: 04-Aug; FOR APPROVAL TR#: 8; FOR APPROVAL RST: 2
26 | VP-TEP-R0012-RO-DS-0026 | External PSV data sheet and drawing | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 17-Aug-22
[5 empty] | A | FOR APPROVAL IN: 31-May; FOR APPROVAL OUT: 04-Aug; FOR APPROVAL TR#: 4; FOR APPROVAL RST: 3; FOR APPROVAL IN: 17-Aug; FOR APPROVAL TR#: 11
27 | VP-TEP-R0012-RO-GA-0027 | Mechanical seal drawing | A4 |  | S | FOR APPROVAL IN: △ 08-Jun-2219-Jul-22; FOR APPROVAL IN: △ 17-Aug-22
[5 empty] | A | FOR APPROVAL IN: 19-Jul; FOR APPROVAL OUT: 04-Aug; FOR APPROVAL TR#: 8; FOR APPROVAL RST: 1; FOR APPROVAL IN: 17-Aug; FOR APPROVAL TR#: 11
28 | VP-TEP-R0012-RO-GA-0028 | Coupling drawing | A4 |  | S | FOR APPROVAL IN: △ 31-May-22; FOR APPROVAL IN: △ 17-Aug-22
[5 empty] | A | FOR APPROVAL IN: 31-May; FOR APPROVAL OUT: 04-Aug; FOR APPROVAL TR#: 4; FOR APPROVAL RST: 1; FOR APPROVAL IN: 17-Aug; FOR APPROVAL TR#: 11
29 | VP-TEP-R0012-RO-RE-0029 | Seismic Analysis Report | A4 |  | S | FOR APPROVAL IN: △ 25-Jul-22
[5 empty] | A | FOR APPROVAL IN: 19-Jul; FOR APPROVAL OUT: 04-Aug; FOR APPROVAL TR#: 8; FOR APPROVAL RST: 2
30 |  |  |  |  | S | bar: FOR APPROVAL IN
A
Note : |  | S/A : Schedule/Actual | RST : Result of V/P Review |  |  | FOR APPROVAL IN: N : Approved As Noted; FOR APPROVAL IN: RE : Reviewed with no comment; FOR FINAL IN: FNL : Final
|  | IN/OUT : Incoming/Outgoing | A: Approved |  |  | FOR APPROVAL IN: R : Rejected; FOR APPROVAL IN: RFC : Return For Correction; FOR FINAL IN: TDB : Technical Data Book
PROJECT NAME |  | TEP Project |  |  | PROJECT NO | FOR APPROVAL IN: ISSUED; FOR APPROVAL RST: 0; FINAL TDB: 2
P/O NO. |  | PO-TEP-R-0012-P |  |  | DATE | FOR APPROVAL IN: 2022-05-23; FOR APPROVAL RST: 1; FINAL TDB: 3