## Table 5
NAME OF EQUIPMENT: Fire Water Pump
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0013-PM-LI-0001 | VENDOR PRINT INDEX & SCHEDULE |  |  | S | A | 2022-05-26
A
2 | VP-TEP-R0013-PM-LI-0002 | EQUIPMENT LIST |  |  | S | A | 2022-05-27
A
3 | VP-TEP-R0013-FF-DS-0001 | PUMP DATA SHEET & CURVE & CALCULATION SHEET |  |  | S | A | 2022-05-27
A
4 | VP-TEP-R0013-FF-GA-0001 | PUMP OUTLINE DRAWING |  |  | S | A | 2022-05-27
A
5 | VP-TEP-R0013-FF-DD-0001 | PUMP SECTIONAL DRAWING |  |  | S | A | 2022-05-27
A
6 | VP-TEP-R0013-FF-OT-0001 | PUMP NAME PLATE DRAWING |  |  | S | A | 2022-06-10
A
7 | VP-TEP-R0013-FF-OT-0002 | COUPLING DRAWING |  |  | S | A | 2022-06-10
A
8 | VP-TEP-R0013-EL-SP-0001 | MOTOR & ENGINE DATA SHEET AND DRAWING |  |  | S | A | 2022-05-27
A
9 | VP-TEP-R0013-EL-LI-0001 | ELECTRICAL LOAD LIST |  |  | S | A | 2022-06-10
A
10 | VP-TEP-R0013-EL-SP-0002 | CONTROL PANEL DRAWING & SPECIFICATION |  |  | S | A | 2022-06-10
A
11 | VP-TEP-R0013-IN-SP-0001 | INSTRUMENT LIST & DATA SHEET & CATALOG |  |  | S | A | 2022-06-10
A
12 | VP-TEP-R0013-PM-LI-0003 | SPARE PART LIST |  |  | S | A | 2022-06-10
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | - | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R 0013-P |  |  | DATE |  |  |  |  | 2022-05-26 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
13 | VP-TEP-R0013-PM-LI-0004 | LUBRICANT LIST |  |  | S | A | 2022-06-10
A
14 | VP-TEP-R0013-PM-LI-0005 | SUB VENDOR LIST |  |  | S | A | 2022-06-10
A
15 | VP-TEP-R0013-PM-PR-0001 | PAINTING PROCEDURE |  |  | S | A | 2022-06-10
A
16 | VP-TEP-R0013-FF-OT-0003 | VIBRATION CONTROL & SEISMIC CALCULATION |  |  | S | A | 2022-06-10
A
17 | VP-TEP-R0013-FF-OT-0004 | PRESSURE SWITCH & PRV & FLOW METER SPECIFICATION |  |  | S | A | 2022-06-10
A
18 | VP-TEP-R0013-QA-PR-0001 | WPS & PQR WITH WELD MAP |  |  | S | A | 2022-06-10
A
19 | VP-TEP-R0013-PM-PR-0002 | PACKING PROCEDURE |  |  | S | A | 2022-06-10
A
20 | VP-TEP-R0013-QA-PL-0001 | INSPECTION & TEST PLAN FOR PUMP |  |  | S | A | 2022-06-10
A
21 | VP-TEP-R0013-QA-PR-0002 | INSPECTION & TEST PROCEDURE FOR PUMP |  |  | S | A | 2022-06-10
A
22 | VP-TEP-R0013-QA-PL-0002 | INSPECTION & TEST PLAN FOR MOTOR |  |  | S | A | 2022-06-10
A
23 | VP-TEP-R0013-QA-PR-0003 | INSPECTION & TEST PROCEDURE FOR MOTOR |  |  | S | A | 2022-06-10
A
24 | VP-TEP-R0013-QA-PR-0004 | INSPECTION & TEST PLAN AND PROCEDURE FOR PANEL |  |  | S | A | 2022-06-10
A
Note |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO |  |  |  |  | - | [11 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R 0013-P |  |  | DATE |  |  |  |  | 2022-05-26 | [14 empty] | 1 | [5 empty] | 3
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
25 | VP-TEP-R0013-QA-PR-0005 | NDE PROCEDURE WITH NDE MAP |  |  | S | A | 2022-06-10
A
26 | VP-TEP-R0013-QA-PR-0006 | PMI PROCEDURE |  |  | S | A | 2022-06-10
A
27 | VP-TEP-R0013-PM-MA-0001 | INSTALLATION, OPERATION & MAINTENANCE MANUAL |  |  | S | A | 2022-06-10
A
28 | VP-TEP-R0013-PM-RE-0001 | INSPECTION AND TEST CERTIFICATES/REPORTS |  |  | S | A | 2022-12-30
A