## Table 3
SONGSAN SPECIAL ELEVATORS
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT: ELEVATOR | [5 empty] | ITEM NO. :
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-R0014-RO-LI-0001 | Vendor Print Index & Schedule | A4 |  | S | 2022-04-25
[5 empty] | A | 25-Apr |  | 1
2 | VP-TEP-R0014-RO-LI-0002 | Sub-Vendor list |  |  | S | 2022-05-18
[5 empty] | A | 18-May |  | 2
3 | VP-TEP-R0014-RO-LI-0003 | 2 years Spare Parts List |  |  | S | 2022-05-18
[5 empty] | A | 18-May |  | 2
4 | VP-TEP-R0014-RO-LI-0004 | Lubricants list |  |  | S | 2022-04-25
[5 empty] | A | 25-Apr |  | 1
5 | VP-TEP-R0014-RO-LI-0005 | Electrical load list |  |  | S | 2022-05-18
[5 empty] | A | 18-May |  | 2
6 | VP-TEP-R0014-RO-DS-0001 | Equipment Data Sheet |  |  | S | 2022-05-23
A
7 | VP-TEP-R0014-RO-DS-0002 | Motor Data Sheet |  |  | S | 2022-06-25
[5 empty] | A | 08-Jun |  | 3
8 | VP-TEP-R0014-RO-OT-0001 | Layout Drawing for HRSG BLDG1 |  |  | S | 2022-05-20
[5 empty] | A | 08-Jun |  | 3
9 | VP-TEP-R0014-RO-OT-0002 | Layout Drawing for HRSG BLDG2 |  |  | S | 2022-05-20
[5 empty] | A | 08-Jun |  | 3
10 | VP-TEP-R0014-RO-OT-0003 | Layout Drawing for ADMIN BLDG |  |  | S | 2022-05-20
[5 empty] | A | 08-Jun |  | 3
11 | VP-TEP-R0014-RO-FD-0001 | Wiring Diagram for HRSG BLDG1 |  |  | S | 2022-04-25
[5 empty] | A | 25-Apr |  | 1
12 | VP-TEP-R0014-RO-FD-0002 | Wiring Diagram for HRSG BLDG2 |  |  | S | 2022-04-25
[5 empty] | A | 25-Apr |  | 1
13 | VP-TEP-R0014-RO-FD-0003 | Wiring Diagram for ADMIN BLDG |  |  | S | 2022-04-25
[5 empty] | A | 25-Apr |  | 1
14 | VP-TEP-R0014RO-PR-0001 | Painting Specification and Procedure |  |  | S | 2022-05-18
[5 empty] | A | 18-May |  | 2
15 | VP-TEP-R0014RO-PR-0001 | Packing Procedure |  |  | S | 2022-05-18
[5 empty] | A | 18-May |  | 2
16 | VP-TEP-R0014-QA-PL-0001 | Inspection and Test Plan |  |  | S | 2022-05-18
[5 empty] | A | 18-May |  | 2
17 | VP-TEP-R0014-QA-PR-0001 | Inspection and Test Procedure |  |  | S | 2022-05-18
[5 empty] | A | 18-May |  | 2
18 | VP-TEP-R0014-QA-PR-0002 | SAT Procedure |  |  | S | 2022-05-18
[5 empty] | A | 18-May |  | 2
19 | VP-TEP-R0014-QA-OT-0001 | Inspection and Test Report/Record |  |  | S | 2022-11-01
A
20 | VP-TEP-R0014-PM-MA-0001 | Installation, Operation & Maintenance Manual |  |  | S | 2022-05-18
[5 empty] | A | 18-May |  | 2
21 | VP-TEP-R0014-PM-DB-0001 | Manufacturing Data Book (Technical Data Book) |  |  | S | 2023-04-15
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO | [16 empty] | ISSUED |  |  | 0 | [5 empty] | 2
P/O NO. |  | PO-TEP-R-0014-P |  |  | DATE | [19 empty] | 1 | [5 empty] | 3