## Table 2
NAME OF EQUIPMENT: CTCS&DEBRIS FILTER, AUX. DEBRIS FILTER
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [15 empty] | FOR CONSTRUCTION | [7 empty] | FINAL | [5 empty] | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-S0002-ST-LI-0001 | Vendor Print Index & Schedule | A4 |  | S | △A | 2021-09-28 |  |  | △B | 2021-11-18 |  |  | △C | 2022-01-11 |  |  | △D | 2022-02-03 |  |  | △0 | 2022-03-24 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 28-Sep | 4-Nov | #0001 | 3 | 11-Jan | 15-Dec | #0012 | 3 | 11-Jan | 16-Feb | #0012 | 3 | 3-Feb | 17-Mar | #0015 | 1 | 24-Mar | 23-Jun | #0020 | 1
2 | VP-TEP-S0002-PI-GA-0001 | Outline Drawing of Ball Strainer for Condenser Tube Cleaning System | A3 |  | S | △A | 2021-10-11 |  |  | △B | 2022-01-11 | [10 empty] | △0 | 2022-03-24 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 14-Oct | 7-Dec | #0002 | 3 | 11-Jan | 4-Mar | #0013 | 2 | [8 empty] | 24-Mar | 23-Jun | #0020 | 2
3 | VP-TEP-S0002-PI-GA-0002 | Outline Drawing of Injection Nozzle for Condenser Tube Cleaning System | A3 |  | S | △A | 2021-10-11 |  |  | △B | 2022-01-11 | [10 empty] | △0 | 2022-03-24 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 14-Oct | 7-Dec | #0002 | 2 | 11-Jan | 4-Mar | #0013 | 1 | [8 empty] | 24-Mar | 23-Jun | #0020 | 1
4 | VP-TEP-S0002-PI-GA-0003 | Outline Drawing of Distributor for Condenser Tube Cleaning System | A3 |  | S | △A | 2021-10-11 |  |  | △B | 2022-01-11 | [10 empty] | △0 | 2022-03-24 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 14-Oct | 7-Dec | #0002 | 2 | 11-Jan | 4-Mar | #0013 | 2 | [8 empty] | 24-Mar | 23-Jun | #0020 | 1
5 | VP-TEP-S0002-PI-GA-0004 | Outline Drawing of Ball Recirculation Unit for Condenser Tube Cleaning System | A3 |  | S | △A | 2021-09-28 |  |  | △B | 2022-01-11 | [10 empty] | △0C | 2022-03-24 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 14-Oct | 7-Dec | #0002 | 3 | 11-Jan | 4-Mar | #0013 | 2 | [8 empty] | 24-Mar | 23-Jun | #0020 | 2
6 | VP-TEP-S0002-PI-GA-0005 | Outline Drawing of Debris Filter for Condenser | A3 |  | S | △A | 2021-09-28 |  |  | △B | 2022-01-11 | [10 empty] | △0C0C | 2022-03-24 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 14-Oct | 7-Dec | #0002 | 3 | 11-Jan | 4-Mar | #0013 | 2 | [8 empty] | 24-Mar | 23-Jun | #0020 | 2
7 | VP-TEP-S0002-PI-GA-0006 | Outline Drawing for Aux. Debris Filter | A3 |  | S | △A | 2021-09-28 |  |  | △B | 2022-01-11 | [10 empty] | △000C | 2022-03-24 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 14-Oct | 7-Dec | #0002 | 3 | 11-Jan | 4-Mar | #0013 | 2 | [8 empty] | 24-Mar | 23-Jun | #0020 | 2
8 | VP-TEP-S0002-PI-GA-0007 | Name Plate Drawing List | A3 |  | S | △A | 2021-09-28 |  |  | △B | 2022-03-24 | [10 empty] | △0 | 2022-07-15
[5 empty] | A | 11-Jan | 4-Mar | #0013 | 3 | 24-Mar | 2-Jun | #0019 | 2
9 | VP-TEP-S0002-PR-PI-0001 | P&I Diagram for Debris Filter & Tube Cleaning System | A3 |  | S | △A | 2021-09-28 |  |  | △B | 2022-01-11 | [10 empty] | △0 | 2022-03-24 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 18-Oct | 15-Dec | #0004 | 3 | 11-Jan | 4-Mar | #0013 | 2 | [8 empty] | 24-Mar | 23-Jun | #0020 | 1
10 | VP-TEP-S0002-PR-PI-0002 | P&I Diagram for Aux. Debris Filter | A3 |  | S | △A | 2021-09-28 |  |  | △B | 2022-01-11 | [10 empty] | △0 | 2022-03-24 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 18-Oct | 15-Dec | #0004 | 3 | 11-Jan | 4-Mar | #0013 | 2 | [8 empty] | 24-Mar | 23-Jun | #0020 | 2
11 | VP-TEP-S0002-RO-DS-0001 | Ball Recirculation Pump & Motor Drawing and Data Sheet | A4 |  | S | △A | 2022-02-04 |  |  | △B | 2022-04-18 | [10 empty] | △0 | 2022-07-08
[5 empty] | A | 3-Feb | 17-Mar | #0015 | 3 | 18-Apr | 23-Jun | #0027 | 2
12 | VP-TEP-S0002-ST-DS-0001 | Technical Data Sheet | A4 |  | S | △A | 2021-09-28 |  |  | △B | 2022-02-03 | [10 empty] | △0 | 2022-04-18
[5 empty] | A | 12-Nov | 5-Jan | #0008 | 3 | 3-Feb | 17-Mar | #0015 | 2 | [8 empty] | 18-Apr |  | #0026
13 | VP-TEP-S0002-ST-DS-0002 | Guarantee Data Sheet | A4 |  | S | △A | 2021-09-28 |  |  | △B | 2022-01-11 | [10 empty] | △0 | 2022-04-05 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 10-Nov | 5-Jan | #0007 | 3 | 11-Jan | 16-Feb | #0012 | 1 | [8 empty] | 24-Mar | 23-Jun | #0020 | 1
14 | VP-TEP-S0002-ST-LI-0002 | Equipment List | A4 |  | S | △A | 2021-10-30 |  |  | △B | 2022-01-11 | [10 empty] | △0 | 2022-04-05 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 10-Nov | 5-Jan | #0007 | 3 | 11-Jan | 16-Feb | #0012 | 2 | [8 empty] | 24-Mar | 23-Jun | #0020 | 1
15 | VP-TEP-S0002-ST-LI-0003 | Lubricant List | A4 |  | S | △A | 2021-10-30 | [14 empty] | △0 | 2022-04-20 | [6 empty] | △F | 2022-07-08
[5 empty] | A | 10-Nov | 5-Jan | #0007 | 1 | [12 empty] | 20-Apr | 13-Jun | #0029 | 2
16 | VP-TEP-S0002-ST-LI-0004 | Spare parts List of Start-up & Commissioning | A4 |  | S | △A | 2021-10-30 |  |  | △B | 2022-01-11 | [10 empty] | △0 | 2022-04-05 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 10-Nov | 5-Jan | #0007 | 3 | 11-Jan | 16-Feb | #0012 | 2 | [8 empty] | 24-Mar | 23-Jun | #0020 | 1
17 | VP-TEP-S0002-ST-LI-0005 | Spare parts List of 2-Years | A4 |  | S | △A | 2021-10-30 |  |  | △B | 2022-01-11 | [10 empty] | △0 | 2022-04-05 | [6 empty] | △F | 2022-07-15
[5 empty] | A | 10-Nov | 5-Jan | #0007 | 3 | 11-Jan | 16-Feb | #0012 | 2 | [8 empty] | 24-Mar | 23-Jun | #0020 | 1
18 | VP-TEP-S0002-EL-SD-0001 | Single Line Diagram for Debris Filter & Tube Cleaning System | A3 |  | S | △A | 2021-10-20 |  |  | △B | 2022-01-11 |  |  | △C | 2022-04-13
[5 empty] | A | 15-Oct | 13-Jan | #0003 | 3 | 28-Dec | 17-Mar | #0011 | 3 | 13-Apr |  | #0022
19 | VP-TEP-S0002-EL-SQ-0001 | Schematic Diagram for Debris Filter & Tube Cleaning System | A3 |  | S | △A | 2021-10-20 |  |  | △B | 2022-01-11 |  |  | △C | 2022-04-13
[5 empty] | A | 15-Oct | 13-Jan | #0003 | 3 | 28-Dec | 17-Mar | #0011 | 3 | 13-Apr |  | #0022
20 | VP-TEP-S0002-EL-SQ-0002 | Control Logic & Loop Diagram for Debris Filter & Tube Cleaning System | A3 |  | S | △A | 2022-02-28
[5 empty] | A | 28-Feb |  | #0018
21 | VP-TEP-S0002-EL-CS-0001 | Wiring Connection Diagram for Debris Filter & Tube Cleaning System | A3 |  | S | △A | 2021-10-20 |  |  | △B | 2021-12-28 |  |  | △C | 2022-04-13
[5 empty] | A | 15-Oct | 13-Jan | #0003 | 3 | 28-Dec | 17-Mar | #0011 | 3 | 13-Apr |  | #0022
22 | VP-TEP-S0002-EL-GA-0001 | Control Panel Outline Drawing for Debris Filter & Tube Cleaning System | A3 |  | S | △A | 2021-10-20 |  |  | △B | 2021-12-28 | [10 empty] | △0 | 2022-04-13 | [6 empty] | △F | 2022-07-20
[5 empty] | A | 15-Oct | 13-Jan | #0003 | 3 | 28-Dec | 17-Mar | #0011 | 2 | [8 empty] | 13-Apr | 23-Jun | #0023 | 2
23 | VP-TEP-S0002-EL-LI-0001 | Electrical Load List for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-10-20 |  |  | △B | 2021-12-28 |  |  | △C | 2022-04-13
[5 empty] | A | 15-Oct | 13-Jan | #0003 | 3 | 28-Dec | 17-Mar | #0011 | 3 | 13-Apr |  | #0022
24 | VP-TEP-S0002-EL-LI-0002 | DCS I/O List(Hard-Wired) for Debris Filter & Tube Cleaning System | A3 |  | S | △A | 2021-10-20 |  |  | △B | 2021-12-28 |  |  | △C | 2022-04-13
[5 empty] | A | 15-Oct | 13-Jan | #0003 | 3 | 28-Dec | 17-Mar | #0011 | 3 | 13-Apr |  | #0022
25 | VP-TEP-S0002-EL-LI-0003 | LCD graphic diagram for Debris Filter & Tube Cleaning System | A3 |  | S | △A | 2022-02-28
[5 empty] | A | 28-Feb |  | #0018
26 | VP-TEP-S0002-EL-LI-0004 | PLC I/O List for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2022-04-13
[5 empty] | A | 13-Apr |  | #0022
27 | VP-TEP-S0002-EL-LI-0005 | DCS I/O List(Communication Link) for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2022-04-13
[5 empty] | A | 13-Apr |  | #0022
28 | VP-TEP-S0002-EL-CF-0001 | Control System Configuration Diagram for Debris Filter & Tube Cleaning System | A3 |  | S | △A | 2021-10-20 |  |  | △B | 2021-12-28 |  |  | △C | 2022-04-13
[5 empty] | A S | 15-Oct | 13-Jan | #0003 | 3 | 28-Dec | 17-Mar | #0011 | 3 | 13-Apr |  | #0022
29 | VP-TEP-S0002-IN-LI-0001 | Instrument List and Data Sheet for Debris Filter & Tube Cleaning System | A4 |  |  | △A | 2021-10-20 |  |  | △B | 2021-12-28 | [10 empty] | △0 | 2022-04-13 | [6 empty] | △F | 2022-07-20
[5 empty] | A | 15-Oct | 13-Jan | #0003 | 4 | 28-Dec | 17-Mar | #0011 | 2 | [8 empty] | 13-Apr | 23-Jun | #0023 | 1
30 | VP-TEP-S0002-IN-LI-0002 | Instrument set point & alarm list for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2022-02-28
[5 empty] | A | 28-Feb |  | #0018
31 | VP-TEP-S0002-EL-DS-0001 | Motor and Electrical Equipment Data Sheet for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-10-20 |  |  | △B | 2021-12-28 |  |  | △C | 2022-04-13
[5 empty] | A | 15-Oct | 13-Jan | #0003 | 4 | 28-Dec | 17-Mar | #0011 | 3 | 13-Apr |  | #0022
32 | VP-TEP-S0002-ST-PR-0001 | Painting Procedure for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-09-28 |  |  | △B | 2022-02-21 |  |  | △C | 2022-04-18 |  |  | △D | 2022-07-08
[5 empty] | A | 3-Nov | 15-Dec | #0006 | 3 | 21-Feb | 17-Mar | #0017 | 3 | 18-Apr | 14-Jun | #0025 | 3
33 | VP-TEP-S0002-ST-PR-0002 | Rubber Lining Procedure for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-10-30 |  |  | △B | 2022-02-21 |  |  | △C | 2022-04-18 | [6 empty] | △0 | 2022-07-15
[5 empty] | A | 3-Nov | 15-Dec | #0006 | 3 | 21-Feb | 17-Mar | #0017 | 3 | 18-Apr | 14-Jun | #0025 | 1
34 | VP-TEP-S0002-ST-PR-0003 | WPS & PQR for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-10-30 |  |  | △B | 2022-03-25 | [10 empty] | △0 | 2022-07-15
[5 empty] | A | 3-Nov | 15-Dec | #0006 | 4 | 25-Mar | 3-Jun | #0021 | 2
35 | VP-TEP-S0002-ST-PR-0004 | Packing Procedure for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-09-28 |  |  | △B | 2022-02-21 | [10 empty] | △0 | 2022-04-15 | [6 empty] | △F | 2022-07-08
[5 empty] | A | 3-Nov | 15-Dec | #0006 | 3 | 21-Feb | 17-Mar | #0017 | 1 | [8 empty] | 15-Apr | 13-Jun | #0024 | 2
36 | VP-TEP-S0002-QA-PL-0001 | Inspection Test Plan for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-10-20 |  |  | △B | 2022-02-15 |  |  | △C | 2022-04-05 | [6 empty] | △0 | 2022-06-24
[5 empty] | A | 18-Nov | 3-Jan | #0009 | 4 | 15-Feb | 3-Mar | #0016 | 4 | 24-Mar | 2-Jun | #0019 | 2
37 | VP-TEP-S0002-QA-PR-0001 | Inspection Test Procedure for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-10-20 |  |  | △B | 2022-02-15 |  |  | △C | 2022-04-05 | [6 empty] | △0 | 2022-07-15
[5 empty] | A | 18-Nov | 3-Jan | #0009 | 4 | 15-Feb | 3-Mar | #0016 | 3 | 24-Mar | 2-Jun | #0019 | 2
38 | VP-TEP-S0002-QA-PR-0002 | HydroTest Procedure for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-10-20 |  |  | △B | 2022-02-15 | [10 empty] | △0 | 2022-04-18
[5 empty] | A | 18-Nov | 3-Jan | #0009 | 4 | 15-Feb | 3-Mar | #0016 | 1 | [8 empty] | 18-Apr |  | #0026
39 | VP-TEP-S0002-QA-PR-0003 | Non-Destructive Examination Procedure for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-10-20 | [14 empty] | △0 | 2022-04-18
[5 empty] | A | 18-Nov | 3-Jan | #0009 | 1 | [12 empty] | 18-Apr |  | #0026
40 | VP-TEP-S0002-PM-LI-0001 | Sub Vendors List for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2021-10-20 |  |  | △B | 2022-01-18 |  |  | △C | 2022-04-20
[5 empty] | A | 27-Oct | 17-Dec | #0005 | 3 | 18-Jan | 17-Mar | #0014 | 2 | 20-May |  | #0031
41 | VP-TEP-S0002-ST-RE-0001 | Operation and Maintenance Manual for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2022-04-20 | [14 empty] | △0 | 2022-07-08
[5 empty] | A | 20-Apr | 23-Jun | #0028 | 2
42 | VP-TEP-S0002-ST-PR-0005 | Welder List and Welder Qualification Record | A4 |  | S | △A | 2021-11-03 | [14 empty] | △0 | 2022-04-15 | [7 empty] | △F | 2022-07-08
[5 empty] | A | 3-Nov | 15-Dec | #0006 | 1 | [12 empty] | 15-Apr | 13-Jun | #0024 | 1
43 | VP-TEP-S0002-QA-PR-0004 | PMI Procedure | A4 |  | S | △A | 2021-12-30 |  |  | △B | 2022-03-15 |  |  | △C | 2022-03-24 |  |  | △D | 2022-06-24
[5 empty] | A | 18-Nov | 3-Jan | #0009 | 4 | 15-Feb | 3-Mar | #0016 | 3 | 24-Mar | 2-Jun | #0019 | 3
44 | VP-TEP-S0002-QA-PR-0005 | FAT Procedure for electic/instrument | A4 |  | S | △A | 2022-02-20 | [14 empty] | △0 | 2022-04-18
[5 empty] | A | 18-Nov | 3-Jan | #0009 | 1 | [12 empty] | 18-Apr |  | #0026
45 | VP-TEP-S0002-QA-PR-0008 | Leakage Test Procedure for Pump Skid | A4 |  | S | △A | 2022-03-24 |  |  | △B | 2022-06-24
[5 empty] | A | 24-Mar | 2-Jun | #0019 | 3
46 | VP-TEP-S0002-QA-PR-0007 | Material Certificates / Inspection and Test Report | A4 |  | S | △A | 2022-09-30
A
47 | VP-TEP-S0002-ST-CA-0001 | Strength Calculation | A4 |  | S | △A | 2021-12-30 |  |  | △B | 2022-06-24
[5 empty] | A | 28-Dec | 27-Jan | #0010 | 3
48 | VP-TEP-S0002-ST-RE-0002 | System Description for Debris Filter & Tube Cleaning System | A4 |  | S | △A | 2022-02-03 | [14 empty] | △0 | 2022-04-13 | [7 empty] | △F | 2022-07-20
[5 empty] | A | 3-Feb | 17-Mar | #0015 | 2 | [12 empty] | 13-Apr | 23-Jun | #0023 | 1
49 | VP-TEP-S0002-PI-GA-0008 | 3D Model | - |  | S | △A | 2022-04-28 | [14 empty] | △0 | 2022-07-08
[5 empty] | A | 28-Apr | 23-Jun | #0030 | 2
|  | … |  |  | S | △
A
|  | … |  |  | S | △
A
51 |  | … |  |  | S | △
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [8 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | Tongyeong Eco Power LNG Power Plant Project |  |  | PROJECT NO | [16 empty] | ISSUED |  |  | 0 | [10 empty] | 2
P/O NO. |  |  |  |  | DATE | [19 empty] | 1 | [10 empty] | 3