## Table 2
VENDOR NAME AND LOGO
VENDOR PRINT INDEX & SCHEDULE
NAME OF EQUIPMENT:Service Gas System | [6 empty] | ITEM NO. :
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-S0006-ST-LI-0001 | Vendor Print Index & Schedule |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
2 | VP-TEP-S0006-ST-LI-0002 | Sub-Vendor List |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
3 | VP-TEP-S0006-PM-MA-0001 | Installation & Operation Manual |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
4 | VP-TEP-S0006-ST-LI-0003 | Spare Part List for Commissioning |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
5 | VP-TEP-S0006-ST-LI-0004 | Spare Part List for 2 years operation |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
6 | VP-TEP-S0006-ST-LI-0005 | Special Tools List |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
7 | VP-TEP-S0006-ST-LI-0006 | Equipment List |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
8 | VP-TEP-S0006-ST-OT-0001 | General Arrangement Drawing |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
9 | VP-TEP-S0006-ST-PI-0001 | P&I Diagram |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
10 | VP-TEP-S0006-ST-OT-0002 | Outline Drawing for N2/H2/CO2 Gas Bottle Rack |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
11 | VP-TEP-S0006-ST-OT-0003 | Outline Drawing for N2/H2 Gas Reducing Skid |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
12 | VP-TEP-S0006-ST-OT-0004 | Outline Drawing for Component Item |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
13 | VP-TEP-S0006-ST-OT-0005 | Name & Tag Plate Drawing |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
14 | VP-TEP-S0006-ST-DS-0001 | Data Sheet |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
15 | VP-TEP-S0006-ST-LI-0007 | Instrument List |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
16 | VP-TEP-S0006-QA-PL-0001 | Inspection and Test Plan(ITP) |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
17 | VP-TEP-S0006-QA-PR-0001 | Inspection and Test Procedure |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
18 | VP-TEP-S0006-QA-OT-0002 | Inspection and Test Report |  |  | S | FOR APPROVAL IN: 2022-08-05
A
19 | VP-TEP-S0006-QA-PR-0002 | Weld Procedure (WPS&PQR) |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
20 | VP-TEP-S0006-ST-PR-0001 | Painting Specification and Painting Procedure |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
21 | VP-TEP-S0006-ST-PR-0002 | Packing Procedure |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
22 | VP-TEP-S0006-QA-PR-0003 | NDE Procedure |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
23 | VP-TEP-S0006-QA-PL-0002 | Quality Assurance Plan and Manual |  |  | S
[5 empty] | A | FOR APPROVAL OUT: 05-13
24 | VP-TEP-S0006-PM-DB-0001 | MANUFACTURING DATA BOOK |  |  | S
A
Note : |  | S/A : Schedule/Actual | RST : Result of V/P Review |  |  | FOR APPROVAL IN: N : Approved As Noted; FOR APPROVAL IN: RE : Reviewed with no comment; FOR FINAL IN: FNL : Final
|  | IN/OUT : Incoming/Outgoing | A: Approved |  |  | FOR APPROVAL IN: R : Rejected; FOR APPROVAL IN: RFC : Return For Correction; FOR FINAL IN: TDB : Technical Data Book
PROJECT NAME |  | TEP Project |  |  | PROJECT NO | FOR APPROVAL IN: ISSUED; FOR APPROVAL RST: 0; FINAL TDB: 2
P/O NO. |  |  |  |  | DATE | FOR APPROVAL RST: 1; FINAL TDB: 3