## Table 7
NAME OF EQUIPMENT:Silencer
NO | DOCUMENT NO | DOCUMENT TITLE | SIZE | PAGE | S/A | FOR APPROVAL | [19 empty] | FOR FINAL |  |  |  | FINAL |  | REMARK
[6 empty] | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | IN | OUT | TR# | RST | FNL | TDB
1 | VP-TEP-S0008-ST-LI-0001 | Vendor Print Index & Schedule | A4 | 2 | S |  | 2022-05-13 |  |  | 2022-07-22
[5 empty] | A | 5-12 | 7/8 | 1 | 2 | 7/13 | 4
2 | VP-TEP-S0008-ST-LI-0002 | Sub-Vendor List | A4 | 2 | S |  | 2022-05-13 |  |  | 2022-07-07
[5 empty] | A | 5-12 | 6-23 | 2 | 1 | 7/5 | 3
3 | VP-TEP-S0008-ST-DS-0001 | Data Sheet | A4 | 3 | S |  | 2022-05-13 |  |  | 2022-07-22
[5 empty] | A | 5-12 | 7/8 | 1 | 2 | 7/13 | 4
4 | VP-TEP-S0008-QA-PL-0001 | Inspection & Test Plan | A4 | 2 | S |  | 2022-05-13 |  |  | 2022-07-07
[5 empty] | A | 5-12 | 6-23 | 2 | 2 | 7/5 | 3
5 | VP-TEP-S0008-ST-PR-0001 | Inspection & Test Procedure | A4 | 9 | S |  | 2022-05-13 |  |  | 2022-07-07
[5 empty] | A | 5-12 | 6-23 | 2 | 2 | 7/5 | 3
6 | VP-TEP-S0008-ST-PR-0002 | NDE(MT) Procedure | A4 | 28 | S |  | 2022-05-13 |  |  | 2022-07-07
[5 empty] | A | 5-12 | 6-23 | 2 | 2 | 7/5 | 3
7 | VP-TEP-S0008-ST-PR-0003 | WPS & PQR(with Welding Map) | A4 | 10 | S |  | 2022-05-13 |  |  | 2022-07-07
[5 empty] | A | 5-12 | 6-23 | 2 | 4 | 7/5 | 3
8 | VP-TEP-S0008-ST-PR-0004 | Packing Procedure | A4 | 6 | S |  | 2022-05-13 |  |  | 2022-07-07
[5 empty] | A | 5-12 | 6-23 | 2 | 2 | 7/5 | 3
9 | VP-TEP-S0008-ST-PR-0005 | Painting Procedure | A4 | 6 | S |  | 2022-05-13 |  |  | 2022-07-07
[5 empty] | A | 5-12 | 6-23 | 2 | 2 | 7/5 | 3
10 | VP-TEP-S0008-ST-CA-0001 | Strength Calculation Sheet | A4 | 6 | S |  | 2022-05-13 |  |  | 2022-07-22
[5 empty] | A | 5-12 | 7/8 | 1 | 1 | 7/13 | 4
11 | VP-TEP-S0008-ST-OT-0001 | General Arrangement Drawing (14LBG10BS001) | A3 | 2 | S |  | 2022-05-13 |  |  | 2022-07-22
[5 empty] | A | 5-12 | 7/8 | 1 | 2 | 7/13 | 4
12 | VP-TEP-S0008-ST-OT-0002 | General Arrangement Drawing (14LCM10BS001) | A3 | 2 | S |  | 2022-05-13 |  |  | 2022-07-22
[5 empty] | A | 5-12 | 7/8 | 1 | 2 | 7/13 | 4
13 | VP-TEP-S0008-ST-OT-0003 | Name Plate Drawing | A3 | 2 | S |  | 2022-05-13 |  |  | 2022-07-22
[5 empty] | A | 5-12 | 7/8 | 1 | 1 | 7/13 | 4
14 | VP-TEP-S0008-PM-DB-0001 | Maunufacturing Data Book | A4 |  | S | 2022-08-30
A
Note : |  | S/A : Schedule/Actual IN/OUT : Incoming/Outgoing | RST : Result of V/P Review A: Approved | [6 empty] | N : Approved As Noted R : Rejected | [7 empty] | RE : Reviewed with no comment RFC : Return For Correction | [7 empty] | FNL : Final TDB : Technical Data Book
PROJECT NAME |  | TEP Project |  |  | PROJECT NO | [16 empty] | ISSUED |  |  | 0 | 2022-05-12 |  |  |  |  | 2 | 2022-07-13
P/O NO. |  | PO-TEP-S-0008-P |  |  | DATE |  |  |  |  | 2002-05-12 | [14 empty] | 1 | 2022-07-05 |  |  |  |  | 3