## VPI&S_Fluff Transfer
Vendor Print Index & Schedule
No. | Document No. | Document Title | Transmittal No. | Category "A/R/I" (For Approval / Review / Information) | Key VP | P/A | Issued for Approval | [11 empty] | Issue for Final | [7 empty] | Final |  |  |  | Final Data Book |  |  |  | Remark
[7 empty] | Rev. A |  |  |  | Rev. B |  |  |  | Rev. C |  |  |  | Rev. 0 |  |  |  | Rev. 1 |  |  |  | N(for final)+1 |  |  |  | Later
[7 empty] | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST | Out | In | TR# | RST
General Documents
1 | VP-TEP-S0011-ST-LI-0001 | Vendor Print Index and Schedule |  |  |  | P | 22년3월31일 |  |  |  | 22년7월15일
[6 empty] | A | 22년3월31일 | 22년5월 11일 | 0001 | 3 | 22년7월14일 |  | 0005
2 | VP-TEP-S0011-ST-LI-0002 | Sub vendor list |  |  |  | P | 22년3월31일 |  |  |  | 22년6월29일
[6 empty] | A | 22년3월31일 | 22년5월 11일 | 0001 | 2 | 22년7월14일 |  | 0005
3 | VP-TEP-S0011-ST-LI-0003 | Spare parts List |  |  |  | P | 22년8월12일
A
4 | VP-TEP-S0011-ST-CA-0001 | strength calculation sheet |  |  |  | P | 22년4월08일
[6 empty] | A | 22년4월06일 | 22년6월 09일 | 0002 | 3 | 22년7월14일 |  | 0005
5 | VP-TEP-S0011-ST-OT-0001 | General Arrangement Drawing |  |  |  | P | 22년3월31일 |  |  |  | 22년6월29일
[6 empty] | A | 22년3월31일 | 22년5월 11일 | 0001 | 3 | 22년7월14일 |  | 0005
P
A
Rotating Documents
6 | VP-TEP-S0011-ST-OT-0003 | Specification for Induction motor |  |  |  | P | 22년4월21일 |  |  |  | 22년7월29일
[6 empty] | A | 22년4월21일 | 22년7월 08일 | 0004 | 2
7 | VP-TEP-S0011-ST-OT-0004 | Specification for Pump |  |  |  | P | 22년4월21일 |  |  |  | 22년7월29일
[6 empty] | A | 22년4월21일 | 22년7월 08일 | 0004 | 2
Stationary Documents
P
A
Piping Documents
8 | VP-TEP-S0011-ST-PI-0001 | P&I Diagram |  |  |  | P | 22년3월31일
[6 empty] | A | 22년3월31일 | 22년5월 11일 | 0001 | 3 | 22년7월22일 |  | 0006
Electrical & Instrument Documents
9 | VP-TEP-S0011-ST-OT-0002 | Electrical Circuit Diagram |  |  |  | P | 22년4월16일 |  |  |  | 22년7월29일
[6 empty] | A | 22년4월20일 | 22년7월 08일 | 0003 | 2
PMI Test
10 | VP-TEP-S0011-ST-PR-0006 | PMI Procedure |  |  |  | P
[6 empty] | A | 22년7월14일 |  | 0005
Hydrostatic Test Procedure
11 | VP-TEP-S0011-ST-PR-0004 | Shop Inspection & Test Procedure |  |  |  | P | 22년4월08일 |  |  |  | 22년7월06일
[6 empty] | A | 22년4월06일 | 22년6월 09일 | 0002 | 4 | 22년7월22일 |  | 0006
Quality Control Documents
12 | VP-TEP-S0011-ST-PR-0001 | Painting Procedure |  |  |  | P | 22년3월31일 |  |  |  | 22년6월29일
[6 empty] | A | 22년3월31일 | 22년5월 11일 | 0001 | 3 | 22년7월14일 |  | 0005
13 | VP-TEP-S0011-ST-PR-0002 | WPS / PQR |  |  |  | P | 22년4월05일 |  |  |  | 22년7월06일
[6 empty] | A | 22년4월06일 | 22년6월 09일 | 0002 | 4 | 22년7월14일 |  | 0005
14 | VP-TEP-S0011-ST-PR-0003 | NDE Procedure |  |  |  | P | 22년4월22일 |  |  |  | 22년7월06일
[6 empty] | A | 22년4월06일 | 22년6월 09일 | 0002 | 4 | 22년7월14일 |  | 0005
15 | VP-TEP-S0011-ST-PL-0001 | Shop Inspection & Test Plan |  |  |  | P | 22년4월08일 |  |  |  | 22년7월06일
[6 empty] | A | 22년4월06일 | 22년6월 09일 | 0002 | 4 | 22년7월14일 |  | 0005
16 | VP-TEP-S0011-ST-PR-0007 | Packing Procedure |  |  |  | P
[6 empty] | A | 22년7월14일 |  | 0005
17 | VP-TEP-S0011-ST-RE-0001 | Inspection Report |  |  |  | P | 22년10월30일
A
Project Name |  | TEP Project |  |  |  | P/O NO. |  |  |  | PO-TEP-S-0011-P | [8 empty] | Doc. No. | VP-TEP-S0011-ST-LI-0001 | [5 empty] | Rev.B
Vendor Name |  | SOLGE
Note
1. Abbreviation - RST: Result of V/P Review, A: Approved, C: Approved with Comments, R: Rjected, RS: Resubmit, FI: For Information
2. Vendor shall submit the revised document within 14 calendar days after receive purchaser's response.